## MSI MasterList
No | Area | Reporting Date | Date Resolved | Cycle Time | Reported By | Observed Point | Severity | Issue | Required To Fix by D2 (20-Aug-18) | Enhancement | ID Team | Green Light | Convert to test case | Occurrence % | Root Cause | Solution | Target Close Date | PIC | Close Date on version? | Status IOS | Status Andriod | Validity | MSI comment | Validity (Auctus) | Analysis (Auctus) | Auctus comment | comment | Planned Close Date | Links | Next To Do | reply comment | 工作量 | APP feedback (XiangYang) 7 June 2018 | Feedback SK (8 June 2018)(1235) | Feedback SK (13 June 2018)(1236) | Feedback SK (16 June 2018)(1237) | Feedback SK (17 June 2018)(1238) | Android 1.9 3 July | Android 2.0 4 July | Android 2.2 7 July | Android 2.4 24 July
1 | On Boarding | 2017-12-20 | 2018-02-08 | 37 | FT | Android V1 | 2 | WELCOME screen is not same as VI design 20171130. The link is missing | [5 empty] | 100% |  |  |  |  | 2018-02-08 | N/A | Closed | Yes |  | Yes | Temporary release in Feb
2 | On Boarding | 2017-12-20 | 2018-02-08 | 37 | FT | Android V1 | 2 | Terms & Privacy Policy screen is missing | [5 empty] | 100% |  |  |  |  | 2018-02-08 | N/A | Closed | Yes |  | Yes | Temporary release in Feb
3 | On Boarding | 2017-12-20 | 2018-02-08 | 37 | FT | Android V1 | 2 | During onboarding if user press LEAVE SETUP there shall be a warning message pop up. This is missing. | [5 empty] | 100% |  |  |  |  | 2018-02-08 | N/A | Closed | Yes |  | Yes | Temporary release in Feb
4 | On Boarding | 2017-12-20 | 2018-07-05 | 142 | FT | Android V1 | 2 | PHONE SETUP: the message to ask user to turn on bluetooth and location service is missing. Is Bluetooth will turn on automatically? | [5 empty] | 100% |  |  |  |  | 7/5/2018 Andriod V2.0 | N/A | Closed | Yes |  | Yes | Temporary release in Feb
5 | On Boarding | 2017-12-20 | 2018-02-08 | 37 | FT | Android V1 | 2 | This is not done: if the radio is not found within 30 seconds, the pairing activity will be stopped and "RETRY" button will be eN/Abled, the user can press "RETRY" to pair again. | [5 empty] | 100% |  |  |  |  | 2018-02-08 | N/A | Closed | Yes |  | Yes | Temporary release in Feb
6 | Hamburger Menu | 2017-12-21 | 2018-02-14 | 40 | FT | Android V1 | 1 | Radio is turned off but in APP still show 'connected' | [5 empty] | 100% |  | This is normal within 30s. APP will only update up to 30s period. |  |  |  | N/A | Closed | Yes |  | Yes | Temporary release in Feb |  | Now always showing "connecting".
7 | Hamburger Menu | 2017-12-21 | 2018-07-05 | 141 | FT | Android V1 | 3 | Typo 'Conected' | [5 empty] | 100% |  |  |  |  | 7/5/2018 Andriod V2.0 | N/A | Closed | Yes |  | Yes | Temporary release in Feb
8 | On Boarding | 2017-12-22 | 2018-07-05 | 140 | FT | Android V1 | 3 | TALKABOUT RADIO SETUP: The radio antenN/A is overlap with wordings. | [5 empty] | 100% |  |  |  |  | 7/5/2018 Andriod V2.0 | N/A | Closed | Yes |  | Yes | Temporary release in Feb
9 | On Boarding | 2017-12-22 | 2018-02-08 | 35 | FT | Android V1 | 2 | PAIRING: The searching for radio shall timed out but it is not. | [5 empty] | 100% |  |  |  |  | 2018-02-08 | N/A | Closed | Yes |  | Yes | Temporary release in Feb
10 | Chat | 2017-12-27 | 2018-02-08 | 32 | SK | Android V1.2 | 2 | Shout message received no notification | [5 empty] | 100% |  |  |  |  | 2018-02-08 | N/A | Closed | Yes |  | Yes | Temporary release in Feb
11 | Bluetooth Connection | 2017-12-27 | 2018-02-14 | 36 | SK | Android V1.2 | 3 | Bluetooth connection sometime will auto disconnect. | [5 empty] | 100% |  |  | 2018-03-23 |  |  | N/A | Closed | Yes |  | Yes | Temporary release in Feb |  | to be monitor. | [9 empty] | .
12 | Chat | 2017-12-27 | 2018-02-08 | 32 | SK | Android V1.2 | 2 | Shout N/AME still remain as "Tom Brown" even User log in as "Dennis". | [5 empty] | 100% |  |  |  |  | 2018-02-08 | N/A | Closed | Yes |  | Yes | Temporary release in Feb
13 | Chat | 2017-12-27 | 2018-02-08 | 32 | SK | Android V1.2 | 2 | "<-" back button cannot function in "MY MEMBERS" tab. | [5 empty] | 100% |  |  |  |  | 2018-02-08 | N/A | Closed | Yes |  | Yes | Temporary release in Feb
14 | Bluetooth Connection | 2017-12-28 | 2018-07-09 | 138 | SK | Android V1.2 | 1 | After Bluetooth disconnect, Radio still showing the bluetooth icon blinking. | [5 empty] | 100% |  | Radio issue |  |  | 7/9/2018 Andriod V2.2 | N/A | Closed | Yes |  | Yes | Temporary release in Feb
15 | Bluetooth Connection | 2017-12-29 | 2018-07-24 | 148 | FT | iOS V1.0(5), Android | 1 | After totally close down APP then re-launch APP, the BT connection is not able to connect back. | [5 empty] | 100% |  |  |  |  | 2/8/2018 24 July 2018 Andriod V2.4 | Closed | Closed | Yes |  | Yes | Temporary release in Feb
16 | Bluetooth Connection | 2017-12-29 | 2018-05-27 | 106 | FT | iOS V1.0(5), Android | 1 | After power off radio, the connection status in app still showing 'connected' | [5 empty] | 80% |  | This is normal within 30s. APP will only update up to 30s period. |  |  | 5/27/2018 IOS V1.2 (1227) 24 July 2018 Andriod V2.4 | Closed | Closed | Yes |  | Yes | Temporary release in Feb
17 | On Boarding | 2017-12-29 | 2018-07-24 | 148 | FT | iOS V1.0(5), Android | 2 | Terms & Privacy Policy screen is missing | [5 empty] | 100% |  |  |  |  | 2/8/2018 24 July 2018 Andriod V2.4 | Closed | Closed | Yes |  | Yes | Temporary release in Feb
18 | Radio Settings | 2018-01-02 | 2018-07-24 | 146 | FT | iOS V1.0(5), Android | 2 | This statement appear in Maroon Bells URD but it not implemeted in APP: 同时在没有外部耳机时，只能设置ivox等级,在有外部耳机时，只能设置Vox等级 | [5 empty] | 100% |  | Radio side need to make change | 2018-03-23 |  | IOS V1.2 (1236) 24 July 2018 Andriod V2.4 | Closed | Closed | Yes |  | Yes | Temporary release in Feb | [7 empty] | IVox /Vox information can be set, but there is no screen on the radio
19 | On Boarding | 2018-01-04 | 2018-07-24 | 144 | FT | iOS V1.0(5) | 1 | Without getting and key in verification code, I can enter the APP as well. | [5 empty] | 100% |  |  | 2018-03-23 |  | 5/28/2018 IOS V1.2 (1228) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
20 | On Boarding | 2018-01-05 | 2018-02-08 | 25 | FT | iOS V1.0(10) | 2 | Users MUST scroll down all the way, AGREE ALL button will be active and they can accept the policy & terms. | [5 empty] | 100% |  |  |  |  | 2018-02-08 | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
21 | On Boarding | 2018-01-05 | 2018-05-28 | 102 | FT | iOS V1.0(10) | 1 | Phone Bluetooth is already turned on but the 'Permission' to turn on bluetooth still appear and user must click GO TO SETTINGS else not able to proceed. | [5 empty] | 100% |  |  | 2018-03-23 |  | 5/28/2018 IOS V1.2 (1228) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
22 | Map | 2018-01-05 | 2018-02-14 | 29 | FT | iOS V1.0(10) | 1 | Map view show me Shenzhen map. Maybe due to I turn off location during onboarding. I turn on the location again, map still show shenzhen. | [5 empty] | 100% |  | When network available, but location service is off, APP will show a default map. Default map please set to North America. When network not available, and location service is off. Screen will be blank. POP up message shall show. Please refer to latest wireframes/VI. When user want to save track, share location or save pin but location service is turned off, pop up message shall show. | 2018-03-23 |  | IOS V1.2 (1236) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | - | [5 empty] | Results will be seen in the latest software version
23 | Map | 2018-01-05 | 2018-02-08 | 25 | FT | iOS V1.0(10) | 2 | The last icon on the right bar, the function is wrong. | [5 empty] | 100% |  |  |  |  | 2018-02-08 | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
24 | Chat | 2018-01-15 | 2018-02-08 | 19 | FT | iOS V1.0(12) | 2 | I have add member 'i6' to My Members. When 1-1 message received, the contact N/Ame does not show 'i6', and shows *1238 (which is the ID). | [5 empty] | 100% |  |  |  |  | 2018-02-08 | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
25 | Chat | 2018-01-15 | 2018-05-31 | 99 | Marjon | iOS V1.0(11) | 2 | Some messages take long to receive and won't show message receive notification even though they were received by other radio | [5 empty] | 100% |  | Radio issue |  |  | 5/31/2018 IOS V1.2 (1231) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
26 | My Members | 2018-01-15 | 2018-02-14 | 23 | Marjon | iOS V1.0(12) | 2 | Missing search function in the Search phone contacts (also the title and back arrow are overlapping). | [5 empty] | 100% |  |  |  |  | IOS V1.2 (1236) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | - | [5 empty] | The main problem is the need to add new search capabilities, which will be resolved when added
27 | Chat | 2018-01-15 | 2018-05-27 | 95 | Marjon | iOS V1.0(12) | 2 | How can you resend a message if not received. If we don't have easy way to resend need to develop, we don't want to rely on user having to retype. | [5 empty] | 100% |  | New feature | 2018-04-20 |  | 5/27/2018 IOS V1.2 (1227) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
28 | General | 2018-01-15 | 2018-05-27 | 95 | Marjon | iOS V1.0(11) | 3 | Talkabout is correct spelling. Not TalkAbout. Please have them correct everywhere (used in notification screen, main app N/Ame on app store, etc. etc.) | [5 empty] | 100% |  |  | 2018-03-23 |  | 5/27/2018 IOS V1.2 (1227) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
29 | Verification Code | 2018-01-18 | 2018-02-14 | 20 | Marjon | iOS V1.0(12) |  | Standardize to 'verification code' in SMS and in APP. On the verification code SMS, please change it from: 'Your authentication code is xxxxxx' to 'Your Talkabout verification code is xxxxxx' On the APP please change to 'Verification code send via phone +*******9181' | [5 empty] | 100% |  |  | 2018-03-23 |  | IOS V1.2 (1237) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | - | [5 empty] | Verify that the problem has been modified | http://compass.mot-solutions.com/doc/538335750/Validation_change_to_Verification.PNG | same in 1236
30 | Myself | 2018-01-22 | 2018-05-15 | 82 | Lee Sun | iOS V1.0(12) | 3 | The circle for image is not a perfect round shape |  |  |  |  | N | 100% | [5 empty] | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | - | [5 empty] | Did not see this problem, please write the reproducing step | LS will review
31 | Myself | 2018-01-22 | 2018-03-15 | 39 | Lee Sun | iOS V1.0(12) | 2 | SN/Ap photo with camera, the photo will flip and angle switched. | [5 empty] | 100% |  | Mirror is normal. This happen on other APP as well. |  |  | 2018-03-15 | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
32 | Myself | 2018-01-22 | 2018-03-15 | 39 | Lee Sun | iOS V1.0(12) | 2 | There is no option to remove photo in profile | [5 empty] | 100% |  | VI does not have remove photo feature. |  |  | 2018-03-15 | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
33 | Add New Member | 2018-01-22 | 2018-05-15 | 82 | Lee Sun | iOS V1.0(12) | 3 | Country code box is not suppose to cover the phone number line. Please shift down. | [5 empty] | 100% |  |  | 2018-03-23 |  | IOS V1.2 (1236) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | - | [5 empty] | Results will be seen in the latest software version | http://compass.mot-solutions.com/doc/539790133/Country_code_box_is_not_suppose_to_cover_the_phone_number_line.PNG
34 | BT Connection | 2018-02-09 | 2018-06-06 | 84 | SK | iOS V1.1(20) | 1 | abnormal connection: 1. Paired to Device, Press "TEST", now can see the icon blinking 2 times. 2. OFF Bluetooth connection in Phone setting. 3. Radio alert disconnected sound. 4. now Phone allow to Press "TEST" 5. But no response in Radio. (Status showing Connected) 6. Then press to "Unpair" - Status "N/A" 7. Go to setting EN/Able the Bluetooth in Phone 8. Now Press "Pair Radio" 9. Pair Status show "Connected", but Battery: N/A 10. Press "Test" on Phone, but still no response in Radio. | [5 empty] | 100% |  |  | 2018-03-23 |  | 6/6/2018 IOS V1.2 (1234) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | - | [5 empty] | It's a radio problem
35 | Chat | 2018-02-09 | 2018-05-28 | 77 | SK | iOS V1.1(20) | 2 | Message Display issue Has a long "SPACE" between message sent until the "time sent". | [5 empty] | 100% |  |  | 2018-03-23 |  | 5/28/2018 IOS V1.2 (1228) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
36 | On Boarding | 2018-02-13 | 2018-07-09 | 105 | FT | Android V1.4(20) | 2 | Why there is pop up message to force user to allow access to photo/media during on boarding steps? | [5 empty] | 100% |  | For issue log purpose. Will not happen in fiN/Al release |  |  | 7/9/2018 Andriod V2.2 | N/A | Closed | Yes |  | Yes | Temporary release in Feb
37 | General | 2018-02-13 | 2018-07-09 | 105 | Tze Lin | Android V1.4(20) | 1 | Talkabout APP will hang, Android version 7.0. | [5 empty] | 80% |  |  | 2018-03-23 |  | 7/9/2018 Andriod V2.2 | N/A | Closed | Yes |  | Yes | Temporary release in Feb
38 | Radio Settings | 2018-02-13 | 2018-07-07 | 104 | Tze Lin | Android V1.4(20) | 2 | Radio and App both showing channel 18, power down radio and app change to channel 17 and close the app. Open app and connect to radio again , now the App shows channel 17 and radio shows channel 18. Radio setting shall always follow RADIO. | [5 empty] | 100% |  |  | 2018-03-23 |  | 7/7/2018 Andriod V2.1 | N/A | Closed | Yes |  | Yes | Temporary release in Feb
39 | On Boarding | 2018-02-13 | 2018-07-09 | 105 | Tze Lin | Android V1.4(20) | 1 | Not able to pair on Android 7.0 | [5 empty] | 100% |  |  | 2018-03-23 |  | 7/9/2018 Andriod V2.2 | N/A | Closed | Yes |  | Yes | Temporary release in Feb
40 | On Boarding | 2018-02-13 | 2018-05-15 | 66 | FT | iOS V1.1(20) | 2 | On Terms and Privacy Policy page, click on DECLINE, this pop up message appear: 'You have to complete the setup to be able to use Talkabout APP...' This is not correct according to wireframes. It should return to branding page. Android version did it correctly. | [5 empty] | 100% |  |  | 2018-03-23 |  | IOS V1.2 (1236) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | - | [5 empty] | This function is now described in the 《TALKABOUT _APP_Wireframes_20180507》document
41 | On Boarding | 2018-02-13 | 2018-05-15 | 66 | FT | iOS V1.1(20) | 3 | After user click YES on pop up message 'You have to complete the setup to be able to use Talkabout APP. Do you want to leave setup and close the app?', the APP shall be close. Now it will only return to Branding screen. | [5 empty] | 100% |  |  | 2018-03-23 |  | IOS V1.2 (1234) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | - | [5 empty] | This problem does not exist in the latest software version
42 | Radio Settings | 2018-02-13 | 2018-07-07 | 104 | LiN/Ar | Android V1.4(20) | 3 | Radio Settingss --> Emergency: Typo on Nmae | [5 empty] | 100% |  |  | 2018-03-23 |  | 7/7/2018 Andriod V2.1 | N/A | Closed | Yes |  | Yes | Temporary release in Feb
43 | On Boarding | 2018-02-20 | 2018-06-01 | 74 | FT | iOS V1.1(20) | 2 | On Terms and Privacy Policy Page, user has to click on the 'I agree to both the terms and privacy policy' in order to click on the AGREE ALL button. This is wrong. Android version did it correctly. | [5 empty] | 100% |  |  | 2018-03-23 |  | 6/1/2018 IOS V1.2 (1231) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
44 | On Boarding | 2018-02-20 | 2018-05-28 | 70 | FT | iOS V1.1(20) | 1 | When pairing successful, radio channel and code will automatically change to 0. This does not happen on Android APP. | [5 empty] | 50% |  |  | 2018-03-23 |  | 5/28/2018 IOS V1.2 (1228) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
45 | On Boarding | 2018-02-20 | 2018-05-28 | 70 | FT | iOS V1.1(20) | 1 | I put my phone to flight mode. At CREATE ACCOUNT page, after I click LOGIN, there is a pop up message show OK. This is same when I turn off WIFI and MOBILE DATA on my phone. If wifi/network is needed when user choose to create account, need to remind user. Then I kill the APP, and launch again. At this time the Bluetooth on my phone is eN/Able, but APP still pop up message ask me to turn on Bluetooth. I need to Bluetooth turn off and on again. After I turn on the WIFI on my phone and click LOGIN, APP goes to TIPS. There is no verification code being sent and APP does not ask to insert verification code. | [5 empty] | 100% |  |  | 2018-03-23 |  | 5/28/2018 IOS V1.2 (1228) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
46 | On Boarding | 2018-02-20 | 2018-05-28 | 70 | FT | iOS V1.1(20) | 2 | During onboarding APP does not show pop up message to ask me turn ON location service. | [5 empty] | 100% |  |  | 2018-03-23 |  | 5/28/2018 IOS V1.2 (1228) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
47 | On Boarding | 2018-02-20 | 2018-05-28 | 70 | FT | iOS V1.1(20) | 1 | When I reach TIPS screen, I kill the APP then launch again, APP back to branding screen. Then I have to click NEXT all the way to reach PAIRING screen. Shouldn't the APP show TIPS screen directly? At this time the radio Bluetooth icon is still showing connected. In Pairing page APP is searching for radio. The Bluetooth connection status on radio is not real. I repeated a few times. When I reach TIPS screen, I kill the APP then launch again. Sometimes the radio Bluetooth will disconnected. When APP is killed, Bluetooth connection between radio and APP shall be kill so radio shall show Bluetooth disconnected. | [5 empty] | 50% |  | After create account/login is completed and user kill the app, re-launch app shall always back to last seen screen. | 2018-03-23 |  | 5/28/2018 IOS V1.2 (1228) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
48 | On Boarding | 2018-02-20 | 2018-05-28 | 70 | FT | iOS V1.1(20) | 2 | The pairing page RETRY button doesn't seem to do anything. The pairing searching time does not time out after 30s. Android version did it correctly, please follow Android. | [5 empty] | 100% |  |  | 2018-03-23 |  | 5/28/2018 IOS V1.2 (1228) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
49 | On Boarding | 2018-02-20 | 2018-05-28 | 70 | FT | iOS V1.1(20) | 1 | Sometimes after PAIRING SUCESSFUL, press on the TEST button, radio screen does not show anything. The TEST button does not work, or the Bluetooth connection is fake? | [5 empty] | 50% |  |  | 2018-03-23 |  | 5/28/2018 IOS V1.2 (1228) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
50 | On Boarding | 2018-02-20 | 2018-05-30 | 72 | FT | iOS V1.1(20), Android V1.4(20) | 3 | Once user reach the last page of TIPS, the START button appear. If user swipe back to previous TIPS, the START button shall stay there as well. START button should always there once user reach the last page of TIPS. | [5 empty] | 100% |  |  | 2018-03-23 |  | 5/30/2018 IOS V1.2 (1228) 7/7/2018 Andriod V2.1 | Closed | Closed | Yes |  | Yes | Temporary release in Feb
51 | Hamburger Menu | 2018-02-20 | 2018-05-31 | 73 | FT | iOS V1.1(20) | 1 | Radio side is showing Bluetooth connected to APP but inside APP the status is showing Connecting. I suspect the Bluetooth connection is not there. | [5 empty] | 50% |  |  | 2018-03-23 |  | 5/31/2018 IOS V1.2 (1231) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
52 | Hamburger Menu | 2018-02-20 | 2018-05-28 | 70 | FT | iOS V1.1(20), Android V1.4(20) | 2 | Radio battery level is not shown in APP. The radio battery icon will need to be updated by Right Click Studio. The icon now looks like sigN/Al strength. | [5 empty] | 100% |  |  | 2018-03-23 |  | 5/28/2018 IOS V1.2 (1228) 7/7/2018 Andriod V2.1 | Closed | Closed | Yes |  | Yes | Temporary release in Feb
53 | Myself | 2018-02-20 | 2018-05-15 | 61 | FT | iOS V1.1(20) | 2 | Myself--> click on the circle --> Take Picture --> Pop up message ask user to go to settings to eN/Able camera permission. I go to setting, but do not know how to eN/Able camera permission. Can you simplify the flow? | [5 empty] | 100% |  |  | 2018-03-23 |  | IOS V1.2 (1238) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | - | [7 empty] | Still same in 1236 | Still same in 1236
54 | Hamburger Menu | 2018-02-20 | 2018-05-30 | 72 | FT | iOS V1.1(20) | 1 | I was testing APP with phon in flight mode. I switch APP to background, then phone disable flight mode. I turn on flight mode again then launch APP. Radio side is showing Bluetooth connected but APP side status is Disconnected. I go to Bluetooth Connection and click on TEST, radio does not have any response. I click on UNPAIR Radio, a pop up message will ask if I wanted to unpair radio. I click YES, radio side is still showing bluetooth connected. I power off and on again on radio. After 1-2 seconds radio side show connected again but APP still showing searching for radio. I power off and on again on radio, this time APP showing searching for radio and radio side is showing waiting to be paired and then timed out. The Bluetooth connection is not successful. I turn off and on again phone Bluetooth setting, then back to APP. Now the APP is hang (stops at the PAIRING screen) but the radio side Bluetooth connection become successful. I kill the APP then launch APP and try to connect again, Bluetooth connection not successful. I reset radio, reset phone Bluetooth setting and kill the APP then launch again, Bluetooth connection still not succcessful. I tried a few times. I need to leave setup, then start all over again from branding to create new account in order to have Bluetooth connection. | [5 empty] | 100% |  |  | 2018-03-23 |  | 5/30/2018 IOS V1.2 (1228) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
55 | My Member | 2018-02-20 | 2018-05-30 | 72 | FT | iOS V1.1(20) | 2 | My members --> Add members --> SEARCH PHONE CONTACTS --> Permissions GO TO SETTINGS. After go to setting I do not know where to eN/Able the access to contact list. Can you simplify this? | [5 empty] | 100% |  |  | 2018-03-23 |  | 5/30/2018 IOS V1.2 (1228) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
56 | My members | 2018-02-20 | 2018-05-15 | 61 | FT | iOS V1.1(20) | 2 | My members --> Add members --> SEARCH PHONE CONTACTS --> Search column is missing. Please follow VI Design. | [5 empty] | 100% |  |  | 2018-03-23 |  | IOS V1.2 (1236) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | - | [5 empty] | This feature has not been added yet
57 | My members | 2018-02-20 | 2018-06-25 | 90 | FT | iOS V1.1(20) | 2 | My members --> Add members --> SEARCH PHONE CONTACTS --> Select a contact number with country code available. The Country code shall be automatically replaced, but in APP it is showing +65 +60125048849. The +65 shall be auto replace by +60. |  |  |  |  | N | 100% |  |  | 2018-03-23 |  | 6/25/2018 IOS V1.2 (1240) | Closed | Closed | Yes |  | Yes | Temporary release in Feb
58 | Bluetooth Connection | 2018-02-20 | 2018-05-30 | 72 | FT | iOS V1.1(20) | 1 | Sometimes radio will automatically power off (I am using alkaline battery) or Bluetooth auto disconnected. I reset radio again, APP is not able to auto connect with radio. I need to go Bluetooth Connection tab --> unpair in order to pair radio again. | [5 empty] | 50% |  |  | 2018-03-23 |  | 5/30/2018 IOS V1.2 (1230) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
59 | Bluetooth Connection | 2018-02-20 | 2018-05-30 | 72 | FT | iOS V1.1(20), Android V1.4(20) | 2 | Hamburger menu --> Bluetooth Connetion --> Click on Test button --> The Bluetooth icon on the radio will blink twice, not turn solid for 2 seconds. Please change the wording. Wireframes will be updated. | [5 empty] | 100% |  |  | 2018-03-23 |  | 5/30/2018 IOS V1.2 (1230) 7/7/2018 Andriod V2.1 | Closed | Closed | Yes |  | Yes | Temporary release in Feb |  | Closed SRS-R2.0-20180512 changed at (OnBorading-3-1-15)
60 | Bluetooth Connection | 2018-02-20 | 2018-05-15 | 61 | FT | iOS V1.1(20) | 2 | I suspect battery level showing 100% in Bluetooth Connection Page is not accurate. Model and Version is not working. | [5 empty] | 100% |  |  | 2018-03-23 |  | IOS V1.2 (1236) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | - | [5 empty] | This capability has been implemented in the latest software version, and you can see the specific battery and version information in BLUETOOTH CONNECTION
61 | Bluetooth Connection | 2018-02-20 | 2018-05-30 | 72 | FT | iOS V1.1(20) | 2 | Sometimes the battery level is not shown in BLUETOOTH SETTINGS. It shows N/A. | [5 empty] | 50% |  |  | 2018-03-23 |  | 5/30/2018 IOS V1.2 (1230) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
62 | Bluetooth Connection | 2018-02-20 | 2018-05-30 | 72 | FT | iOS V1.1(20) | 2 | Power off radio, the status in BLUETOOTH SETTINGS change from Connected to Connecting and stays in Connecting for quite long. How long will it change to Disconected? Or it will never change to Disconnected? When it shows Connecting it should means the APP is searching for radio, is that the case? | [5 empty] | 100% |  | Connecting means APP is searching for radio. It will keep on searching |  |  | 5/30/2018 IOS V1.2 (1230) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
63 | General | 2018-02-20 | 2018-05-30 | 72 | FT | iOS V1.1(20) | 1 | APP goes to background then come to foreground again, sometimes radio side will have a beep sound and display will light on. And one of the time, radio display gone abnormal. Need to reset radio in order to back to normal. Refer video and photo here: http://compass.mot-solutions.com/cgi/go/535946739 | [5 empty] | 20% |  |  | 2018-03-23 |  | 5/30/2018 IOS V1.2 (1230) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
64 | Radio Settings | 2018-02-20 | 2018-05-27 | 69 | FT | iOS V1.1(20) | 1 | In APP it is showing CONNECTED, and radio side also showing CONNECTED but changing Radio Settings at APP side does not reflect in radio. Go to BLUETOOTH SETTINGS press on TEST, radio side has no response too. The Bluetooth connection is there but doesn't seem work in real. Turn off radio then turn on again, the Bluetooth connection is success but changing Radio Settingss on APP still makes no effect on radio. Unpair radio then pair again, same thing. Need to kill the APP in order to make the Bluetooth connection works real. I notice this can be duplicate by press PTT on radio after Bluetooth connection success. | [5 empty] | 50% |  | Radio issue |  |  | 5/27/2018 IOS V1.2 (1227) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
65 | Radio Settings | 2018-02-20 | 2018-05-27 | 69 | FT | iOS V1.1(20), Android V1.4(20) | 2 | Try to change the call tone fast in APP (before the call tone finish played, change again). The tone play on radio side does not reflect the correct tone. The switch shall be fast enough like the vibration feature. The call tone icon on radio display sometimes will disappear too. | [5 empty] | 100% |  | Radio issue |  |  | 5/27/2018 IOS V1.2 (1227) 7/7/2018 Andriod V2.1 | Closed | Closed | Yes |  | Yes | Temporary release in Feb
66 | Radio Settings | 2018-02-20 | 2018-05-30 | 72 | FT | iOS V1.1(20), Android V1.4(20) | 2 | VOX and iVOX shall be combine as 1 feature. Please refer to Wireframes. | [5 empty] | 100% |  | Radio issue | 2018-03-23 |  | 5/30/2018 IOS V1.2 (1230) 7/7/2018 Andriod V2.1 | Closed | Closed | Yes |  | Yes | Temporary release in Feb
67 | Bluetooth Connection | 2018-02-20 | 2018-05-30 | 72 | FT | iOS V1.1(20) | 1 | Sometimes changing Radio Settings in APP does not take effect at radio. I suspect the Bluetooth connection is lost on its own. Then I killed the APP but radio side still showing connected. | [5 empty] | 50% |  |  | 2018-03-23 |  | 5/30/2018 IOS V1.2 (1230) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
68 | Radio Settings | 2018-02-20 | 2018-05-30 | 72 | FT | iOS V1.1(20) | 3 | Sometimes when setting call tone from APP, on radio display the call tone icon is not shown, only show the call tone number. | [5 empty] | 20% |  | Radio issue |  |  | 5/30/2018 IOS V1.2 (1230) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
69 | Radio Settings | 2018-02-20 | 2018-06-06 | 77 | FT | iOS V1.1(20), Android V1.4(20) | 1 | Switching from two-way mode to weather mode is not working. Changing setting for weather mode is not working. | [5 empty] | 100% |  |  | 2018-03-23 |  | 6/6/2018 IOS V1.2 (1234) 7/9/2018 Andriod V2.2 | Closed | Closed | Yes |  | Yes | Temporary release in Feb | [7 empty] | You can successfully switch from two-way mode to WEATHER mode, after which the word for WEATHER is displayed on the radio screen, and the sound on the radio will change
70 | Radio Settings | 2018-02-20 | 2018-05-30 | 72 | FT | iOS V1.1(20) | 2 | Radio Settings --> Emergency: Something missing in the wordings, not following the Wireframes. This is missing: 2. Select the emergency S.O.S message from the predefined chat options. I am using iphone 5s. | [5 empty] | 100% |  |  | 2018-03-23 |  | 5/30/2018 IOS V1.2 (1230) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
71 | Radio Settings | 2018-02-20 | 2018-05-30 | 72 | FT | iOS V1.1(20), Android V1.4(20) | 2 | For Emergency message is there any character limit? I can keep typing. | [5 empty] | 100% |  |  | 2018-03-23 |  | 5/30/2018 IOS V1.2 (1230) 7/7/2018 Andriod V2.1 | Closed | Closed | Yes |  | Yes | Temporary release in Feb
72 | Radio Settings | 2018-02-20 | 2018-05-30 | 72 | FT | iOS V1.1(20) | 3 | Let say I have key in 5 lines in emergency message and I wanted to modify something in line 2 and 3. On iphone 5s(small screen) it is very difficult to select specific line. | [5 empty] | 100% |  |  | 2018-03-23 |  | 5/30/2018 IOS V1.2 (1231) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
73 | Radio Settings | 2018-02-20 | 2018-05-30 | 72 | FT | iOS V1.1(20) | 2 | On iphone 5S after key in the emergency message user has to swipe down in order to see the CLEAR/SAVE button. This might be unclear to user. Can we improve this? | [5 empty] | 100% |  |  | 2018-03-23 |  | 5/30/2018 IOS V1.2 (1231) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
74 | Radio Settings | 2018-02-20 | 2018-05-30 | 72 | FT | iOS V1.1(20), Android V1.4(20) | 2 | Emergency message after user click on SAVE, there is nothing to show user that this has been successfully saved. Need some action. | [5 empty] | 100% |  |  | 2018-03-23 |  | 5/30/2018 IOS V1.2 (1230) 7/7/2018 Andriod V2.1 | Closed | Closed | Yes |  | Yes | Temporary release in Feb
75 | APP Setting | 2018-02-20 | 2018-05-30 | 72 | FT | iOS V1.1(20) | 1 | APP setting --> Delete Account --> able to key in message to the screen after that APP will hang. Have to kill the APP. | [5 empty] | 100% |  |  | 2018-03-23 |  | 5/30/2018 IOS V1.2 (1231) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
76 | Bluetooth Connection | 2018-02-20 | 2018-05-30 | 72 | FT | iOS V1.1(20) | 1 | After kill APP, the bluetooth connection will not auto connect back. Have to unpair radio then pair again. | [5 empty] | 100% |  |  | 2018-03-23 |  | 5/30/2018 IOS V1.2 (1231) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
77 | My Maps | 2018-02-20 | 2018-05-30 | 72 | FT | iOS V1.1(20) | 2 | My Maps --> Offline Maps --> Search Maps --> key in place N/Ame to search column but nothing happen (note: I do not turn on location service and there is no pop up to ask me turn on location service). On Android after key in place N/Ame the APP will list out few suggestions. | [5 empty] | 100% |  |  | 2018-03-23 |  | 5/30/2018 IOS V1.2 (1231) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
78 | My Maps | 2018-02-20 | 2018-05-15 | 61 | FT | iOS V1.1(20) | 3 | My Maps --> Offline Maps --> click on Bin icon at top right corner, user might not know that need to select the Bin on the right of map in order to delete it. | [5 empty] | 100% |  | No changes for now unless there is further customer feedback |  |  |  | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
79 | My Maps | 2018-02-20 | 2018-05-15 | 61 | FT | iOS V1.1(20) | 3 | My Maps --> Offline Maps --> click on Bin icon at top right corner, user might not know how to cancel it. In this version use need to click on the < at top left corner. | [5 empty] | 100% |  | No changes for now unless there is further customer feedback |  |  |  | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
80 | My Maps | 2018-02-20 | 2018-05-30 | 72 | FT | iOS V1.1(20) | 3 | My Maps --> My Tracks --> when the list is empty, the SHOW ON MAP is there. I think this should be grey out until you have tracks saved. | [5 empty] | 100% |  |  | 2018-03-23 |  | 5/30/2018 IOS V1.2 (1231) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
81 | My Maps | 2018-02-20 | 2018-05-30 | 72 | FT | iOS V1.1(20) | 2 | My Maps --> Geofence is not working | [5 empty] | 100% |  |  | 2018-03-23 |  | 5/30/2018 IOS V1.2 (1231) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
82 | My members | 2018-02-20 | 2018-06-06 | 77 | FT | iOS V1.1(20) | 3 | Iphone 5S. My Members --> Add Member --> Search Phone Contacts --> the < and Search is overlap. | [5 empty] | 100% |  |  | 2018-03-23 |  | 6/6/2018 IOS V1.2 (1236) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | - | [5 empty] | The main problem is the need to add new search capabilities, which will be resolved when added
83 | Shout | 2018-02-20 | 2018-05-30 | 72 | FT | iOS V1.1(20) | 3 | When Shout is empty, click on Delete Chat History there is pop up message to ask if want to delete shout history. But there is nothing to delete. | [5 empty] | 100% |  |  | 2018-03-23 |  | 5/30/2018 IOS V1.2 (1231) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
84 | Shout | 2018-02-20 | 2018-05-30 | 72 | FT | iOS V1.1(20) | 2 | In Maroon Bells URD section 5.2.5 it says if the text message send is not success, radio will feedback to APP. Where is this in APP? | [5 empty] | 100% |  | Follow latest VI and style guide |  |  | 5/30/2018 IOS V1.2 (1231) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
85 | On Boarding | 2018-02-20 | 2018-07-23 | 110 | LS | iOS V1.1(20) | 3 | On Terms and Privacy Policy Page, the background color is wrong and font type is wrong. Please use Arial - same as the rest of Apps. |  |  |  |  | N | 100% |  |  | 2018-03-23 |  | 23 July 2018 IOS V1.2 (1248) | CLosed | N/A | Yes |  | Yes | Temporary release in Feb |  | Still not correct 6/29 4 Jul, CS: all use Arial? if using this font , then need to provide the font doc. Color need to be double confirmed if it is real issue. FT phone is able to reflect correct color. 18 jul, XY: fixed 1.2 47 | [5 empty] | It will be modified further | LS will review
86 | On Boarding | 2018-02-20 | 2018-05-15 | 61 | LS | iOS V1.1(20) | 3 | On Terms and Privacy Policy Page, the button style is wrong. Follow the Setup button style. |  |  |  |  | N | 100% |  |  | 2018-03-23 |  |  | Closed | Closed | Yes |  | Yes | Temporary release in Feb | [7 empty] | It's already a uniform button state | LS will review
87 | On Boarding | 2018-02-20 | 2018-05-27 | 69 | LS | iOS V1.1(20) | 1 | While pairing, suddenly the radio just vibrate and off. | [5 empty] | 10% |  | Radio issue |  |  | 5/27/2018 IOS V1.2 (1227) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
88 | On Boarding | 2018-02-20 | 2018-03-15 | 18 | LS | iOS V1.1(20) | 3 | On pairing page, the "Skip Pairing" button should be same style as the "Test". Follow the Android version | [5 empty] | 100% |  | Skip Pairing' button will be removed so this is not an issue anymore. |  |  | 2018-03-15 | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
89 | On Boarding | 2018-02-20 | 2018-03-15 | 18 | LS | iOS V1.1(20) | 3 | After "Skip Pairing" - it is weird to go to "Pairing Successful" page. Note: MSI is still yet to decide whether to keep the skip pairing feature. | [5 empty] | 100% |  | Skip Pairing' button will be removed so this is not an issue anymore. |  |  | 2018-03-15 | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
90 | On Boarding | 2018-02-20 | 2018-06-06 | 77 | LS | iOS V1.1(20) | 3 | After paired, touch "TEST", the radio LED glow is wrong. It should blink twice very bright like the mock up. | [5 empty] | 30% |  | Radio issue |  |  | 6-Jun-18 IOS V1.2 (1234) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | - | [5 empty] | The APP has implemented this function, and the rest is the display problem of radio
91 | On Boarding | 2018-02-20 | 2018-05-27 | 69 | LS | iOS V1.1(20) | 2 | TIPS: On second page onward, pressing the left arrow it does not work, but it can be swiped. Please allow the left button to work. | [5 empty] | 100% |  |  | 2018-03-23 |  | 5/27/2018 IOS V1.2 (1227) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
92 | Hamburger Menu | 2018-02-20 | 2018-05-30 | 72 | LS | iOS V1.1(20), Android V1.4(20) | 2 | The Radio with the stair bar should be removed. Please follow latest wireframes/VI. It should Radio battery level. | [5 empty] | 100% |  |  | 2018-03-23 |  | 5/30/2018 IOS V1.2 (1230) 7/7/2018 Andriod V2.1 | Closed | Closed | Yes |  | Yes | Temporary release in Feb
93 | Myself | 2018-02-20 | 2018-05-15 | 61 | LS | iOS V1.1(20) | 2 | The color bubble is still not align on both left and right edge |  |  |  |  | N | 100% |  |  | 2018-03-23 |  |  | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | - | [6 empty] | LS will review
94 | Myself | 2018-02-20 | 2018-03-15 | 18 | LS | iOS V1.1(20) | 2 | When taking the selfie photo, the picture is still mirror. MUST fix. | [5 empty] | 100% |  | Mirror is normal. Same happen on other APP. |  |  | 2018-03-15 | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
95 | Create Group | 2018-02-20 | 2018-05-27 | 69 | LS | iOS V1.1(20) | 2 | After N/Ame and selecting members, I click the Done button on keyboard many time no response. I try to swipe the keyboard down not working. then by accident, double tap on screen, it close the keyboard. | [5 empty] | 100% |  |  | 2018-03-23 |  | 5/27/2018 IOS V1.2 (1227) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
96 | My Maps | 2018-02-20 | 2018-05-27 | 69 | LS | iOS V1.1(20) | 3 | Inside Offline Maps, when there is no offline maps, the dustbin icon should not appear. | [5 empty] | 100% |  |  | 2018-03-23 |  | 5/27/2018 IOS V1.2 (1227) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
97 | My Maps | 2018-02-20 | 2018-05-27 | 69 | LS | iOS V1.1(20) | 2 | My Maps - Offline Maps - Search Maps - when I key in search - Bayan Baru, it is not working. | [5 empty] | 100% |  |  | 2018-03-23 |  | 5/27/2018 IOS V1.2 (1227) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
98 | My Maps | 2018-02-20 | 2018-05-27 | 69 | LS | iOS V1.1(20) | 3 | When create 1 offline maps - the list menu should not show the line below | [5 empty] | 100% |  |  | 2018-03-23 |  | 5/27/2018 IOS V1.2 (1227) | Closed | Closed | Yes |  | Yes | Temporary release in Feb
99 | My Maps | 2018-02-20 | 2018-05-27 | 69 | LS | iOS V1.1(20) | 2 | On the right side of the offline maps save - tap the icon, it does not work. Then I try to create new offline maps, once tap download, the whole apps shut down. | [5 empty] | 100% |  |  | 2018-03-23 |  | 5/27/2018 IOS V1.2 (1227) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
100 | My Tracks | 2018-02-20 | 2018-05-27 | 69 | LS | iOS V1.1(20) | 3 | When there is no track, the dustbin icon should not appear. | [5 empty] | 100% |  |  | 2018-03-23 |  | 5/27/2018 IOS V1.2 (1227) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
101 | My Location Pin | 2018-02-20 | 2018-05-27 | 69 | LS | iOS V1.1(20) | 2 | When there is so many location within a day, it is hard to tell which is which. Please implement default file N/Ame as: Location Pin YYYYMMDD_HH:MM:SS | [5 empty] | 100% |  |  | 2018-03-23 |  | 5/27/2018 IOS V1.2 (1227) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
102 | Geofence | 2018-02-20 | 2018-05-15 | 61 | LS | iOS V1.1(20) | 2 | When happen I brought my phone out further than the Geofence area, and my radios stay at home. Message appears saying 'GPS sigN/Al low...' and I turn it off. Not sure what happen. Now, my offline maps not working. | [5 empty] | 100% |  | Geofence feature is not ready in P1A. To retest when Geofence feature is ready. |  |  | IOS V1.2 (1236) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | - | [6 empty] | not duplicate in IOS V1.2 (1236)
103 | Purchase Map Types | 2018-02-20 | 2018-05-15 | 61 | LS | iOS V1.1(20), Android V1.4(20) | 3 | This feature not working | [5 empty] | 100% |  |  | 2018-04-20 |  |  | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | Purchase map is not required in phase 1 release. | [6 empty] | IOS V1.2 (1236) Engineering version
104 | Apps Settings | 2018-02-20 | 2018-05-27 | 69 | LS | iOS V1.1(20) | 3 | Auto Update Location - When I pull the dot to OFF, when I try to drag it from OFF to the number, I tends to drag the whole APPS SETTING page to Hamburger Menu rather than dragging the dot. Unless I drag it very carefully on the right side of the dot. It causes frustration. | [5 empty] | 100% |  |  | 2018-03-30 |  | 5/27/2018 IOS V1.2 (1227) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
105 | Apps Settings | 2018-02-20 | 2018-05-27 | 69 | LS | iOS V1.1(20) | 2 | Access Permissions - When I click in, the SETTINGS page appears. When I click the top back arrow, it should bring me back to the Talkabout Apps. | [5 empty] | 100% |  |  | 2018-03-23 |  | 5/27/2018 IOS V1.2 (1227) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
106 | Apps Settings | 2018-02-20 | 2018-05-27 | 69 | LS | iOS V1.1(20) | 3 | Languages - Below the last list menu, the line should not appears (the line below French should not be there). | [5 empty] | 100% |  |  | 2018-03-30 |  | 5/27/2018 IOS V1.2 (1227) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
107 | Apps Settings | 2018-02-20 | 2018-05-27 | 69 | LS | iOS V1.1(20) | 3 | Metric - Below is the last list menu, the line should not appears (the line below Imperial should not appears). | [5 empty] | 100% |  |  | 2018-03-23 |  | 5/27/2018 IOS V1.2 (1227) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
108 | Apps Settings | 2018-02-20 | 2018-05-27 | 69 | LS | iOS V1.1(20) | 2 | Account - Delete Account - Warning Message. When I click LOG OUT - keyboard appears and when I type, it added text to the Warning message and the whole apps hang. | [5 empty] | 100% |  |  | 2018-03-23 |  | 5/27/2018 IOS V1.2 (1227) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
109 | Verification Code | 2018-02-20 | 2018-05-27 | 69 | LS | iOS V1.1(20) | 2 | When I tap on CODE, the numeric keyboard should appear rather than the alphabet keyboard. Follow Android style. | [5 empty] | 100% |  |  | 2018-03-23 |  | 5/27/2018 IOS V1.2 (1227) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
110 | Chat | 2018-02-20 | 2018-05-27 | 69 | LS | iOS V1.1(20) | 3 | The typing window should be rounded front and back. Now it is square with small corner. | [5 empty] | 100% |  |  | 2018-03-23 |  | 5/27/2018 IOS V1.2 (1227) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
111 | Chat | 2018-02-20 | 2018-05-27 | 69 | LS | iOS V1.1(20) | 3 | Chat bubble shape is still not perfect round. It is squashed. | [5 empty] | 100% |  |  | 2018-03-23 |  | 5/27/2018 IOS V1.2 (1227) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
112 | Chat | 2018-02-20 | 2018-05-15 | 61 | LS | iOS V1.1(20) | 3 | Chat bubble time stamp font color should be grey #A8AAAD. Please refer guideline. |  |  |  |  | N | 100% |  |  | 2018-03-23 |  |  | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | - | [5 empty] | The problem is under check | LS will review
113 | Chat | 2018-02-20 | 2018-05-27 | 69 | LS | iOS V1.1(20) | 2 | Predefined Message - SOS - After I type message, I use double tap to close the keyboard it does not work. Please keep consistent behavior through out the apps to close the keyboard - 1. double tap on window, (2) swipe down the keyboard. | [5 empty] | 100% |  |  | 2018-03-23 |  | 5/27/2018 IOS V1.2 (1227) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
114 | Chat | 2018-02-20 | 2018-05-27 | 69 | LS | iOS V1.1(20) | 2 | Predefined Message - SOS - Emergency. After I type the message, tap SAVE, no indication or response. After pressing the SAVE, it should return to the main Chat Window | [5 empty] | 100% |  | Follow new wireframes. | 2018-03-23 |  | 5/27/2018 IOS V1.2 (1227) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
115 | Maps | 2018-02-20 | 2018-05-27 | 69 | LS | iOS V1.1(20) | 2 | Pop up window on side (Map styles...) the window should not block the icons. | [5 empty] | 100% |  |  | 2018-03-23 |  | 5/27/2018 IOS V1.2 (1227) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
116 | Maps | 2018-02-20 | 2018-05-27 | 69 | LS | iOS V1.1(20) | 2 | View Members - when I select Show - select member. The member does not appear yet does not prompt message. | [5 empty] | 100% |  |  | 2018-03-23 |  | 5/27/2018 IOS V1.2 (1227) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
117 | Maps | 2018-02-20 | 2018-05-27 | 69 | LS | iOS V1.1(20) | 2 | My Tracks - Is it possible to add a time to each track? Please use this default file N/Ame: My Track YYYYMMDD_HH:MM:SS | [5 empty] | 100% |  |  | 2018-03-23 |  | 5/27/2018 IOS V1.2 (1227) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
118 | Maps | 2018-02-20 | 2018-05-15 | 61 | LS | iOS V1.1(20) | 2 | Geofence - After I click SHARE, there is no confirmation. Not sure I maN/Age to share. | [5 empty] | 100% |  |  | 2018-03-23 |  | IOS V1.2 (1226) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | - | [5 empty] | The success of sharing can be viewed in the Chat box | Yes, but after checked in Chat Box, it will showed to Retry every time i sent. actually the recever already received. Video
119 | Maps | 2018-02-20 | 2018-05-27 | 69 | LS | iOS V1.1(20) | 2 | When Geofence is active, I click the Map styles, I can not close the pop up. | [5 empty] | 100% |  |  | 2018-03-23 |  | 5/27/2018 IOS V1.2 (1227) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
120 | Radio Settings | 2018-02-20 |  | -30822 | LS | iOS V1.1(20), Android V2.3 | 3 | The Channel, Sub Code & Call Tone scroll bar is hard to know what is the upper and lower limit. May need N/A to suggest | N | Enh_D1 | N | P | N | 100% |  |  | 2018-03-23 |  |  | Closed | Closed | Yes |  |  |  |  | Still not correct 6/29 4 Jul, XY: XY: already followed the latest UI doc, LS pls confirm 18 jul, XY: new feature , will not support 24 Jul, FT: we have feedback this on 20-Feb-18 together with ID feedback file (see attached slide#18). You should not come back now saying you will not fix it. 26 Jul, XY: Denied and come back that this is Enh 31 Jul, XY: APP independent, not related to radio SW. 1 Aug CS: This should not considered as Enhget email from LeeSun on the evidence. Please refer to links for email evidences. | needs 2 weeks after cost is locked down | https://drive.google.com/open?id=1MlZzceu4eNHeSXCuLgQlgm_RB7sBmjJk | SiauFong please mention | 这一项，之前已经反复跟设计公司的反复确认过，设计公司也确认就是这样做。邮件为证。 后续这个部分设计公司并没有更新文档。遇到冲突，我们只能以 TALKABOUT_APP_VI_Design TALKABOUT_APP_Wireframes 为准。 comment 提到的文档UI APPS Feedback IOS V1.1 (20) 20180220.pptx 这个文档只能作为moto跟设计公司讨论的初稿，并不能作为我们开发的依据，因为这个文档跟最终设计本来就很多不一样。如第8页 slider bar。 | android 1 week , iOS 1 week, test 0.5week, document 0.2week | This situation is defined in the radio document | LS will review
121 | Radio Settings | 2018-02-20 | 2018-05-27 | 69 | LS | iOS V1.1(20) | 2 | VOX and iVOX shall be combine as 1 feature. Since the options is limited, Can we do different from Scroll bar? | [5 empty] | 100% |  |  | 2018-03-23 |  | 5/27/2018 IOS V1.2 (1227) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
122 | Radio Settings | 2018-02-20 | 2018-05-27 | 69 | LS | iOS V1.1(20) | 2 | Easy Pairing - Set as Leader vs Set as Member. The UI will be updated. Please refer to latest wireframes/VI. | [5 empty] | 100% |  |  | 2018-03-30 |  | 5/27/2018 IOS V1.2 (1227) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
123 | Button | 2018-02-20 | 2018-07-23 | 110 | LS | iOS V1.1(20) | 3 | Whenever there is single button at bottom of screen, it should appears long like Android version. |  |  |  |  | N | 100% |  |  | 2018-03-30 |  | 23 July 2018 IOS V1.2 (1248) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | - | [5 empty] | Results will be seen in the latest software version | LS will review
124 | On Boarding | 2018-02-21 | 2018-05-15 | 60 | LS | Android V1.4(20) | 3 | Term and Conditions - the background color is wrong. The last sentence will blink when I tap. It should not be. If we just want the user to tap AGREE button. | Y |  | N | Y |  | N/A | Open |  | 2018-03-23 |  |  | N/A | Closed | Yes |  | Yes | Temporary release in Feb |  | LS to review 26 Jul, CS: Android still showing greyish, requested Auctus to change color. Please change the DECLINE button background color to be same as Terms and condition background color. 26 Jul, CS: was not fixed yet. Please change "DECLINE" button background color to be same as Terms and Conditions background color.​ 31 Jul, XY: APP independent, not related to radio SW. | 2018-08-10
125 | On Boarding | 2018-02-21 | 2018-05-15 | 60 | LS | Android V1.4(20) | 2 | Create Account: Why Country Code for Android is set as US +1. And the options is limited. It is different from IOS. | [5 empty] | 100% | [5 empty] | N/A | Closed | Yes |  | Yes | Temporary release in Feb
126 | On Boarding | 2018-02-21 | 2018-03-15 | 17 | LS | Android V1.4(20) | 2 | Create Account: The pop up window after LOGIN, the style of window can be defined? Or follow phone Android? | [5 empty] | 100% |  | Android default |  |  | 2018-03-15 | N/A | Closed | Yes |  | Yes | Temporary release in Feb
127 | On Boarding | 2018-02-21 | 2018-07-07 | 98 | LS | Android V1.4(20) | 2 | TIPS: The first page of TIPS should not have left arrow. Tapping the arrow is not working. | [5 empty] | 100% |  |  | 2018-03-23 |  | 7/7/2018 Andriod V2.1 | N/A | Closed | Yes |  | Yes | Temporary release in Feb
128 | Hamburger Menu | 2018-02-21 | 2018-07-07 | 98 | LS | Android V1.4(20) | 3 | The Radio Settings icon is wrong. | [5 empty] | 100% |  |  | 2018-03-23 |  | 7/7/2018 Andriod V2.1 | N/A | Closed | Yes |  | Yes | Temporary release in Feb
129 | Myself | 2018-02-21 | 2018-07-07 | 98 | LS | Android V1.4(20) | 2 | Myself - I have never set any picture. How come there is a picture inside my profile? | [5 empty] | 100% |  |  | 2018-03-23 |  | 7/7/2018 Andriod V2.1 | N/A | Closed | Yes |  | Yes | Temporary release in Feb
130 | Myself | 2018-02-21 | 2018-07-09 | 99 | LS | Android V1.4(20) | 1 | After taking picture and SAVE, the whole apps shut down, setting all deleted and going back to Welcome Screen | [5 empty] | 100% |  |  | 2018-03-23 |  | 7/9/2018 Andriod V2.2 | N/A | Closed | Yes |  | Yes | Temporary release in Feb
131 | Myself | 2018-02-21 | 2018-07-07 | 98 | LS | Android V1.4(20) | 2 | The default user color should be the first bubble. The tick should be shown. | [5 empty] | 100% |  |  | 2018-03-23 |  | 7/7/2018 Andriod V2.1 | N/A | Closed | Yes |  | Yes | Temporary release in Feb
132 | Myself | 2018-02-21 | 2018-03-15 | 17 | LS | Android V1.4(20) | 2 | Profile photo from album - now the picture can be zoom and pan, yet the crop window can move around. Very annoying. Please choose either fix the picture and move the crop box or fix the crop box and move and zoom the photo. Why IOS does not have this option? | [5 empty] | 100% |  | Android default |  |  | 2018-03-15 | N/A | Closed | Yes |  | Yes | Temporary release in Feb
133 | Myself | 2018-02-21 | 2018-07-07 | 98 | LS | Android V1.4(20) | 2 | After setting MYSELF profile, tapping back, it should return to the Hamburger Menu. | [5 empty] | 100% |  |  | 2018-03-23 |  | 7/7/2018 Andriod V2.1 | N/A | Closed | Yes |  | Yes | Temporary release in Feb
134 | My Members | 2018-02-21 | 2018-05-15 | 60 | LS | Android V1.4(20) | 3 | After click Dustbin, the member list should not have the line on the most bottom list item. | [5 empty] | 100% |  |  | 2018-03-23 |  |  | N/A | Closed | Yes |  | Yes | Temporary release in Feb |  | LS to review
135 | Radio Settings | 2018-02-21 | 2018-07-07 | 98 | LS | Android V1.4(20) | 2 | The Vibracall, Keypad tone switch should be same design as IOS. | [5 empty] | 100% |  |  | 2018-03-23 |  | 7/7/2018 Andriod V2.1 | N/A | Closed | Yes |  | Yes | Temporary release in Feb
136 | Radio Settings | 2018-02-21 | 2018-05-30 | 71 | LS | iOS V1.1 (20), Android V1.4(20) | 2 | Easy Pairing is not working. | [5 empty] | 100% |  |  | 2018-03-23 |  | 5/30/2018 IOS V1.2 (1230) 7/7/2018 Andriod V2.1 | Closed | Closed | Yes |  | Yes | Temporary release in Feb
137 | Radio Settings | 2018-02-21 | 2018-07-07 | 98 | LS | Android V1.4(20) | 2 | Weather - I have not make any changes, the message "The Setting has been sent to your radio successfully" keep appearing. | [5 empty] | 100% |  |  |  |  | 7/7/2018 Andriod V2.1 | N/A | Closed | Yes |  | Yes | Temporary release in Feb
138 | Radio Settings | 2018-02-21 | 2018-07-07 | 98 | LS | Android V1.4(20) | 2 | The "i" = information button is not working | [5 empty] | 100% |  |  | 2018-03-23 |  | 7/7/2018 Andriod V2.1 | N/A | Closed | Yes |  | Yes | Temporary release in Feb
139 | Help and Support | 2018-02-21 | 2018-05-15 | 60 | LS | Android V1.4(20) | 3 | Inside the list, the Help and Support list should not have icons. The last list menu should not show line. | [5 empty] | 100% |  |  | 2018-03-23 |  |  | N/A | Closed | Yes |  | Yes | Temporary release in Feb |  | LS to review
140 | About | 2018-02-21 | 2018-07-07 | 98 | LS | Android V1.4(20) | 3 | Inside the list, there should not have icons. | [5 empty] | 100% |  |  | 2018-03-23 |  | 7/7/2018 Andriod V2.1 | N/A | Closed | Yes |  | Yes | Temporary release in Feb
141 | About | 2018-02-21 | 2018-07-07 | 98 | LS | Android V1.4(20) | 2 | App Info is not working | [5 empty] | 100% |  |  | 2018-03-23 |  | 7/7/2018 Andriod V2.1 | N/A | Closed | Yes |  | Yes | Temporary release in Feb
142 | Help and Supports | 2018-02-21 | 2018-07-07 | 98 | LS | Android V1.4(20) | 2 | FAQ and Troubleshooting, and Send Feedback are not working | [5 empty] | 100% |  |  | 2018-03-23 |  | 7/7/2018 Andriod V2.1 | N/A | Closed | Yes |  | Yes | Temporary release in Feb
143 | Maps | 2018-02-21 | 2018-07-07 | 98 | LS | Android V1.4(20) | 3 | When tap the Map Style, the pop up window appear style should follow IOS, just pop up. It should not be pan from bottom. | [5 empty] | 100% |  |  | 2018-03-23 |  | 7/7/2018 Andriod V2.1 | N/A | Closed | Yes |  | Yes | Temporary release in Feb
144 | My Track | 2018-02-20 | 2018-05-15 | 61 | Marjon | iOS V1.1(20) | 1 | Wrong GPS reading. See image here: http://compass.mot-solutions.com/doc/535945199/1_wrong_gps_reading.JPG. You see the line spike to accross the river. In reality the trail continued on same side of river (I did not fly over the river and back). I think the GPS sigN/Al got picked up on the other side (not sure why, I was not in airplane mode, so maybe has to do with cell tower). Anyway, my husband was tracking same trail on his Gaia GPS app on his phone and they did not have the issue. What they likely do have some intelligence in the tracking that if a gps coordiN/Ate is far off what is reasoN/Able (based on speed etc), they ignore the reading of that. The app needs to distinguished deviations that do not make sense so when GPS sigN/Al is lost and the map shows track incorrect they need to be able to correct it and ignore 'false' information. Suggest Intelligent alogoritms (use prior speed, time lapsed, distance etc.). | [5 empty] | 50% |  |  | 2018-04-20 |  | IOS V1.2 (1236) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | - | [6 empty] | not duplicate in IOS V1.2 (1236)
145 | On boarding | 2018-02-20 | 2018-07-07 | 99 | FT | Android V1.4(20) | 2 | During PAIRING, why is APP asking permission to access media/photos etc? I keep click on DENY for 8 times, then it will disappear. Is this necessary? | [5 empty] | 100% |  |  | 2018-03-23 |  | 7/7/2018 Andriod V2.1 | N/A | Closed | Yes |  | Yes | Temporary release in Feb
146 | On boarding | 2018-02-20 | 2018-07-07 | 99 | FT | Android V1.4(20) | 2 | I noticed that Android APP will auto turn on the Bluetooth, but the permission to turn on Bluetooth pop up message never appear. Please follow VI design. | [5 empty] | 100% |  |  | 2018-03-23 |  | 7/7/2018 Andriod V2.1 | N/A | Closed | Yes |  | Yes | Temporary release in Feb
147 | On boarding | 2018-02-20 | 2018-07-09 | 100 | FT | Android V1.4(20) | 1 | 1. Error when try to launch Talkabout APP 2. Pop up message ask permission to access media/photos keep appears. 3. UN/Able to UNPAIR. Check video here: http://compass.mot-solutions.com/doc/535951470/Android_V1.4(20)_on_boarding_error.MOV | [5 empty] | 50% |  |  | 2018-03-23 |  | 7/9/2018 Andriod V2.2 | N/A | Closed | Yes |  | Yes | Temporary release in Feb
148 | On boarding | 2018-02-20 | 2018-05-30 | 72 | FT | iOS V1.1(20) | 2 | Whenever I re-open APP, if the phone Bluetooth is disable, there is no pop up message to remind me to turn on Bluetooth. So the radio and APP never paired. | [5 empty] | 100% |  |  | 2018-03-23 |  | 5/30/2018 IOS V1.2 (1231) | Closed | N/A | Yes |  | Yes | Temporary release in Feb
149 | On boarding | 2018-02-20 | 2018-05-30 | 72 | FT | iOS V1.1(20) | 1 | Whenever I re-open APP, the radio will not auto reconnect to APP even though phone Bluetooth is eN/Abled. Always need to unpair radio then pair again. | [5 empty] | 100% |  |  | 2018-03-23 |  | 5/30/2018 IOS V1.2 (1231) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
150 | On boarding | 2018-02-20 | 2018-05-15 | 61 | FT | Android V1.4(20) | 1 | When wifi and mobile data is turned off, uN/Able to get verification code SMS. Isn't as long as has phone network(no data) user able to get verification code? | [5 empty] | 100% |  | Need network to get verification code SMS |  |  |  | N/A | N/A | No |  |  |  |  | not an issue, verification code needs data/ wifi. |  |  | 1
151 | On boarding | 2018-02-20 | 2018-07-07 | 99 | FT | Android V1.4(20) | 2 | After key in verification code and enter first TIPS, 'get verification code fail' message pop up and disappeared. | [5 empty] | 100% |  |  | 2018-03-23 |  | 7/7/2018 Andriod V2.1 | N/A | Closed | Yes |  | Yes | Temporary release in Feb
152 | Bluetooth Connection | 2018-02-20 | 2018-05-30 | 72 | FT | iOS V1.1(20) | 3 | Hamburger menu --> Bluetooth Connection --> The page header showing Bluetooth Settings. It should be Bluetooth Connection. Android did it correctly. | [5 empty] | 100% |  |  | 2018-03-23 |  | 5/30/2018 IOS V1.2 (1231) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
153 | Hamburger Menu | 2018-02-20 | 2018-07-07 | 99 | FT | Android V1.4(20) | 2 | Hamburger menu --> Bluetooth Connection --> click on the top left arrow back button --> should bring user to hamburger menu. In Android it brings user to Chat screen. Please follow how IOS do it. | [5 empty] | 100% |  |  | 2018-03-23 |  | 7/7/2018 Andriod V2.1 | N/A | Closed | Yes |  | Yes | Temporary release in Feb
154 | Bluetooth Connection | 2018-02-20 | 2018-07-09 | 100 | FT | Android V1.4(20) | 1 | Hamburger menu --> Bluetooth Connection --> Click on Unpair radio --> Bluetooth Connection status in APP still showing Connected, on radio side Bluetooth icon still showing connected. Click on Pair radio, then power off radio, before radio is power on again, APP shows pair succesful. This is very weird. After few seconds, radio side have pair success tone and Bluetooth icon showing pair successful. | [5 empty] | 50% |  |  | 2018-03-23 |  | 7/9/2018 Andriod V2.2 | N/A | Closed | Yes |  | Yes | Temporary release in Feb
155 | Bluetooth Connection | 2018-02-20 | 2018-05-15 | 61 | FT | Android V1.4(20) | 2 | Power off radio, APP side still showing status Connected for few seconds. The connection status sync is slow. | [5 empty] | 100% |  | This is normal within 30s. APP will only update up to 30s period. |  |  |  | N/A | N/A | No |  |  |  |  | Depending on Phone system. Not an issue? |  |  | 1
156 | Bluetooth Connection | 2018-02-21 | 2018-07-09 | 99 | FT | Android V1.4(20) | 1 | I have pair radio with my LG phone yesterday. This morning when I turn on radio, the Bluetooth connection will not auto connect. Try to unpair radio then pair again, still fail to connect. I need to kill the APP in order to connect radio to APP. | [5 empty] | 100% |  |  | 2018-03-23 |  | 7/9/2018 Andriod V2.2 | N/A | Closed | Yes |  | Yes | Temporary release in Feb
157 | On boarding | 2018-02-21 | 2018-07-09 | 99 | FT | Android V1.4(20) | 1 | I kill the APP then launch again. The APP will start from branding screen, skip privacy policy, go through the setup and ask me to create a new account again. This should not be the way. I did not delete account. | [5 empty] | 100% |  |  | 2018-03-23 |  | 7/9/2018 Andriod V2.2 | N/A | Closed | Yes |  | Yes | Temporary release in Feb
158 | Myself | 2018-02-21 | 2018-07-07 | 98 | FT | Android V1.4(20) | 2 | I have changed profile picture. But every time when I go to MYSELF, profile pic will show the old photo then only change to new photo. See video: http://compass.mot-solutions.com/doc/535939614/Android_Profile_Pic_Bug.MOV | [5 empty] | 100% |  |  | 2018-03-23 |  | 7/7/2018 Andriod V2.1 | N/A | Closed | Yes |  | Yes | Temporary release in Feb
159 | My Members | 2018-02-21 | 2018-07-07 | 98 | FT | Android V1.4(20) | 2 | My Members --> Add Members --> Search phone contacts does not work. It does not go to phone contact list. | [5 empty] | 100% |  |  | 2018-03-23 |  | 7/7/2018 Andriod V2.1 | N/A | Closed | Yes |  | Yes | Temporary release in Feb
160 | My Members | 2018-02-21 | 2018-07-07 | 98 | FT | Android V1.4(20) | 2 | On My Members list, there is default photo assigned. It should just use a logo same as how iOS version did. | [5 empty] | 100% |  |  | 2018-03-23 |  | 7/7/2018 Andriod V2.1 | N/A | Closed | Yes |  | Yes | Temporary release in Feb
161 | My Members | 2018-02-21 | 2018-07-07 | 98 | FT | Android V1.4(20) | 3 | On My Members contact, tap on the member N/Ame, the color of the circle will change. If I do not set any color, the color will keep changing. | [5 empty] | 100% |  |  | 2018-03-23 |  | 7/7/2018 Andriod V2.1 | N/A | Closed | Yes |  | Yes | Temporary release in Feb
162 | My Members | 2018-02-21 | 2018-07-07 | 98 | FT | Android V1.4(20) | 2 | Hamburger menu --> My Members --> Click on any member N/Ame --> the title shows MYSELF. | [5 empty] | 100% |  |  | 2018-03-23 |  | 7/7/2018 Andriod V2.1 | N/A | Closed | Yes |  | Yes | Temporary release in Feb
163 | My Members | 2018-02-21 | 2018-05-30 | 71 | FT | iOS V1.1(20) | 2 | Hamburger menu --> My Members --> Click on any member N/Ame --> the title shows MEMBER. It should show the N/Ame. | [5 empty] | 100% |  |  | 2018-03-23 |  | 5/30/2018 IOS V1.2 (1231) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
164 | My Maps | 2018-02-21 | 2018-07-09 | 99 | FT | Android V1.4(20) | 2 | After reN/Ame offline map N/Ame, there is no way to hide the keyboard. | [5 empty] | 100% |  |  | 2018-03-23 |  | 7/9/2018 Andriod V2.2 | N/A | Closed | Yes |  | Yes | Temporary release in Feb
165 | My Maps | 2018-02-21 | 2018-07-07 | 98 | FT | Android V1.4(20) | 2 | Change My Waypoints to Location Pin | [5 empty] | 100% |  |  | 2018-03-23 |  | 7/7/2018 Andriod V2.1 | N/A | Closed | Yes |  | Yes | Temporary release in Feb
166 | App Settings | 2018-02-21 | 2018-07-07 | 98 | FT | Android V1.4(20) | 2 | When choose to delete account, Bluetooth connection on radio does not disconnect immediately. | [5 empty] | 100% |  |  | 2018-03-23 |  | 7/7/2018 Andriod V2.1 | N/A | Closed | Yes |  | Yes | Temporary release in Feb
167 | Radio Settings | 2018-02-21 | 2018-05-30 | 71 | FT | iOS V1.1(20) | 2 | The 'i' is missing from Radio Settings page top right corner | [5 empty] | 100% |  |  | 2018-03-23 |  | 5/30/2018 IOS V1.2 (1231) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
168 | Bluetooth Connection | 2018-02-21 | 2018-07-07 | 98 | FT | Android V1.4(20) | 2 | Model, Version and Battery has no info | [5 empty] | 100% |  |  | 2018-03-23 |  | 7/7/2018 Andriod V2.1 | N/A | Closed | Yes |  | Yes | Temporary release in Feb
169 | App/Radio setting | 2018-02-21 | 2018-07-09 | 99 | Dennis | Android V1.4(20) | 1 | Starting APP can be pairing after that it was auto disconnect and can not pairing need to restart again (Android Phone) | [5 empty] | 50% |  |  | 2018-03-23 |  | 7/9/2018 Andriod V2.2 | N/A | Closed | Yes |  | Yes | Temporary release in Feb
170 | Bluetooth Connection | 2018-02-21 | 2018-07-09 | 99 | Dennis | Android V1.4(20) | 1 | from the status show connected but the test button no function . | [5 empty] | 100% |  |  | 2018-03-23 |  | 7/9/2018 Andriod V2.2 | N/A | Closed | Yes |  | Yes | Temporary release in Feb
171 | Bluetooth Connection | 2018-02-21 | 2018-07-07 | 98 | Dennis | Android V1.4(20) | 2 | sometime the status there was not showing connected/disconnected | [5 empty] | 50% |  |  | 2018-03-23 |  | 7/7/2018 Andriod V2.1 | N/A | Closed | Yes |  | Yes | Temporary release in Feb
172 | Chat | 2018-02-21 | 2018-07-09 | 99 | Dennis | Android V1.4(20) | 1 | after send the chat message will pop up "unfortunely ,talkabout has stopped" . | [5 empty] | 50% |  |  | 2018-03-23 |  | 7/9/2018 Andriod V2.2 | N/A | Closed | Yes |  | Yes | Temporary release in Feb
173 | Bluetooth Connection | 2018-02-21 | 2018-05-31 | 72 | FT | iOS V1.1(20) | 1 | Bluetooth connection between radio and APP will suddenly lost. But at radio side is still showing connected. APP side showing 'Connecting'. Need to reset radio to establish the Bluetooth connection. | [5 empty] | 50% |  |  | 2018-03-23 |  | 5/31/2018 IOS V1.2 (1231) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
174 | Bluetooth Connection | 2018-02-21 | 2018-05-31 | 72 | FT | iOS V1.1(20) | 1 | After received 1 text message or sent 1 text message, the Bluetooth connection will lost. | [5 empty] | 100% |  |  | 2018-03-23 |  | 5/31/2018 IOS V1.2 (1231) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
175 | Shout | 2018-02-21 | 2018-05-31 | 72 | FT | iOS V1.1(20) | 2 | Text message overlapping. Using iphone 5s. Refer photo here: http://compass.mot-solutions.com/doc/535966623/iphone_5S_text_message_overlapping.PNG | [5 empty] | 100% |  |  | 2018-03-23 |  | 5/31/2018 IOS V1.2 (1231) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
176 | Chat | 2018-02-21 | 2018-07-07 | 98 | FT | Android V1.4(20) | 2 | Text message not following wireframes/VI design. Inside SHOUT, it shows 'N/AME: FT', shall only show 'FT'. At Chat Home screen, shall show 'me: test 3', now only show 'test 3'. | [5 empty] | 100% |  |  | 2018-03-23 |  | 7/7/2018 Andriod V2.1 | N/A | Closed | Yes |  | Yes | Temporary release in Feb
177 | Help and Support | 2018-02-21 | 2018-07-07 | 98 | FT | Android V1.4(20) | 2 | Help & Support --> Motorola Contact Info --> the email address should be an active email link to open email client. | [5 empty] | 100% |  |  | 2018-03-23 |  | 7/7/2018 Andriod V2.1 | N/A | Closed | Yes |  | Yes | Temporary release in Feb
178 | Shout | 2018-02-21 | 2018-05-31 | 72 | FT | iOS V1.1(20) | 2 | It does not show the shout message is from who. In chat home screen it shows the sender ID, but when go into Shout message, does not show. | [5 empty] | 100% |  |  | 2018-03-23 |  | 5/31/2018 IOS V1.2 (1231) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
179 | My Tracks | 2018-02-21 | 2018-07-07 | 98 | Dennis | Android V1.4(20) | 2 | inside my tracks when press "Show on map" it go to chat | [5 empty] | 100% |  |  | 2018-03-23 |  | 7/7/2018 Andriod V2.1 | N/A | Closed | Yes |  | Yes | Temporary release in Feb
180 | App setting | 2018-02-21 | 2018-07-07 | 98 | Dennis | Android V1.4(20) | 2 | App setting default was not same to wireframes . | [5 empty] | 100% |  |  | 2018-03-23 |  | 7/7/2018 Andriod V2.1 | N/A | Closed | Yes |  | Yes | Temporary release in Feb
181 | Shout | 2018-02-21 | 2018-05-15 | 60 | FT | iOS V1.1(20), Android V1.4(20) | 2 | In Shout, share Offline Map. Rx side does not get anything. Note: Receive side is Android phone. | [5 empty] | 100% |  |  | 2018-03-23 |  |  | N/A | N/A | No |  |  |  |  | not available to share Offline Maps in SHOUT. Not an issue? |  |  | 1
182 | Radio Settings | 2018-02-21 | 2018-07-07 | 98 | Dennis | Android V1.4(20) | 2 | in radio setting press easy pairing was nothing come out | [5 empty] | 100% |  |  | 2018-03-23 |  | 7/7/2018 Andriod V2.1 | N/A | Closed | Yes |  | Yes | Temporary release in Feb
183 | Shout | 2018-02-21 | 2018-05-31 | 72 | FT | iOS V1.1(20) | 2 | There is no message delivered notification | [5 empty] | 100% |  |  | 2018-04-13 |  | 5/31/2018 IOS V1.2 (1231) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
184 | Bluetooth Connection | 2018-02-21 | 2018-07-09 | 99 | Dennis | Android V1.4(20) | 1 | radio power off but the app still showing connected | [5 empty] | 50% |  | This is normal within 30s. APP will only update up to 30s period. |  |  | 7/9/2018 Andriod V2.2 | N/A | Closed | Yes |  | Yes | Temporary release in Feb
185 | Chat | 2018-02-21 | 2018-07-07 | 98 | Dennis | Android V1.4(20) | 2 | at the chat there press the member that we have add can not go in | [7 empty] | UN/Able to reproduce issue |  |  | 7/7/2018 Andriod V2.1 | N/A | Closed | Yes |  | Yes | Temporary release in Feb
186 | On boarding | 2018-02-22 | 2018-05-31 | 71 | FT | iOS V1.1(20) | 3 | TIPS #1: Link is overlaped with sentence above. Using iphone 5S. See photo: http://compass.mot-solutions.com/doc/535964643/IOS_Tips_1_Overlapped.PNG | [5 empty] | 100% |  |  | 2018-03-23 |  | 5/31/2018 IOS V1.2 (1231) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
187 | Bluetooth Connection | 2018-02-22 | 2018-05-31 | 71 | FT | iOS V1.1(20) | 2 | Pair iphone to radio#1. Then turn off radio#1. Turn on radio#2. App not able to auto connect with radio#2. Note: radio#2 paired with LG phone yesterday. | [5 empty] | 100% |  | APP will only auto pair with paired radio. |  |  | 5/31/2018 IOS V1.2 (1231) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
188 | Bluetooth Connection | 2018-02-22 | 2018-05-31 | 71 | FT | iOS V1.1(20) | 1 | Pair iphone to radio#1. Then turn off radio#1. Turn on radio#2. App not able to auto connect with radio#2. I need to unpair, then only able to pair with radio#2. However after pair the status in APP and radio shows connected, but when I click TEST, no response at radio. Change channel from APP, no response at radio. The Bluetooth connection does not seems to be real. Then I will need to Leave Setup and Create Accout again. Note: radio#2 paired with LG phone yesterday. | [5 empty] | 100% |  | Radio issue | 2018-03-23 |  | 5/31/2018 IOS V1.2 (1231) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
189 | Bluetooth Connection | 2018-02-22 | 2018-05-15 | 59 | FT | iOS V1.1(20) | 2 | I paired radio#2 with iphone. Then I try to pair radio#1 with LG phone. After turn on radio#1, the Bluetooth shows connected after 1 second. But LG phone still show disconnected. After checked, seems like radio#1 become connects to iphone(I changed radio channel from iphone, radio#1 shows response). At this time radio#2 still show bluetooth connected, which phone is radio#2 connected to? Note: Yesterday radio#1 paired with iphone, radio#2 paired with LG phone. | [5 empty] | 100% |  | Radio issue | 2018-03-23 |  | IOS V1.2 (1236) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
190 | On boarding | 2018-02-22 | 2018-07-07 | 97 | Dennis | Android V1.4(20) | 3 | Preparation for setup/ phone setup: Change the button from CONTINUE to NEXT. CHange the sentence from click continue to click next. | [5 empty] | 100% |  |  | 2018-03-23 |  | 7/7/2018 Andriod V2.1 | N/A | Closed | Yes |  | Yes | Temporary release in Feb
191 | On boarding | 2018-02-22 | 2018-05-30 | 70 | FT | iOS V1.1(20) | 3 | Talkabout Radio Setup: The radio antenN/A is overlap with wordings. iOS iphone 5s. See photo here: http://compass.mot-solutions.com/doc/535989203/iOS_Radio_AntenN/A_Overlapping_With_Wordings.PNG | [5 empty] | 100% |  |  | 2018-03-23 |  | 5/30/2018 IOS V1.2 (1231) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
192 | On boarding | 2018-02-22 | 2018-07-07 | 97 | FT | Android V1.4(20) | 3 | PAIRING page, the left button should be LEAVE SETUP according to VI design. In the APP is CANCEL. | [5 empty] | 100% |  |  | 2018-03-23 |  | 7/7/2018 Andriod V2.1 | N/A | Closed | Yes |  | Yes | Temporary release in Feb
193 | Bluetooth Connection | 2018-02-22 | 2018-07-09 | 98 | FT | Android V1.4(20) | 1 | I paired radio#1 with iphone yesterday. Today I wanted to pair radio#1 with LG phone but fail. Reset radio, does not help. I kill the app for 1st time, not work. 2nd time kill the app only it works. After few minutes the Bluetooth connection lost. I have to kill the app + reset radio a few times to connect Bluetooth back. | [5 empty] | 50% |  |  | 2018-03-23 |  | 7/9/2018 Andriod V2.2 | N/A | Closed | Yes |  | Yes | Temporary release in Feb
194 | Map | 2018-02-22 | 2018-05-15 | 59 | Dennis | Android V1.4(20) | 3 | From VI Mapbox Menu only 3 selection from app got 4 selection. | [5 empty] | 100% |  | This is define by Mapbox |  |  |  | N/A | Closed | Yes |  | Yes | Temporary release in Feb
195 | Chat | 2018-02-22 | 2018-07-09 | 98 | FT | iOS V1.1(20), Android V1.4(20) | 1 | 1st try: Out of 20 messages, 2 of the messages did not received. 2nd try: Out of 20 messages, 9 of the messages did not received. Note: Android Rx, iOS Tx. | [5 empty] | 50% |  | Radio issue |  |  | 7/9/2018 Andriod V2.2 | Closed | Closed | Yes |  | Yes | Temporary release in Feb
196 | Add New Member | 2018-02-22 | 2018-07-07 | 97 | Dennis | Android V1.4(20) | 2 | in add new members press search phone contacts no function | [5 empty] | 100% |  |  | 2018-03-23 |  | 7/7/2018 Andriod V2.1 | N/A | Closed | Yes |  | Yes | Temporary release in Feb
197 | Chat | 2018-02-22 | 2018-07-09 | 98 | FT | Android V1.4(20) | 1 | When the APP receive more than 8 characters (example 'test aaa') APP will suddenly jump out with this pop up message 'UnfortuN/Ately Talkabout has stop working'. | [5 empty] | 100% |  |  | 2018-03-23 |  | 7/9/2018 Andriod V2.2 | N/A | Closed | Yes |  | Yes | Temporary release in Feb
198 | Chat | 2018-02-22 | 2018-05-30 | 70 | FT | iOS V1.1(20), Android V1.4(20) | 2 | The sent and delivered notification tick color is too close, grey and white. User might not be able to see the different. VI will be updated. | [5 empty] | 100% |  |  | 2018-03-23 |  | 5/30/2018 IOS V1.2 (1231) 7/7/2018 Andriod V2.1 | Closed | Closed | Yes |  | Yes | Temporary release in Feb
199 | Chat | 2018-02-22 | 2018-07-09 | 98 | FT | iOS V1.1(20), Android V1.4(20) | 1 | Android Tx, iOS Rx. Sent 20 messages, iOS received 7. but Android only get 4 delivered notification. | [5 empty] | 70% |  | Radio issue |  |  | 7/9/2018 Andriod V2.2 | Closed | Closed | Yes |  | Yes | Temporary release in Feb
200 | Chat | 2018-02-22 | 2018-05-30 | 70 | FT | iOS V1.1(20) | 2 | UN/Able to read complete message. Using iphone 5S. See photo: http://compass.mot-solutions.com/doc/535995143/iOS_Text_Message_Not_Able_To_View.PNG | [5 empty] | 70% |  |  | 2018-03-23 |  | 5/30/2018 IOS V1.2 (1231) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
201 | Radio Settings | 2018-02-23 | 2018-05-30 | 69 | SK | iOS V1.1(20) | 2 | Adjust the Call Tone in APP, sometimes the display abnormal: 1. display number of call tone abnormal. 2. another case is when i entered Menu from Radio "Menu Button", then now adjust the call tone number, Radio is not displaying the Call Tone number selection. | [5 empty] | 100% |  | Radio issue |  |  | 5/30/2018 IOS V1.2 (1231) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
202 | Radio Settings | 2018-02-23 | 2018-05-30 | 69 | SK | iOS V1.1(20) | 2 | Radio setting Keypad tone is ON by default, but the App Keypad Tone is OFF. | [5 empty] | 100% |  |  | 2018-03-23 |  | 5/30/2018 IOS V1.2 (1231) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
203 | Chat | 2018-02-23 | 2018-05-30 | 69 | SK | iOS V1.1(20) | 1 | Sometimes Radio will automatically power off when Chatting (sender side), i need to reset radio and the last message not delivered to receiver phone. | [5 empty] | 60% |  | Radio issue |  |  | 5/30/2018 IOS V1.2 (1231) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
204 | MAPS | 2018-02-23 | 2018-05-30 | 69 | SK | iOS V1.1(20) | 1 | IOS version 10.3.3 and 11.0.3 we have, MAPS > MY TRACK, MY LOCATION PIN, GEOFENCE > cannot do selection while IOS version 11.2.6 OK See issue photo here: http://compass.mot-solutions.com/doc/536054785/Maps_My_Location_Pin_No_selection_button_Save.PNG http://compass.mot-solutions.com/doc/535623289/Maps_My_Track_No_selection_button_to_save_or_cancel.PNG | [5 empty] | 100% |  |  | 2018-03-23 |  | 5/30/2018 IOS V1.2 (1231) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
205 | Bluetooth Connection | 2018-02-26 | 2018-05-30 | 68 | SK | iOS V1.1(20) | 1 | New installed the APP, try to connect to Radio, after Blutooth connected, Radio Screen showing in Freq = 0, Code = 0. | [5 empty] | 100% |  |  | 2018-03-23 |  | 5/30/2018 IOS V1.2 (1231) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
206 | MySelf | 2018-02-26 | 2018-05-31 | 69 | SK | iOS V1.1(20) | 2 | User N/Ame can add over than 32 characters, it should less than 32 characters. | [5 empty] | 100% |  |  | 2018-03-23 |  | 5/31/2018 IOS V1.2 (1231) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
207 | Chat | 2018-02-26 | 2018-05-31 | 69 | SK | iOS V1.1(20) | 2 | Add member: Added same ID/ number, with 2 different N/Ame, cannot update correctly in TALKABOUT CHAT history page. Step to duplicate: 1. In Chat, to add member with phone # or ID and assigned N/Ame as SK1 for example. 2. Now we can see in "New Chat" displayed a member as "SK1" 3. Back to the Chat page to add another N/AME as "SK2" with same ID or phone number. 4. after the "SK2" added, back to the CHAT page, the "SK1" not updated to "SK2". 5. But we can see in "New Chat" member had updated/ replaced to "SK2". 6. Then now we try to click the New N/Ame member "SK2" system will go to the Chat mode with N/Ame as "SK1". where it should changed as "SK2". | [5 empty] | 100% |  |  | 2018-03-23 |  | 5/31/2018 IOS V1.2 (1231) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
208 | Bluetooth Connection | 2018-02-26 | 2018-05-31 | 69 | Marjon | iOS V1.1(20) | 2 | When you go to check if the Bluetooth is connected at first the Bluetooth connection screen shows not connected and it quickly changes to connected. Should immediately show connected and not first not connected. | [5 empty] | 100% |  |  | 2018-03-23 |  | 5/31/2018 IOS V1.2 (1231) | Closed | N/A | Yes |  | Yes | Temporary release in Feb
209 | General | 2018-02-26 | 2018-05-15 | 57 | LiN/Ar | Android V1.4(20) | 1 | While sending text message on LG phone, the LG phone suddenly shut down. Try to power up again, the LG phone screen is forever stop at start up branding screen. Take out battery and insert again still the same. Now the LG phone is damage. | [5 empty] | 5% |  | Should be not due to APP |  |  |  | N/A | Closed | Yes |  | Yes | Temporary release in Feb
210 | Bluetooth Connection | 2018-02-26 | 2018-05-31 | 69 | Marjon | iOS V1.1(20), Android V1.4(20) | 1 | Radio pairing does not always work automatically, sometimes requires killing app and turning on/of radio a few times. | [5 empty] | 50% |  | Radio issue | 2018-03-23 |  | 5/31/2018 IOS V1.2 (1231) 7/9/2018 Andriod V2.2 | Closed | Closed | Yes |  | Yes | Temporary release in Feb
211 | Bluetooth Connection | 2018-02-26 | 2018-05-31 | 69 | Marjon | iOS V1.1(20) | 1 | Random behavior, sometimes when connecting, the app channel/code setting gets changed on the radio when pairing, but other times stays on the origiN/Al radio setting. When that happens, even though radio shows connected, it wont react to radio setting changes on the app. unpair and repair did not solve. Had to close app, unpair and pair. Only then it was functioning ok again. When paired success, APP shall follow all settings in radio. After that, whichever side has done changes, the other side shall follow. Example make change in APP, radio shall follow. | [5 empty] | 50% |  | Radio issue | 2018-03-23 |  | 5/31/2018 IOS V1.2 (1231) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
212 | Chat | 2018-02-26 | 2018-05-15 | 57 | Marjon | iOS V1.1(20) | 1 | Very few messages go through and sometimes only from A to B , not from B to A. Very random behavior. Needs rigoureous testing with many radios at the same time (also in larger group setting, at different distances, under different sceN/Arios (voice in the mix etc. ) | [5 empty] | 50% |  | Radio issue |  |  | IOS V1.2 (1236) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | - | [6 empty] | but need more radio to confirm, now did not see in 2 radios interaction.
213 | Chat | 2018-02-26 | 2018-05-31 | 69 | Marjon | iOS V1.1(20), Android V1.4(20) | 2 | There is no unread message or incoming message notification when APP is at the background. Wireframes/VI need to be updated. | [5 empty] | 100% |  |  | 2018-04-13 |  | 5/31/2018 IOS V1.2 (1231) 7/8/2018 Andriod V2.2 | Closed | Closed | Yes |  | Yes | Temporary release in Feb
214 | Chat | 2018-02-26 | 2018-05-31 | 69 | Marjon | iOS V1.1(20), Android V1.4(20) | 2 | There is no unread message or incoming message notification when APP is at chat home screen (not inside Shout/1-1chat/group chat window). Wireframes/VI need to be updated. | [5 empty] | 100% |  |  | 2018-04-13 |  | 5/31/2018 IOS V1.2 (1231) 7/8/2018 Andriod V2.2 | Closed | Closed | Yes |  | Yes | Temporary release in Feb
215 | Chat | 2018-02-26 | 2018-05-31 | 69 | SK | iOS V1.1(20) | 2 | After received a new chat message from a new user (not added in Member list), now open the received message to edit the N/Ame, but the edited N/Ame did not take action to reflect. | [5 empty] | 100% |  |  | 2018-03-23 |  | 5/31/2018 IOS V1.2 (1231) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
216 | Chat | 2018-02-26 | 2018-05-31 | 69 | SK | iOS V1.1(20) | 2 | sometimes the sent message not deliver to the receiver, if continuesly send a few messages.. | [5 empty] | 60% |  | Radio issue |  |  | 5/31/2018 IOS V1.2 (1231) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
217 | Chat | 2018-02-26 | 2018-05-31 | 69 | SK | iOS V1.1(20) | 1 | After received 1 text message or sent 1 text message, the radio DIED, but the volume knob in switching ON status (powering ON). | [5 empty] | 30% |  | Radio issue |  |  | 5/31/2018 IOS V1.2 (1231) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
218 | Chat | 2018-02-26 | 2018-05-15 | 57 | Li N/Ar | Android V1.4(20) | 1 | Tested using LG brand phone, after few times sending text message, the smartphone suddenly reset itself, then hang, cannot recover even after remove and reinsert battery for the LG smart phone. Now the LG phone not able to power up. When try to power up it will stay at the LG start up/branding screen. | [5 empty] | 10% |  | Phone issue |  |  |  | N/A | Closed | Yes |  | Yes | Temporary release in Feb
219 | My Members | 2018-02-27 | 2018-05-31 | 68 | Marjon | iOS V1.1(20), Android V1.4(20) | 2 | When you add a contact from phone contact list, it does not take the N/Ame only phone number. Prefer to copy the N/Ame as well. | [5 empty] | 100% |  |  | 2018-03-30 |  | 5/31/2018 IOS V1.2 (1231) 7/8/2018 Andriod V2.2 | Closed | Closed | Yes |  | Yes | Temporary release in Feb
220 | Myself | 2018-02-27 | 2018-06-06 | 72 | Marjon | iOS V1.1(20), Android V1.4(20) | 2 | The contact card still showing ‘MYSELF’ in the title. if feasible have Myself be updated to the real N/Ame of the person. ‘Change your N/Ame’ should be change contact’s N/Ame or similar. Please refer to latest wireframes/VI. (Change Profile N/Ame) | [5 empty] | 100% |  |  | 2018-03-30 |  | 6/6/2018 IOS V1.2 (1234) 7/8/2018 Andriod V2.2 | Closed | Closed | Yes |  | Yes | Temporary release in Feb | [7 empty] | Results will be seen in the latest software version
221 | My Maps | 2018-02-27 | 2018-06-06 | 72 | Marjon | iOS V1.1(20), Android V1.4(20) | 2 | My location pin is confusing N/Aming because of the other option with the locator. Indeed they are my location pins but does not reflect my location. Delete all references to 'my'. Should just be 'location pin'. (make sure it is deleted everywhere where it occurs (eg. Predefined Messages). Please refer to latest wireframes/VI. | [5 empty] | 100% |  |  | 2018-03-23 |  | 6/6/2018 IOS V1.2 (1234) 7/8/2018 Andriod V2.2 | Closed | Closed | Yes |  | Yes | Temporary release in Feb | [7 empty] | Results will be seen in the latest software version
222 | My Maps | 2018-02-27 | 2018-05-31 | 68 | Marjon | iOS V1.1(20), Android V1.4(20) | 2 | Add feature to allow to select map layers in download map view. Please refer to latest wireframes/VI. | [5 empty] | 100% |  |  | 2018-04-06 |  | 5/31/2018 IOS V1.2 (1231) 7/8/2018 Andriod V2.2 | Closed | Closed | Yes |  | Yes | Temporary release in Feb
223 | My Maps | 2018-02-27 | 2018-05-31 | 68 | Marjon | iOS V1.1(20), Android V1.4(20) | 2 | Download and reN/Ame is straight forward. but if user download multiple offline maps at once, the default N/Ame should reN/Ame itself instead of user manually reN/Ame it each time. Default offline map file N/Ame shall change to Map YYYYMMDD_HH:MM:SS | [5 empty] | 100% |  |  | 2018-04-06 |  | 5/31/2018 IOS V1.2 (1231) 7/8/2018 Andriod V2.2 | Closed | Closed | Yes |  | Yes | Temporary release in Feb
224 | Maps | 2018-02-27 | 2018-05-15 | 56 | Marjon | iOS V1.1(20) | 1 | My Maps --> My Tracks: not recording elevation gain | [5 empty] | 100% |  |  | 2018-03-23 |  | IOS V1.2 (1237) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | - | [7 empty] | still open
225 | Maps | 2018-02-27 | 2018-05-15 | 56 | Marjon | iOS V1.1(20), Android V1.4(20) | 3 | My Maps --> My Tracks --> for track recording can we alert user if they have not moved for a while? E.g. Would you like to pause recording? | Y |  | N | Y | N | Open | Open | Add pop up message if user not moved for a while. |  |  |  | Closed | Closed | Yes |  | Yes | Temporary release in Feb |  | 5/31/2018 How long will the App pop up the message? i stayed at the same place for around 10 mins, but still no message pop up. 12 Jul, CS: are we fine to set to 10 mins? 18 jul, XY: new feature ,will not support 24 Jul, FT: we also shared as early as 27-Feb-18. How can you say is new request? 24 Jul, XY: agree to fix without additioN/Al cost. 31 Jul, XY: APP independent, not related to radio SW. | iOS: 3-Aug-18 Android: 10-Aug-18 |  |  |  |  | This is new demand | no pop up message. | pop up message every 10mins if no movement. | pop up message every 10mins if no movement.
226 | Maps | 2018-02-27 | 2018-05-31 | 68 | Marjon | iOS V1.1(20), Android V1.4(20) | 2 | Track recording: User should be able to reN/Ame it afterward. And the statistics unit should be unified. Current app use km as distance but average speed is in mph. | [5 empty] | 100% |  |  | 2018-04-06 |  | 5/31/2018 IOS V1.2 (1231) 7/8/2018 Andriod V2.2 | Closed | Closed | Yes |  | Yes | Temporary release in Feb
227 | Maps | 2018-02-27 | 2018-07-09 | 95 | Marjon | iOS V1.1(20), Android V1.4(20) | 1 | change Elevation to 'Total Ascent'. And should record cumulative elevation gain. | [5 empty] | 100% |  |  | 2018-04-06 |  | IOS V1.2 (1235) 7/9/2018 Andriod V2.2 | Closed | Closed | Yes |  | Yes | Temporary release in Feb
228 | Chat | 2018-02-27 | 2018-05-15 | 56 | SK | iOS V1.1(20) | 2 | If user is online, the icon will be shown in color and the outer ring will show assigned color. If the user is offline, the icon shall be shown as the grey color. *The icon still displaying color line even the members is offline. | [5 empty] | 100% |  |  | 2018-03-23 |  | IOS V1.2 (1236) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | - | [5 empty] | There is no such problem in the latest version | let me reduplicate and share the video. (issue 309)
229 | Chat | 2018-02-27 | 2018-05-31 | 68 | Marjon | iOS V1.1(20), Android V1.4(20) | 2 | Timestamp for the text messages should be more detailed. Please refer latest wireframes/VI. | [5 empty] | 100% |  |  | 2018-04-06 |  | 5/31/2018 IOS V1.2 (1231) 7/8/2018 Andriod V2.2 | Closed | Closed | Yes |  | Yes | Temporary release in Feb
230 | Chat | 2018-02-27 | 2018-05-31 | 68 | SK | iOS V1.1(20) | 2 | To add members, need to add phone number or ID at first: 1. Phone number or ID can add over than 16 digits, and the member can add successful, and no warning dialog appear to ask confirmation. | [5 empty] | 100% |  |  | 2018-03-23 |  | 5/31/2018 IOS V1.2 (1231) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
231 | Chat | 2018-02-27 | 2018-05-31 | 68 | Marjon | iOS V1.1(20), Android V1.4(20) | 1 | Triggering the emergency alert button does not result in a shout with the defined emergency message | [5 empty] | 100% |  |  | 2018-03-23 |  | 5/31/2018 IOS V1.2 (1231) 7/9/2018 Andriod V2.2 | Closed | Closed | Yes |  | Yes | Temporary release in Feb
232 | Chat | 2018-02-27 | 2018-05-31 | 68 | SK | iOS V1.1(20) | 2 | If user accidently press to select the COUNTRY CODE(where he don't want to set it) the user must select the COUNTRY CODE in order to escape. | [5 empty] | 100% |  |  | 2018-03-23 |  | 5/31/2018 IOS V1.2 (1231) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
233 | Chat | 2018-02-27 | 2018-06-06 | 72 | SK | iOS V1.1(20) | 1 | Emergency message: 1. can key in over than 90 characters (where the message is limited to 90 Characters). 2. Cannot send the message which contented >=90 Characters 3. Sometimes Message contend below than 90 characters also cannot send.. example 80 characters. | [5 empty] | 100% |  | Radio issue |  |  | 6/6/2018 IOS V1.2 (1234) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | - | [5 empty] | Now you can only enter 73 characters as required, not more than 73 characters
234 | Chat | 2018-02-27 | 2018-05-31 | 68 | SK | iOS V1.1(20) | 2 | In "SHOUT" cannot see the sender ID/user N/Ame. | [5 empty] | 100% |  |  | 2018-03-23 |  | 5/31/2018 IOS V1.2 (1231) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
235 | APP Settings | 2018-02-27 | 2018-06-06 | 72 | Marjon | iOS V1.1(20), Android V1.4(20) | 3 | default to imperial instead of metric. | [5 empty] | 100% |  |  | 2018-03-23 |  | 6/6/2018 IOS V1.2 (1234) 7/8/2018 Andriod V2.2 | Closed | Closed | Yes |  | Yes | Temporary release in Feb |  | - | [5 empty] | The effect will be seen in the latest version
236 | Chat | 2018-02-27 | 2018-05-15 | 56 | SK | iOS V1.1(20) | 2 | a recipient cannot get notification after a member had add him as in Group member. |  |  |  |  | Y | 100% | [5 empty] | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | 6-Jun-18: Still same in IOS V1.2 (1234) 26-Jun-18: No need to add notification. Just need to make sure group N/Ame is shown instead of number. | [5 empty] | The receiver can recognize the voice of the radio in time, and can also check it in MY MEMBERS and New Chat | New request need to add the notification
237 | Chat | 2018-02-27 | 2018-05-31 | 68 | SK | iOS V1.1(20) | 2 | a member send a message in Group to recipent (continue from case 227), the recepient can receive the message but without the member ID or N/Ame (* the member already isthe member in Chat list). | [5 empty] | 100% |  |  | 2018-03-23 |  | 5/31/2018 IOS V1.2 (1231) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
238 | Chat | 2018-02-27 | 2018-05-31 | 68 | SK | iOS V1.1(20) | 2 | Continue from case 227. In recipent phone app, check the Group info is Group member should display the sender ID/ N/Ame, but it is diplaying recipent ID. | [5 empty] | 100% |  |  | 2018-03-23 |  | 5/31/2018 IOS V1.2 (1231) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
239 | Bluetooth Connection | 2018-02-28 | 2018-05-31 | 67 | SK | iOS V1.1(20), Android V1.4(20) | 1 | Blutooth Connection always lost when connect to Radio received from 12Feb 2018 (P1A rework 2 units) | [5 empty] | 100% |  |  | 2018-03-23 |  | 5/31/2018 IOS V1.2 (1231) 7/9/2018 Andriod V2.2 | Closed | Closed | Yes |  | Yes | Temporary release in Feb
240 | Bluetooth Connection | 2018-02-28 | 2018-05-31 | 67 | SK | iOS V1.1(20) | 2 | Battery Level in percentage showing in iphone different: By Using a same Battery (in Radio Battery Bar is showing Full) 1 Radio P1A (5 Feb) - App showing in 100% 2 Radio P1A (12 Feb) - App Showing in 68% | [5 empty] | 100% |  |  | 2018-03-23 |  | 5/31/2018 IOS V1.2 (1231) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
241 | On boarding | 2018-02-28 | 2018-05-31 | 67 | Tze Lin | iOS V1.1(20), Android V1.4(20) | 2 | After delete account or after LEAVE SETUP, the Terms and Privacy page should appear again in on boarding. | [5 empty] | 100% |  |  | 2018-03-23 |  | 5/31/2018 IOS V1.2 (1231) 7/8/2018 Andriod V2.2 | Closed | Closed | Yes |  | Yes | Temporary release in Feb
242 | On boarding | 2018-02-28 | 2018-07-08 | 93 | Tze Lin | Android V1.4(20) | 2 | My phone already turn on BT , but it is still show permissions window " Turn on bluetooth from your phone preference" OK /DISMISS | [5 empty] | 50% |  |  | 2018-03-23 |  | 7/8/2018 Andriod V2.2 | N/A | Closed | Yes |  | Yes | Temporary release in Feb
243 | On boarding | 2018-02-28 | 2018-07-08 | 93 | Tze Lin | Android V1.4(20) | 3 | BT status " DisConnected". Typo. | [5 empty] | 100% |  |  | 2018-03-23 |  | 7/8/2018 Andriod V2.2 | N/A | Closed | Yes |  | Yes | Temporary release in Feb
244 | On boarding | 2018-02-28 | 2018-07-08 | 93 | Tze Lin | Android V1.4(20) | 2 | Click on Shout > pre- defined message , 1st message SOS not working | [5 empty] | 100% |  |  | 2018-03-23 |  | 7/8/2018 Andriod V2.2 | N/A | Closed | Yes |  | Yes | Temporary release in Feb
245 | On boarding | 2018-02-28 | 2018-07-08 | 93 | Tze Lin | Android V1.4(20) | 2 | The bluetooth was disconnected but the shout message still able to be send out | [5 empty] | 100% |  |  | 2018-03-23 |  | 7/8/2018 Andriod V2.2 | N/A | Closed | Yes |  | Yes | Temporary release in Feb
246 | Bluetooth Connection | 2018-02-28 | 2018-05-31 | 67 | FT | iOS V1.1(20) | 1 | When try to pair radio but phone Bluetooth is off, there is no reminder to inform user to turn on Bluetooth on phone. | [5 empty] | 100% |  |  | 2018-03-23 |  | 5/31/2018 IOS V1.2 (1231) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
247 | Bluetooth Connection | 2018-02-28 | 2018-05-31 | 67 | FT | iOS V1.1(20) | 2 | Sometimes the battery info is not shown in BLUETOOTH CONNECTION. It shows N/A. | [5 empty] | 80% |  |  | 2018-03-23 |  | 5/31/2018 IOS V1.2 (1231) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
248 | Chat | 2018-02-28 |  | -30828 | Marjon | iOS V1.1(20), Android V1.4(20) | 3 | There is no notification on APP icon when there is new message. Please refer to latest wireframes/VI. | N | Enh_PostD1 | N |  |  | 100% |  |  | 2018-04-13 |  | 5/31/2018 IOS V1.2 (1231) | Closed | Open | Yes |  |  |  |  | to be discuss with tzelin. XY, 9 July: not a defect, should be an enhancement. https://stackoverflow.com/questions/17565307/how-to-display-count-of-notifications-in-app-launcher-icon 24 Jul, XY: iOS已经解决了。安卓本来就不支持在app icon上显示消息数量，之前已经解释过，需要作为新功能评估成本。 25 Jul, CS: it was raised to Auctus way back in Feb, and was committed to be resolved by 13 Apr 2018 Please refer to screen captured below (Talkabout APP Issue Tracking 6-Mar-18). Therefore, It should not be still considered as New Enhancement and not to be fixed. Kindly take the necessary action and deliver Android solution not later than 3-Aug-18. 26 Jul, XY: Denied that this is not Enh. Request for costing 26 Jul, Marjon: Critical but not gating D2 Can be put as future enhancement, would be a running change for customer release.
249 | My Maps | 2018-02-28 | 2018-04-06 | 28 | Marjon | iOS V1.1(20) | 2 | My maps--> offline maps --> search map --> download --> the download will start immediately. It shall only start after user click on SAVE button. | [5 empty] | 100% |  | No change needed for now, remain current wireframe design. | 2018-04-06 |  | 2018-04-06 | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
250 | Chat | 2018-02-28 | 2018-05-31 | 67 | SK | iOS V1.1(20) | 2 | Received an message from unknown person (not in member list), in Chat will display the ID/ phone number registered. Now receiver try to set a N/Ame for it in 3 dot menu (top right) -> Member info -> Change N/Ame. Then back to Chat, the N/Ame was not changed. Also, it should appear in "My Member" list after N/Ame changed which it already add as member. | [5 empty] | 100% |  |  | 2018-03-23 |  | 5/31/2018 IOS V1.2 (1231) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
251 | Radio Settings | 2018-02-28 | 2018-05-31 | 67 | FT | iOS V1.1(20), Android V1.4(20) | 1 | When first paired success, APP shall follow setting in radio. After that, whichever side has done changes, the other side shall follow. Example make change in APP, radio shall follow. | [5 empty] | 100% |  |  | 2018-03-23 |  | 5/31/2018 IOS V1.2 (1231) 7/9/2018 Andriod V2.2 | Closed | Closed | Yes |  | Yes | Temporary release in Feb
252 | Chat | 2018-03-01 | 2018-05-15 | 54 | Tze Lin | Android V1.4(20) | 2 | Click on the "setting" button next to "SOS" , it goes to radio setting page instead of emergency msg | [5 empty] | 100% |  |  | 2018-03-23 |  |  | Closed | Closed | Yes |  | Yes | Temporary release in Feb |  | SOS changed to "Customized Message" |  |  | 1
253 | Chat | 2018-03-01 | 2018-05-31 | 66 | Tze Lin | iOS V1.1(20) | 1 | Radio sudden off , the app still show status connected even after 5min | [5 empty] | 100% |  |  | 2018-03-30 |  | 5/31/2018 IOS V1.2 (1231) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
254 | Bluetooth Connection | 2018-03-01 | 2018-05-31 | 66 | Tze Lin | iOS V1.1(20) | 1 | Radio show connected but the app still pairing | [5 empty] | 100% |  | Radio issue |  |  | 5/31/2018 IOS V1.2 (1231) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
255 | Bluetooth Connection | 2018-03-01 | 2018-05-31 | 66 | Tze Lin | iOS V1.1(20), Android V1.4(20) | 1 | After close the radio and app, the connection disconnected and not able to auto connect anymore. Need to unpair and pair again | [5 empty] | 100% |  |  | 2018-03-23 |  | 5/31/2018 IOS V1.2 (1231) 7/9/2018 Andriod V2.2 | Closed | Closed | Yes |  | Yes | Temporary release in Feb
256 | Chat | 2018-03-01 | 2018-05-31 | 66 | Tze Lin | iOS V1.1(20) | 2 | OrigiN/Ally the chat group N/Ame is "Talkabout", from the chat , reN/Ame it to "123". It show in group info but in the chat group it is not changed. | [5 empty] | 100% |  |  | 2018-03-23 |  | 5/31/2018 IOS V1.2 (1231) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
257 | Chat | 2018-03-01 | 2018-05-31 | 66 | FT | iOS V1.1(20), Android V1.4(20) | 1 | Not all SHOUT message can be received. Sometimes 5/10 not received, sometimes 10/10 not received, sometimes 8/10 not received. | [5 empty] | 90% |  | Radio issue |  |  | 5/31/2018 IOS V1.2 (1231) 7/9/2018 Andriod V2.2 | Closed | Closed | Yes |  | Yes | Temporary release in Feb
258 | Chat | 2018-03-01 | 2018-05-31 | 66 | FT | iOS V1.1(20), Android V1.4(20) | 2 | Other members received SHOUT message, but the sender does not receive delivered notification. | [5 empty] | 30% |  | Radio issue |  |  | 5/31/2018 IOS V1.2 (1231) 7/8/2018 Andriod V2.2 | Closed | Closed | Yes |  | Yes | Temporary release in Feb
259 | On boarding | 2018-03-01 | 2018-05-31 | 66 | FT | iOS V1.1(20), Android V1.4(20) | 2 | Click on Bluetooth Connection --> Unpair radio --> Leave Setup. Sometimes user will be asked to create account again. Since user does not delete account, shall not be ask to create account again. | [5 empty] | 50% |  |  | 2018-03-23 |  | 5/31/2018 IOS V1.2 (1231) 7/8/2018 Andriod V2.2 | Closed | Closed | Yes |  | Yes | Temporary release in Feb
260 | Bluetooth Connection | 2018-03-02 | 2018-05-31 | 65 | Marjon | iOS V1.1(20), Android V1.4(20) | 1 | Connection status is hidden in the hamburger menu and user have no idea if the messaging is working or not without seeing the connection status. Must always show top of screen. Please refer to latest wireframes/VI. This will be updated. | [5 empty] | 100% |  |  | 2018-03-30 |  | 5/31/2018 IOS V1.2 (1231) 7/9/2018 Andriod V2.2 | Closed | Closed | Yes |  | Yes | Temporary release in Feb
261 | General | 2018-03-02 | 2018-05-31 | 65 | Marjon | iOS V1.1(20), Android V1.4(20) | 2 | Radio channel and code info need to show to user. Wireframes and VI will be updated. Please refer to latest wireframes/VI. | [5 empty] | 100% |  |  | 2018-03-30 |  | 5/31/2018 IOS V1.2 (1231) 7/8/2018 Andriod V2.2 | Closed | Closed | Yes |  | Yes | Temporary release in Feb
262 | Bluetooth Connection | 2018-03-02 | 2018-05-31 | 65 | Marjon | iOS V1.1(20) | 1 | Radio information: Status- Connected. (sometimes it shows connected but I can not operate some functions to verify that (e.g. try changing channel won't work so only after unpair and pair it is successful again. | [5 empty] | 100% |  | Radio issue |  |  | 5/31/2018 IOS V1.2 (1231) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
263 | Bluetooth Connection | 2018-03-02 | 2018-07-09 | 92 | Marjon | Android V1.4(20) | 1 | Message never went through even though it showed delivered in the UI. Connection with radio is not stable and it's constantly disconnected with the radio and cannot easily monitor the connection status on message view. | [5 empty] | 80% |  |  | 2018-03-30 |  | 7/9/2018 Andriod V2.2 | N/A | Closed | Yes |  | Yes | Temporary release in Feb
264 | Chat | 2018-03-02 | 2018-07-09 | 92 | Marjon | iOS V1.1(20), Android V1.4(20) | 1 | Messaging didn't work between iOS and Android. Motorola Z phone (Android 7.1.1). and iphone 7. IOS 11.2.6. | [5 empty] | 100% |  | Radio issue |  |  | 7/9/2018 Andriod V2.2 | Closed | Closed | Yes |  | Yes | Temporary release in Feb
265 | Maps | 2018-03-02 | 2018-05-31 | 65 | Marjon | iOS V1.1(20), Android V1.4(20) | 1 | Add this feature: user click on the people icon, date and time of GPS location was captured will be shown . | [5 empty] | 100% |  |  | 2018-04-14 |  | 5/31/2018 IOS V1.2 (1231) 7/9/2018 Andriod V2.2 | Closed | Closed | Yes |  | Yes | Temporary release in Feb
266 | My Members | 2018-03-02 | 2018-07-08 | 91 | Marjon | iOS V1.1(20), Android V1.4(20) | 2 | When you add a contact from phone contacts, it does not consider the phone number format. In my case I already have +1 and it just adds it. Some phone numbers have '(678)' and some have - in between numbers. | [5 empty] | 100% |  |  | 2018-03-23 |  | IOS V1.2 (1237) 7/8/2018 Andriod V2.2 | Closed | Closed | Yes |  | Yes | Temporary release in Feb | [7 empty] | Demand has been raised, but the actual landline phone number does not have a "--" display | > Sev 3
267 | My Members | 2018-03-02 | 2018-05-31 | 65 | Marjon | iOS V1.1(20), Android V1.4(20) | 2 | Adding contacts flow: In current implementation, no matter where you start the adding new contact flow, it always ends at the 'My member screen' and seeing a list our your contacts. If user starts the adding contact flow in the message tab, after he finishes the adding flow, he needs to find the newly added contact in the contact list first to confirm the adding is complete, then have to back out of 'my member' view to go back to where he origiN/Ally at. If we are going to eN/Able user adding contact from different places, then the flow should always end at where user started. That's why I listed 2 flow for the adding new contact: Message view -> user taps on add contact -> add contact screen ->the new contact's contact card (contact detail) ->user taps back to go back to message view My member view ->user taps on add contact -> add contact screen -> the new contact's contact card (contact detail) -> user taps back to go back to my member view | [5 empty] | 100% |  |  | 2018-03-23 |  | 5/31/2018 IOS V1.2 (1231) 7/8/2018 Andriod V2.2 | Closed | Closed | Yes |  | Yes | Temporary release in Feb
268 | My Members | 2018-03-02 | 2018-06-06 | 69 | Marjon | iOS V1.1(20), Android V1.4(20) | 2 | You shouldn't be able to create yourself twice with the same N/Ame which you are now able to do in the app. IOS V1.2 (1231) Fixed But the pop up message I is missing: "ID is invalid" | [5 empty] | 100% |  |  | 2018-03-23 |  | 6/6/2018 IOS V1.2 (1234) 7/9/2018 Andriod V2.3 | Closed | Closed | Yes |  | Yes | Temporary release in Feb | [7 empty] | Results will be seen in the latest software version
269 | Myself | 2018-03-02 | 2018-06-27 | 84 | Marjon | iOS V1.1(20), Android V1.4(20) | 3 | The contact card still showing ‘MYSELF’ in the title and ‘Change your N/Ame’ should be change contact’s N/Ame or similar. if feasible have Myself be updated to the real N/Ame of the person. Change to 'Change your profile N/Ame'. Please refer to latest wireframes/VI. |  |  |  |  | N | 100% |  |  | 2018-03-23 |  | 27/6/2018 IOS V1.2 (1242) 7/8/2018 Andriod V2.2 | Closed | Closed | Yes |  | Yes | Temporary release in Feb | [7 empty] | This is what is shown above the document | no need change for this release
270 | Maps | 2018-03-02 | 2018-05-31 | 65 | Marjon | iOS V1.1(20), Android V1.4(20) | 2 | When there is no network, the mapview will be blank. Add pop up message method to inform user that no network/location sharing/gps disabled. Wireframes/VI will be updated. Please refer to latest wireframes/VI. | [5 empty] | 100% |  |  | 2018-03-23 |  | 5/31/2018 IOS V1.2 (1231) 7/8/2018 Andriod V2.2 | Closed | Closed | Yes |  | Yes | Temporary release in Feb
271 | My Members | 2018-03-02 | 2018-07-08 | 91 | Marjon | iOS V1.1(20), Android V1.4(20) | 2 | Need to coordiN/Ate the page scrolling with keyboard up. When typing the N/Ame the keyboard is covering half of the input field. See photo: https://compass.motorolasolutions.com/cgi/doc/534893275/Keyboard_covering_half_of_the_input_field.JPG | [5 empty] | 100% |  |  | 2018-03-23 |  | IOS V1.2 (1235) 7/8/2018 Andriod V2.2 | Closed | Closed | Yes |  | Yes | Temporary release in Feb | [7 empty] | 1 The effect will be seen in the latest version 2 Please send the picture together with the document next time
272 | Radio Settings | 2018-03-02 | 2018-07-08 | 91 | Marjon | Android V1.4(20) | 3 | Scrubber and +/- shall works for radio settings. It is now work in iOS. Need correction in Android. | [5 empty] | 100% |  |  | 2018-03-23 |  | 7/8/2018 Andriod V2.2 | N/A | Closed | Yes |  | Yes | Temporary release in Feb
273 | On boarding | 2018-03-03 | 2018-05-31 | 64 | Marjon | iOS V1.1(20), Android V1.4(20) | 2 | Remove 'Skip Radio Pairing'. The key is that once you paired once to a radio during set up, you don't have to keep pairing the radio to an app in order to use the app. After first set up, the user should be able to use the app (e.g. to download a new map before a trip without having to use the radio. If that is the case, we can remove after first set up. If not, we need to add option "use app without radio pairing" after initial set up. | [5 empty] | 100% |  |  | 2018-03-23 |  | 5/31/2018 IOS V1.2 (1231) 7/8/2018 Andriod V2.2 | Closed | Closed | Yes |  | Yes | Temporary release in Feb
274 | Chat | 2018-03-03 | 2018-05-31 | 64 | Marjon | iOS V1.1(20), Android V1.4(20) | 3 | Pre Redefined is incorrect, should be Predefined messages | [5 empty] | 100% |  |  | 2018-03-23 |  | 5/31/2018 IOS V1.2 (1231) 7/8/2018 Andriod V2.2 | Closed | Closed | Yes |  | Yes | Temporary release in Feb
275 | Validation Code | 2018-03-03 | 2018-05-27 | 60 | Lee Sun | iOS V1.1(20) | 1 | At the Validation Code page, I did not received SMS for the CODE. When I touch the CODE, a pop up message shown "InvalidParameterException - Missing required parameter SMS_MFA_CODE" | [5 empty] | 1% |  |  | 2018-03-23 |  | 5/27/2018 IOS V1.2 (1227) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
276 | Chat | 2018-03-03 | 2018-05-15 | 52 | LS | iOS V1.1(20) | 3 | The Chat Bubble size is inconsistent. With the same number of text, the Chat bubbles length are different. It appears like mistake. |  |  |  |  | N | 100% |  |  | 2018-03-23 |  |  | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | - | [5 empty] | Did not see this problem, please write the reproducing step | LS will review
277 | Radio Settings | 2018-03-04 | 2018-05-15 | 52 | SK | iOS V1.1(20) | 3 | after setting in Hamburger Menu, click back button, should back to Chat Menu in IOS (diff to Andriod). IOS will just back to Drop down Menu. | [5 empty] | 100% |  | Not an issue. iOS is done correctly per wireframes. Shall back to hamburger menu |  |  |  | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
278 | Chat Menu | 2018-03-04 | 2018-06-06 | 68 | SK | iOS V1.1(20) | 2 | in Shout, top right is Menu with 3 dot, not follow VI design, the icon should a dustbin. | [5 empty] | 100% |  |  | 2018-03-23 |  | 6/6/2018 IOS V1.2 (1234) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | - | [5 empty] | The results will be seen in the latest software version
279 | Maps | 2018-03-04 | 2018-05-31 | 64 | SK | iOS V1.1(20), Android V1.4(20) | 1 | in a very weak GPS sigN/Al, where i cannot view the map when i enter to MAPS (without internet connection). in this location, i try to send a Waypoint. it successfull sent. Then i try to open to view the Map in receiver Phone, it is nothing. THEN I TRY TO CONNECT AN INTERNET (WIFI/DATA), it can view the MAP sent, but, is not from the Location sent. | [5 empty] | 100% |  |  | 2018-03-23 |  | 5/31/2018 IOS V1.2 (1231) 7/9/2018 Andriod V2.2 | Closed | Closed | Yes |  | Yes | Temporary release in Feb
280 | Chat | 2018-03-04 | 2018-05-15 | 52 | SK | iOS V1.1(20), Android V1.4(20) | 3 | >Chat > Add New member > Using phone number: (it's different between IOS and Andriod) IOS showing in +60 Andriod showing in +1 Please set default country to +1 | Y |  | N |  |  | 100% |  |  | 2018-03-23 |  | IOS V1.2 (1235) | Closed | Closed | Yes |  | Yes | Temporary release in Feb |  | IOS is follow phone region setting Now Andriod follow Phone Language (to be defind) 24 Jul, CS: 已经解释过很多次，安卓和苹果本来就不一样，安卓的做法是语言和国家在一起切换，苹果是分开切换的。 24 JUl, CS: You can consider to use either of these API to address the issue: locale OR TelephonyMaN/Ager. Please refer to https://stackoverflow.com/questions/11293642/how-can-i-get-my-android-device-country-code-without-using-gps 31 Jul, XY: User should select the correct language and then followed by Country , then Country code will be able to be reflected correctly. | [5 empty] | The display of Country Code is selected according to the language and region in the common Settings of mobile phones | OK, follow phone setting
281 | Chat | 2018-03-05 | 2018-05-31 | 64 | SK | iOS V1.1(20) | 1 | In Group Info cannot do Member Request as in Document "TALKABOUT_APP_VI_Design_20180201" in page 32 | [5 empty] | 100% |  |  | 2018-03-23 |  | 5/31/2018 IOS V1.2 (1231) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
282 | Chat | 2018-03-05 | 2018-07-08 | 90 | SK | Android V1.4(20) | 2 | Cannot select the Group Chat added in "MY MEMBER" | [5 empty] | 100% |  |  | 2018-03-23 |  | 7/8/2018 Andriod V2.2 | N/A | Closed | Yes |  | Yes | Temporary release in Feb
283 | Hamburger Menu | 2018-03-05 | 2018-07-08 | 90 | Carmen | Android V1.4(20) | 2 | While on the hamburger menu, let say "radio settings" is selected, once "back" is pressed from the UI, should the UI stays at the hamburger menu? The current behaviour is the UI jump to the chat screen. | [5 empty] | 100% |  |  | 2018-03-23 |  | 7/8/2018 Andriod V2.2 | N/A | Closed | Yes |  | Yes | Temporary release in Feb
284 | Group Chat | 2018-03-05 | 2018-07-08 | 90 | Carmen | Android V1.4(20) | 2 | On group chat, I am not able to press on the "Group Icon" to view the particular group's detail i.e. member N/Ame/ID | [5 empty] | 100% |  |  | 2018-03-23 |  | 7/8/2018 Andriod V2.2 | N/A | Closed | Yes |  | Yes | Temporary release in Feb
285 | Chat | 2018-03-08 | 2018-07-09 | 88 | SK | Android V1.4(20) | 1 | sometimes send or received message chat will force to close app | [5 empty] | 20% |  |  |  |  | 7/9/2018 Andriod V2.2 | N/A | Closed | Yes |  | Yes | Temporary release in Feb
286 | Chat/ MAP | 2018-03-08 | 2018-07-08 | 87 | SK | Android V1.4(20) | 2 | In Chat, cannot click to OffLine Maps | [5 empty] | 100% |  |  |  |  | 7/8/2018 Andriod V2.2 | N/A | Closed | Yes |  | Yes | Temporary release in Feb
287 | Maps | 2018-03-08 | 2018-07-08 | 87 | SK | Android V1.4(20) | 2 | in Hamburger Menu, > My Maps > then cannot click to open "My Waypoints" and Geofence. | [5 empty] | 100% |  |  |  |  | 7/8/2018 Andriod V2.2 | N/A | Closed | Yes |  | Yes | Temporary release in Feb
288 | Maps | 2018-03-08 | 2018-07-08 | 87 | SK | Android V1.4(20) | 2 | In Maps view (satelite), if move to somewhere which not at my current location, the maps will automatically move back to my current location. | [5 empty] | 100% |  |  |  |  | 7/8/2018 Andriod V2.2 | N/A | Closed | Yes |  | Yes | Temporary release in Feb
289 | On Boarding | 2018-04-06 | 2018-05-31 | 40 | Tze Lin | iOS V1.1(20), Android V1.4(20) | 2 | If user leave setup halfway, the 'Terms and Privacy Policy' page does not appear again when user back to APP. The 'Terms and Privacy Policy' page shall appear again until user successfully created an account. | [5 empty] | 100% |  |  |  |  | 5/31/2018 IOS V1.2 (1231) 7/8/2018 Andriod V2.2 | Closed | Closed | Yes |  | Yes | Temporary release in Feb
290 | On Boarding | 2018-04-06 | 2018-05-31 | 40 | Tze Lin | iOS V1.1(20) | 2 | At Terms and Privacy Policy page, user scroll down all the way, then click on the 'I agree....' sentence, then click DECLINE button and back to Welcome page. At Welcome page user click START, the Terms and Privacy Policy page never appear again. It should appear because user did not AGREE to the Terms and Privacy Policy. | [5 empty] | 100% |  |  |  |  | 5/31/2018 IOS V1.2 (1231) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
291 | On Boarding | 2018-04-06 | 2018-05-31 | 40 | Tze Lin | iOS V1.1(20) | 2 | Reminder to turn on location did not pop up in preparation page, but it pop up after we close the app and open again | [5 empty] | 100% |  |  |  |  | 5/31/2018 IOS V1.2 (1231) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
292 | Chat | 2018-05-22 | 2018-05-31 | 8 | FT | iOS V1.2 (1227) | 3 | In chat window, when user choose to send location pin, it shall show Location Pin. But now is showing My Current Location. | [5 empty] | 100% |  |  |  |  | 5/31/2018 IOS V1.2 (1231) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
293 | Maps | 2018-05-22 | 2018-05-31 | 8 | FT | iOS V1.2 (1227) | 2 | When phone is in standby, no notification for geofence request. | [5 empty] | 100% |  |  |  |  | 5/31/2018 IOS V1.2 (1231) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | - | [5 empty] | You didn't turn on the Talkabout notification feature in your phone's Settings | I check all the notification setting are ON.
294 | Chat | 2018-05-22 | 2018-05-31 | 8 | FT | iOS V1.2 (1227) | 3 | After accepted Geofence request, in chat window the 'Geofence has been set' appears twice. | [5 empty] | 100% |  |  |  |  | 5/31/2018 IOS V1.2 (1231) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
295 | Chat | 2018-05-22 | 2018-05-31 | 8 | FT | iOS V1.2 (1227) | 2 | After member accepted Geofence request, the requestor side shall receive message of 'Geofence has been set'. but now is receive Geofence request which is wrong. | [5 empty] | 100% |  |  |  |  | 5/31/2018 IOS V1.2 (1231) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
296 | Maps | 2018-05-23 | 2018-06-06 | 11 | FT | iOS V1.2 (1227) | 2 | Press target button in map, the location of member is not updated. The timestamp still show previous timing. | [5 empty] | 100% |  |  |  |  | 6/6/2018 IOS V1.2 (1234) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | - | [5 empty] | It has been revised in the latest version
297 | Bluetooth Connection | 2018-05-23 | 2018-05-31 | 7 | FT | iOS V1.2 (1227) | 1 | After connected, bluetooth connection sometimeswill become not working. Not sure how to duplicate it. Press test button in' Bluetooth Connection' and radio side has no response, this shows that bluetooth connection is fake (even though radio BT icon is show connected status). To solve this, I have to kill the app then reconnect again. | [5 empty] | 50% |  |  |  |  | 5/31/2018 IOS V1.2 (1231) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
298 | Chat | 2018-05-25 | 2018-06-06 | 9 | SK | iOS V1.2 (1227) | 2 | App ICON no message notification in iPhone 5 (Version 10.3.3), but in app Chat has. | Y |  |  |  |  | 100% |  |  |  |  | 6/6/2018 IOS V1.2 (1234) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | - | [5 empty] | You didn't turn on the Talkabout notification feature in your phone's Settings
299 | Chat | 2018-05-25 | 2018-05-31 | 5 | SK | iOS V1.2 (1227) | 2 | App in Iphone 5 sent Shout message to Iphone 6. Iphone 6 received the message, but Iphone 5 showing to retry, then press "Retry", message received again in iphone 6, but still showing to retry in iphone 5. | [5 empty] | 40% |  |  |  |  | 5/31/2018 IOS V1.2 (1231) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | -
300 | Radio Settings | 2018-05-25 | 2018-06-06 | 9 | SK | iOS V1.2 (1227) | 2 | In App Radio Setting to change "Keypad Tone" and "Talk Confirmation Tone", from ON to OFF... changed Success (Radio setting changed correct). Then now continue change it back from OFF to ON... FAIL (in App already ON, but Radio NO action) | [5 empty] | 100% |  |  |  |  | 6/6/2018 IOS V1.2 (1234) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | - | [5 empty] | Did not see this problem, please write the reproducing step
301 | Bluetooth Connection | 2018-05-27 | 2018-06-06 | 8 | SK | iOS V1.2 (1227) | 3 | Bluetooth connection with Radio for a few times (Pair and unpair radio in App for few times) At radio will show TX icon after paired. | [5 empty] | 70% |  |  |  |  | 6/6/2018 IOS V1.2 (1234) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | - | [5 empty] | Did not see this problem, please write the reproducing step
302 | Radio Settings | 2018-05-28 | 2018-08-10 | 55 | SK | iOS V1.2 (1227) | 2 | In App Radio Setting change iVOX and VOX level no effect in Radio. | [5 empty] | 100% |  |  |  |  | IOS V1.2 (1236) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | - | [5 empty] | This effect will be seen in the latest software version
303 | Bluetooth Connection | 2018-05-28 | 2018-06-06 | 8 | SK | iOS V1.2 (1228) | 2 | In talkabout_app_srs_r2.0-20180512 [OnBoarding-3-1-15] When the user press "TEST” button, the Bluetooth icon on the radio also will blink twice in 100% brightness and sound ‘pairing successful’ tone. Issue: But in actual now in radio the Bluetooth icon did NOT WORK to blink twice in 100% brightness | [5 empty] | 100% |  |  |  |  | 6/6/2018 IOS V1.2 (1234) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | - | [5 empty] | This is a radio problem
304 | Radio Settings | 2018-05-30 | 2018-06-06 | 6 | SK | iOS V1.2 (1230) | 3 | Emergency setting in Radio Setting, there is an typo wording: channl/code -> channel/code Also "The message is limited to 73 characters." not 90 anymore. | [5 empty] | 100% |  |  |  |  | 6/6/2018 IOS V1.2 (1234) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | - | [5 empty] | This effect will be seen in the latest software version
305 | Radio Settings | 2018-05-30 | 2018-06-06 | 6 | SK | iOS V1.2 (1230) | 2 | Emergency message after user click on SAVE, Saved success. Then now user clicked to clear the message, message is cleared. (from the display) BUT in actual it is not cleared. after clear to return to main Chat mode, then go in again to Emergency message, it is showing the message created before cleared. | [5 empty] | 100% |  |  |  |  | 6/6/2018 IOS V1.2 (1234) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | - | [5 empty] | This effect will be seen in the latest software version
306 | Radio Settings | 2018-05-30 | 2018-08-10 | 53 | SK | iOS V1.2 (1231) | 3 | Easy Pairing Error message pop up after paired success | [5 empty] | 100% |  |  |  |  | IOS V1.2 (1236) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | - | [5 empty] | The current APP version does not have this problem | let me reduplicate and share the video.
307 | Bluetooth Connection | 2018-05-30 | 2018-08-10 | 53 | SK | iOS V1.2 (1231) | 3 | in Bluetooth connection page > check connection > "The bluetooth icon on the radio will turn solid for 2 seconds." it should "The Bluetooth icon on the radio also will blink twice in 100% brightness and sound ‘pairing successful’ tone." | [5 empty] | 100% |  |  |  |  | IOS V1.2 (1237) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | - | [5 empty] | This is a radio problem |  | same
308 | Maps | 2018-05-31 | 2018-08-10 | 52 | SK | iOS V1.2 (1231), Android | 3 | Before purchase the Dark and Light Maps view. I can see the Dark and Light selection in Download Offline Map (Selection Maps Styles) | N |  |  |  | N | 100% | [5 empty] | N/A | N/A | No |  |  |  |  | Pending verification for release version now is Beta version where user can view the DARK n LIGHT Map view. 26 Jul, XY: solution will be available by 3 Aug |  |  | 1 |  |  | This issue has been updated in the latest version of the APP
309 | Chat | 2018-05-31 | 2018-08-10 | 52 | SK | iOS V1.2 (1231) | 1 | i am doing checking for the icon color when user in offline condition, then i found: the radio cannot send out message, it do keep asking to RETRY, even both radio already connected and in same freq and code. Also the icon is in Greyed not actual color. | [5 empty] | 100% |  |  |  |  | IOS V1.2 (1236) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | - | [5 empty] | Did not see this problem, please write the reproducing step | let me reduplicate and share the video.
310 | Chat | 2018-05-31 | 2018-07-18 | 35 | SK | iOS V1.2 (1231) | 3 | After add some member in Group, and the N/Ame of the Group is "Family Trip". Then the Leader send a message to members, The receiver (members) received the message, but the Group title show a number, it should show the "Family Trip" as leader had edited. |  |  |  |  | Y | 100% |  |  | Before 6-Jul-18 |  | 18 July 2018 IOS V1.2 (1247) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | - | [5 empty] | This is defined in the document | New Request | New Request | New Request
311 | Maps | 2018-05-31 | 2018-08-10 | 52 | SK | iOS V1.2 (1231) | 3 | Iphone 5 Display abnormal when i click into Maps page. http://compass.mot-solutions.com/doc/539586918/Abnormal_display_in_Maps_view.PNG | [5 empty] | 100% |  |  |  |  | IOS V1.2 (1237) | Closed | N/A | Yes |  | Yes | Temporary release in Feb |  | - | [5 empty] | 1 Did not see this problem, please write the reproducing step 2 Please send the picture together with the document next time | IOS10
312 | Maps | 2018-06-01 | 2018-08-10 | 51 | SK | iOS V1.2 (1231) | 1 | Geofence alert message always promnt out even i Disable the Geofence. | [5 empty] | 100% |  |  |  |  | IOS V1.2 (1236) | Closed | N/A | Yes |  | No | Duplicate to Auctus | duplicate 213 | - | [5 empty] | This issue has been updated in the latest version of the APP | OK
313 | Chat | 2018-06-01 | 2018-07-19 | 35 | SK | iOS V1.2 (1231) | 3 | Transmittor to TX Emergency Message by long press on Emergency button on Radio. Receiver RX the message, but i cannot see in Transmittor's App has sent out the message in Shout. |  |  |  |  | Y | 100% |  |  |  |  | 19 July 2018 IOS V1.2 (1247) | Closed | N/A | Yes |  | Yes | Escape to MSI |  | 6/6/2018 Still same in IOS V1.2 (1234) Sev 2 > 3 Still same in 1240 Still same in 1243 18 jul, XY: app side finished 1.2 47 ,also need update radio software(new feature ) | [5 empty] | This is defined in the document | Sender App should also display the sending Emergency message. | New request might not fix at Beta version. still same in (1236) | New request might not fix at Beta version. still same in (1236)
314 | radio Settings | 2018-06-01 | 2018-08-10 | 51 | SK | iOS V1.2 (1231) | 2 | Easy pairing via App Member eN/Able and ready to be pair (starting cowndown 3 mins) Leader eN/Able to start pairing, BUT Leader sometimes need to press a few time to pair success. | [5 empty] | 80% |  |  |  |  | IOS V1.2 (1236) | Closed | N/A | Yes |  | Yes | Escape to MSI |  | - | [5 empty] | This is a radio problem | Pending New Radio
315 | Radio Settings | 2018-06-01 | 2018-08-10 | 51 | SK | iOS V1.2 (1231) | 3 | sometimes first change/ switch Channel or Call tone from App, Radio site did not perform the beep/ call tone. | [5 empty] | 50% |  |  |  |  | IOS V1.2 (1236) | Closed | N/A | Yes |  | Yes | Escape to MSI |  | - | [5 empty] | This is a radio problem | Pending New Radio
316 | MAPS | 2018-06-05 | 2018-08-10 | 49 | LiN/Ar | iOS V1.2 (1233) | 3 | Maps view in Satellite style, it will black out once zoom in. (Only PeN/Ang island) | N |  |  |  | Y | 100% | [5 empty] | Pending verification | Pending verification | Yes |  | No | Not defect |  | Suspect Maps Issue 18 jul, XY: not app issue 24 Jul, CS: XiongTao, please advise on the action plan 25 Jul, CS: submitted issue report to Mapbox to fix the map missing problem under satelite view. |  |  | 1 |  |  |  | let me reduplicate and share the video. | (Only PeN/Ang island) | (Only PeN/Ang island)
317 | Emergency Shout | 2018-06-06 | 2018-08-10 | 48 | SK | iOS V1.2 (1234) | 2 | Radio Setting > Emergency > to Edit emergency message, the message is: "Iphone6, +6011-6296 4209 Please come to the river" 1. radio A Trigger Emergency on Radio. 2. recipent App B receive an emergency message in Shout. > message received not complete: "Iphone6, +6011-6296 4209" | [5 empty] | 100% |  |  |  |  | IOS V1.2 (1236) | Closed | N/A | Yes |  | Yes | Escape to MSI |  | -
318 | Chat | 2018-06-06 | 2018-08-10 | 48 | SK | iOS V1.2 (1234) | 2 | Sending Message in shout sometimes asked for retry with no reason, but the receiver has received the message actually. this happen even i wait App/ radio in IDLE for 1 mins then sent again the message. | [5 empty] | 40% |  |  |  |  | IOS V1.2 (1236) | Closed | N/A | Yes |  | Yes | Escape to MSI |  | - | [6 empty] | let me reduplicate and share the video.
319 | MAPS | 2018-06-14 |  | -30904 | SK | iOS V1.2 (1236) | 3 | When radio is disconnected, the 'radio dissconnected' bar notification shall also show in map view. now it is only show in chat view. | N | Enh_PostD1 | N |  | Y | 100% | [5 empty] | Open | Open | Yes |  |  |  |  | Still same in 1240 Still same in 1243 18 jul, XY: new feature ,will not support 26 Jul, Marjon: park under future enh (<3 mths) | [7 empty] | new request | new request
320 | MAPS | 2018-06-14 | 2018-08-10 | 42 | SK | iOS V1.2 (1236) | 2 | When you download a map and choose a different layer it does not download the layer but only downloads the street view. | [5 empty] | 100% |  |  |  |  | IOS V1.2 (1237) | Closed | N/A | Yes |  | Yes | Escape to MSI |  | -
321 | Hamburger Menu | 2018-06-14 | 2018-08-10 | 42 | SK | iOS V1.2 (1236), Android | 3 | in FAQ the icons are not added in but instead shows my text e.g. (show icon of hamburger menu) | Y |  | N | Y |  | Open | Open |  |  |  | IOS V1.2 (1238) | Closed | Closed | Yes |  | Yes | Escape to MSI |  | 24 Jul, CS: this was not fixed properly. Hence this issue is re-opened. | 2018-08-03
322 | MAPS | 2018-06-14 | 2018-08-10 | 42 | SK | iOS V1.2 (1236) | 1 | Iphone 6 (IOS 11.2.1)eN/Abled Track recording, all details not activate. Iphone 8 (IOS 11.3.1) OK. | [5 empty] | 100% |  |  |  |  | IOS V1.2 (1238) | Closed | N/A | Yes |  | Yes | Escape to MSI |  | - | [7 empty] | Supplier site cannot duplicate, and only happen in iphone6. future verification will be enhance. | Supplier site cannot duplicate, and only happen in iphone6. future verification will be enhance.
323 | MAPS | 2018-06-14 | 2018-06-29 | 12 | SK | iOS V1.2 (1236) | 3 | in My Maps > Offline Map > to download Offline Map? Now i see App is keep loading no indication message to alert user to turn ON network and Location service |  |  |  |  | N | 100% |  |  |  |  | 6/29/2018 IOS V1.2 (1243) | Closed | N/A | Yes |  | Yes | Enhancement |  | - | [7 empty] | new request | new request
324 | Track | 2018-06-15 | 2018-06-25 | 7 | Marjon | iOS V1.2 (1234) | 2 | When you select show track on map, should go to your offline map and show. Right now it does not, only if you are on the network or a the actual location. |  |  |  |  | Y | 100% |  |  |  |  | 25/6/2018 IOS V1.2 (1240) | Closed | N/A | Yes |  | Yes | Escape to MSI |  | - | [8 empty] | new request | discussion needed
325 | Radio Settings | 2018-06-15 | 2018-08-10 | 41 | SK | iOS V1.2 (1236) | 3 | every setting in Radio must take reflect directly in APP | [5 empty] | 100% |  |  |  |  | IOS V1.2 (1238) | Closed | N/A | Yes |  | Yes | Enhancement |  | - | [7 empty] | new request | new request
326 | Chat | 2018-06-15 | 2018-08-10 | 41 | SK | iOS V1.2 (1237) | 3 | Chat->Add new member--> it is hard to select a different country code member, not convinient |  |  |  |  | Y | 100% | [5 empty] | Closed | N/A | Yes |  | Yes | Enhancement |  | Now followed Alphabet. | [7 empty] | new request | new request
327 | Maps | 2018-06-15 | 2018-08-10 | 41 | FT | iOS V1.2 (1237) | 2 | When I am not connect APP to radio, press the locate button in map, it shows 'Location has been sent' which is wrong info to user. There is no location been sent when radio not connected. | [5 empty] | 100% |  |  |  |  | IOS V1.2 (1238) | Closed | N/A | Yes |  | Yes | Escape to MSI |  | - | [8 empty] | new request
328 | Maps | 2018-06-15 | 2018-08-10 | 41 | FT | iOS V1.2 (1237) | 2 | When I click locate button in map, my location is sent to others and suppose I will get auto response from other with their gps location info. Is this implemented? | [5 empty] | 100% |  |  |  |  | IOS V1.2 (1237) | Closed | N/A | Yes |  | Yes | Enhancement |  | -
329 | Maps | 2018-06-15 | 2018-08-10 | 41 | FT | iOS V1.2 (1237) | 2 | Press easy pairing button to send location, this need to follow 30s rule. Is this implemented? | [5 empty] | 100% |  |  |  |  | IOS V1.2 (1237) | Closed | N/A | Yes |  | Yes | Enhancement |  | -
330 | Radio Settings | 2018-06-15 | 2018-08-10 | 41 | FT | iOS V1.2 (1237) | 3 | I think when radio is disconnected, the battery info, radio model, sw info (in BLUETOOTH CONNECTION), battery icon,and channel info(in hamburger menu) shall not shown. | [5 empty] | 100% |  |  |  |  | IOS V1.2 (1238) | Closed | N/A | Yes |  | Yes | Enhancement |  | - | [7 empty] | new request | new request
331 | Setting | 2018-06-15 | 2018-08-10 | 41 | FT | iOS V1.2 (1237) | 3 | My Maps> Purchase Map Types> Typo at Default Map > Sattelite Street correction is "Satellite" | [5 empty] | 100% |  |  |  |  | IOS V1.2 (1238) | Closed | N/A | Yes |  | Yes | Escape to MSI |  | -
332 | Maps | 2018-06-15 | 2018-08-10 | 41 | FT | iOS V1.2 (1237), Android | 2 | Press radio easy pairing button OR press locate button(in map view) to send location shall follow the FCC 30s rule. Right now it is not implemented. | [5 empty] | 100% |  |  |  |  | IOS V1.2 (1238) Andriod V2.3 | Closed | Closed | Yes |  | Yes | Enhancement |  | need to update to not send in queue if pressed many times within 30s FCC rule. | [7 empty] | discussion needed | discussion needed | need to update to not send in queue if pressed many times within 30s FCC rule.
333 | Maps | 2018-06-15 | 2018-08-10 | 41 | FT | iOS V1.2 (1237) | 3 | In Map, to save a TRACK. start to save track, at the bottom of the MAP will show "RESUME", "STOP". where the "RESUME" was wrong, it should show as "PAUSE" due to the Track already in recording. |  |  |  |  | N | 100% |  |  |  |  | IOS V1.2 (1239) | Closed | N/A | Yes |  | Yes | Escape to MSI |  | - | [7 empty] | discussion needed |  | NEW issue found
334 | Maps | 2018-06-19 | 2018-08-10 | 39 | SK | iOS V1.2 (1238) | 3 | My Maps > Geofence > setting of "EN/Able notification" and "Sound" shall set to EN/ABLE by default. |  |  |  |  | Y | 100% |  |  |  |  | IOS V1.2 (1239) | Closed | N/A | Yes |  | Yes | Enhancement |  | -
335 | Maps | 2018-06-19 | 2018-08-10 | 39 | SK | iOS V1.2 (1238) | 2 | Geofence: When EN/Able Notification is turned ON -> should pop up notification message every 1 min. Right now the condition is not consistent. Sometimes will appear, sometimes it will not no matter notification is turn OFF or ON. When Sound is turned - ON -> Should alert user every 1 min. Right now the condition is not consistent. Sometimes will appear, sometimes it will not no matter sound is turn OFF or ON. |  |  |  |  | Y | 100% | [5 empty] | Closed | N/A | Yes |  | Yes | Escape to MSI |  | FT: requirement not needed anymore. Does not need pop up notification every 1 min. Just pop up notification one time (when user first exit Geofence) is enough unless there is any Beta feedback.
336 | Maps | 2018-06-20 | 2018-06-27 | 6 | FT | iOS V1.2 (1238) | 1 | Geofence out of boundary alert, when user click on OK the alert is actually not sent out. |  |  |  |  | Y | 100% |  |  |  |  | 27/6/2018 IOS V1.2 (1242) | Closed | N/A | Yes |  | Yes | Escape to MSI |  | - 25 Jun, CS: Resolved
337 | Maps | 2018-06-20 | 2018-06-27 | 6 | FT | iOS V1.2 (1238) | 2 | Press to Locate the location in map/ press easy pairing button to locate a location: -> Receiver can see the time stamp updated, but the transmitter did not see the reply update from receiver side. concept is the receiver should have a reply back once received a update locate from others. |  |  |  |  | Y | 100% |  |  |  |  | 27/6/2018 IOS V1.2 (1242) | Closed | N/A | Yes |  | Yes | Enhancement
338 | Maps | 2018-06-20 | 2018-08-10 | 38 | SK | iOS V1.2 (1238) | 3 | After saved my track, view the track from My Maps: there is just show the track saved N/Ame... there should also show the number of details captured: km¦min¦km/h¦m |  |  |  |  | Y | 100% | [5 empty] | Closed | N/A | Yes |  | Yes | Escape to MSI |  | Already follow latest VI design.
339 | Maps | 2018-06-20 | 2018-07-04 | 11 | FT | iOS V1.2 (1238) | 3 | This is not issue, this is UI enhancement. When geofence out of boundary alert message pop up, after click OK user does not need to select member. Once user click OK the sender location will send to other members who accepted the geofence request, or send to all other member in same chat group. Please follow TALKABOUT_APP_Wireframes_20180620. |  |  |  |  | Y | 100% |  |  | 2018-06-20 |  | 4/7/2018 IOS V1.2 (1244) | Closed | N/A | Yes |  | Yes | Enhancement |  | UI enhancement.
340 | Maps | 2018-06-20 |  | -30908 | FT | iOS V1.2 (1238) | 3 | This is not issue, this is UI enhancement. When user A is out of boundary, user A APP will pop up alert message and user A click on OK. User A location will then sent to user B and user B APP will have show a pop up message, and show user A updated location in map. Please follow TALKABOUT_APP_Wireframes_20180620. | N | Enh_PostD1 | N |  | Y | 100% | [5 empty] | Open | Open | Yes |  |  |  |  | UI enhancement. 18 jul, XY: new feature ,will not support 26 Jul, Marjon: park under future enh (<3 mths)
341 | Maps | 2018-06-20 |  | -30908 | Marjon | iOS V1.2 (1238) | 3 | In radio setting the scroll ruler need to change. When scroll to min and max value the ruler shall not show. Please follow TALKABOUT_APP_Wireframes_20180620 slide#119 | N | Enh_D1 | N | P | N | 100% | [5 empty] | Duplicated | N/A | Yes |  |  |  |  | Still same in 1240 Still same in 1243 18 jul, XY: new feature ,will not support Duplicated to #120 26 Jul, Marjon: Has to be fixed by D2 27 Aug, FT: same issue as #120 | needs 2 weeks after cost is locked down
342 | Radio Settings | 2018-06-20 | 2018-07-04 | 11 | Marjon | iOS V1.2 (1238), Android | 3 | This is not issue, this is UI enhancement: After set emergency message and click SAVE, the pop up message shall shows 'message saved' and OK. OrigiN/Ally was 'message saved' and DISMISS. |  |  |  |  | N | 100% |  |  |  |  | 4/7/2018 IOS V1.2 (1244) | Closed | Closed | Yes |  | Yes | Enhancement |  | UI enhancement. 24 Jul, XY: iOS1248以前就解决了，安卓2.5 已经解决
343 | Chat | 2018-06-20 |  | -30908 | Marjon | iOS V1.2 (1238) | 3 | This is not issue, this is UI enhancement: When you are in the map you don't get new message notification. Only shown if out of app or in the chat window | N | Enh_PostD1 | N |  | N | 100% | [5 empty] | Open | Open | Yes |  |  |  |  | UI enhancement. 18 jul, XY: new feature ,will not support 26 Jul, Marjon: park under future enh (<3 mths)
344 | Maps | 2018-06-20 | 2018-06-22 | 3 | Marjon | iOS V1.2 (1238) | 3 | When you select show track on map, should go to your offline map and show. Right now it does not, only if you are on the network or a the actual location. The track shall displayed on map after user click 'SHOW ON MAP'. If user selected multiple tracks at multile location to show on map, the track closest to user location shall show. |  |  |  |  | Y | 100% |  |  |  |  | 6/22/2018 IOS V1.2 (1240) | Closed | N/A | Yes |  | Yes | Enhancement
345 | Hamburger Menu | 2018-06-20 |  | -30908 | Marjon | iOS V1.2 (1238) | 3 | File N/Ame cannot be seen in full. Please change to 2 rows. | N | Enh_D1 | N | P | Y | 100% | [5 empty] | Closed | Closed | Yes |  |  |  |  | Still same in 1240 Still same in 1243 18 jul, XY: new feature ,will not support 24 Jul, FT: the file N/Ame cannot seen in full and we only request to change to 2 lines. This is solving issue to eN/Able user can see the file N/Ame. 26 Jul, CS: Denied and come back that this is Enh | needs 1 week after cost is locked down |  |  |  | android 0.25 week , iOS 0.25week, test 0.25week, document 0.05week
346 | Maps | 2018-06-21 | 2018-06-25 | 3 | SK | iOS V1.2 (1238) | 2 | Accepted a new Geofence request should replace the previous Geofence. Now if i accept new Geofence request where i already activated one.. it still showing the old one which is wrong.. the Geofence need to update to latest accepted. |  |  |  |  | Y | 100% |  |  |  |  | 25/6/2018 IOS V1.2 (1240) | Closed | N/A | Yes |  | Yes | Escape to MSI
347 | Maps | 2018-06-21 | 2018-07-04 | 10 | FT | iOS V1.2 (1239) | 3 | This is not issue, this is UI enhancement: Out of boundary geofence message content change to 'You are now leaving the Geofence boundary. Do you want to send your current location to the others?' Please refer to TALKABOUT_APP_Wireframes_20180621 sdlie#84 |  |  |  |  | Y | 100% |  |  |  |  | 4/7/2018 IOS V1.2 (1244) | Closed | N/A | Yes |  | Yes | Enhancement |  | UI enhancement Implemented in V1.2 (1242) but with typo. End of the sentence shall be '?' --> fixed in 1243
348 | Hamburger Menu | 2018-06-21 | 2018-06-27 | 5 | SK | iOS V1.2 (1239) | 3 | Geofence in activated. Now i going to KILL the App and OFF the radio. (Bluetooth disconnected) I move out from Geofence area, then open the APP and connect to the Radio. i do not be alert that i am out of Geofence area. |  |  |  |  | Y | 100% |  |  |  |  | 27/6/2018 IOS V1.2 (1242) | Closed | N/A | Yes |  | Yes | Escape to MSI
349 | Maps | 2018-06-21 | 2018-06-27 | 5 | SK | iOS V1.2 (1239) | 2 | Tested in actual case in talk able range: Geofence out of boundary alert appeared, pressed OK, but not get notification and location pin at member side. (tested also in side by side, Location pin received, but no notification to alert member is out of boundary) |  |  |  |  | Y | 50% |  |  |  |  | 27/6/2018 IOS V1.2 (1242) | Closed | N/A | Yes |  | Yes | Escape to MSI
350 | Hamburger Menu | 2018-06-21 | 2018-06-22 | 2 | FT | iOS V1.2 (1239) | 3 | On iphone 5 back arrow interferes with Motorola Contact Info. |  |  |  |  | N | 100% |  |  |  |  | 6/22/2018 IOS V1.2 (1240) | Closed | N/A | Yes |  | Yes | Escape to MSI
351 | Maps | 2018-06-21 | 2018-07-18 | 20 | SK | iOS V1.2 (1239), Android | 2 | User A send a location pin(which is away from user A location) to user B, when user B click to open the location pin, location pin will show on map together with user A icon next it. This is not correct because that is not user A real location. User B has to click on Locate button once then only able to get user A actual location. |  |  |  |  | Y | 100% |  |  | Before 6-Jul-18 |  | 18 July 2018 IOS V1.2 (1247) 24 July 2018 Andriod V2.4 | Closed | Closed | Yes |  | Yes | Enhancement |  | 18 Jul, CS: finished 1.2 47 (new feature )
352 | Chat | 2018-06-25 | 2018-06-27 | 3 | SK | iOS V1.2 (1240) | 3 | received an Emergency Message in SHOUT, the old message will replaced by latest, which this was wrong, where old message shall stay. |  |  |  |  | Y | 100% |  |  |  |  | 27/6/2018 IOS V1.2 (1242) | Closed | N/A | Yes |  | Yes | Escape to MSI
353 | Chat | 2018-06-25 | 2018-06-27 | 3 | SK | iOS V1.2 (1240) | 3 | In Chat page, enter Hamberger Menu, select My Maps select My Track, at this moment just click "<" back button, the page will direct go to MAPS. which this was wrong, it should back to "MY MAPS" Menu. |  |  |  |  | N | 100% |  |  |  |  | 27/6/2018 IOS V1.2 (1242) | Closed | N/A | Yes |  | Yes | Escape to MSI
354 | Chat | 2018-06-25 | 2018-06-27 | 3 | FT | iOS V1.2 (1240) | 3 | After I sent offline map, the offline map will show sent(a tick is shown). I exit from chat then enter again, the offline map will have a timer icon on it(pending to send status). |  |  |  |  | N | 100% |  |  |  |  | 27/6/2018 IOS V1.2 (1242) | Closed | N/A | Yes |  | Yes | Escape to MSI
355 | My Track | 2018-06-25 | 2018-06-26 | 2 | FT | iOS V1.2 (1240) | 2 | When user received track from other member, all the statistic become 0. | [5 empty] | 100% |  |  |  |  | 26/6/2018 IOS V1.2 (1241) | Closed | N/A | Yes |  | Yes | Escape to MSI
356 | Chat | 2018-06-26 | 2018-06-27 | 2 | SK | iOS V1.2 (1241) | 1 | "RETRY" issue appear again in IOS V1.2 (1241) |  |  |  |  | N | 100% |  |  |  |  | 27/6/2018 IOS V1.2 (1242) | Closed | N/A | Yes |  | Yes | Escape to MSI
357 | Chat | 2018-06-26 | 2018-06-29 | 4 | SK | iOS V1.2 (1241) | 3 | i am in the Chat, reading message from member A. Member A sent 3 messages to me, while i am reading. i clicked "<" return button to the Chat mode, there still dispalying a unread message as "3". this was wrong where actually i am already read all the messages. |  |  |  |  | Y | 100% |  |  |  |  | 29/6/2018 IOS V1.2 (1243) | Closed | N/A | Yes |  | Yes | Escape to MSI |  | Still same in 1241 Still same in 1242
358 | Chat | 2018-06-26 | 2018-06-27 | 2 | SK | iOS V1.2 (1241) | 2 | delivered Message should not be replace if sender press to RETRY to send again. |  |  |  |  | N | 100% |  |  |  |  | 27/6/2018 IOS V1.2 (1242) | Closed | N/A | Yes |  | Yes | Escape to MSI
359 | Chat | 2018-06-26 | 2018-06-27 | 2 | SK | iOS V1.2 (1241) | 1 | several issue found in sending Maps, please do review in video captured: 1. timer icon keep showing even Maps already downloaded. 2. Maps still can open but Maps not completed download. 3. Sometimes received Maps showing in loading icon. 4. in Chat page to click on received Maps (downloaded complete), cannot open. |  |  |  |  | Y | 100% |  |  |  |  | 27/6/2018 IOS V1.2 (1242) | Closed | N/A | Yes |  | Yes | Escape to MSI
360 | Chat | 2018-06-26 | 2018-06-29 | 4 | FT | iOS V1.2 (1241) | 3 | The chat history will roll every time enter chat window. The chat history will roll every time there is new message come in. | [5 empty] | 100% |  |  |  |  | 29/6/2018 IOS V1.2 (1243) | Closed | N/A | Yes |  | Yes | Escape to MSI |  | Still same in 1242. Auctus mention need time to fix this.
361 | Maps | 2018-06-27 | 2018-06-29 | 3 | FT | iOS V1.2 (1242) | 3 | When I wanted to set Geofence, I cant see my own location. It is disappeared. | [5 empty] | 100% |  |  |  |  | 29/6/2018 IOS V1.2 (1243) | Closed | N/A | Yes |  | Yes | Escape to MSI
362 | Maps | 2018-06-27 | 2018-06-29 | 3 | SK | iOS V1.2 (1242) | 2 | Geofence out of boundary alert, when user click on OK to sent a Location Pin to members. Members received the Location Pin, then click to view, but sender actual Location not update. | [5 empty] | 100% |  |  |  |  | 29/6/2018 IOS V1.2 (1243) | Closed | N/A | Yes |  | Yes | Escape to MSI
363 | Maps | 2018-06-27 | 2018-06-29 | 3 | SK | iOS V1.2 (1242) | 2 | Share a Geofence area to members, my members accept and set in his APP, then when he clicked to view, the Geofence not appear... keep showing in blue page, until he click on the LOCATE button.. | [5 empty] | 100% |  |  |  |  | 29/6/2018 IOS V1.2 (1243) | Closed | N/A | Yes |  | Yes | Escape to MSI
364 | Bluetooth Connection | 2018-06-27 | 2018-07-06 | 8 | FT | iOS V1.2 (1242) | 3 | shall not allow Auto tx once radio reconnect in low batt condition. | [10 empty] | 6/7/2018 IOS V1.2 (1244) | Closed | N/A | Yes |  | Yes | Enhancement
365 | Chat | 2018-06-29 | 2018-06-29 | 1 | SK | iOS V1.2 (1243) | 3 | the message delivered hide behind the typing box.. | [5 empty] | 100% |  |  |  |  | 29/6/2018 IOS V1.2 (1244) | Closed | N/A | Yes |  | Yes | Escape to MSI
366 | Maps | 2018-07-02 | 2018-08-10 | 30 | CS | Android V1.8 | 1 | After saved my track, go to Chat and send my track to app 2, observed that app 1 Stopped and entire app crashed | [5 empty] | 100% | [5 empty] | N/A | Closed | Yes |  | Yes | Escape to MSI
367 | Chat | 2018-07-02 | 2018-07-08 | 5 | CS | Android V1.8 | 2 | Sending basic chat from app 1 to app 2. Observed that app 1 showing RETRY though app 2 has received the message | [5 empty] | 100% |  |  |  |  | 7/8/2018 Andriod V2.2 | N/A | Closed | Yes |  | Yes | Escape to MSI | [13 empty] | intermittent
368 | Maps | 2018-07-02 | 2018-08-10 | 30 | CS | Android V1.8 | 2 | Activate geofence in app1, and share to app2. Observed that geofence request did not send out | [11 empty] | N/A | Closed | Yes |  | Yes | Escape to MSI
369 | Chat | 2018-07-02 | 2018-08-10 | 30 | CS | Android V1.8 | 1 | Intermittently, app1 and app2 will not be able to communicate, failed to send and receive for Chat and Maps features | [5 empty] | 50% | [5 empty] | N/A | Closed | Yes |  | Yes | Escape to MSI | [12 empty] | Same issue in 1.9
370 | Geofence | 2018-07-02 | 2018-07-09 | 6 | CS | Android V1.8 | 2 | Activate geofence and set it to be out of boundary. Observed that there is no alert message pop up | [5 empty] | 100% |  |  |  |  | 7/9/2018 Andriod V2.3 | N/A | Closed | Yes |  | Yes | Escape to MSI |  | 反应慢应该跟gps定位速度有关，可能是天气或者其他遮挡引起。 | [10 empty] | Same issue in 1.9 | Same
371 | Chat | 2018-07-02 | 2018-08-10 | 30 | LS | iOS V1.2 (1243), Android | 3 | The chat bubble corner radius are not perfect round. It is distorted/stretched. | [5 empty] | 100% | [5 empty] | Closed | Closed | Yes |  | Yes | Enhancement |  | LS to review 25 Jul, CS: LeeSun has clarified with Auctus to proceed with fixing.
372 | Maps | 2018-07-02 | 2018-07-08 | 5 | CS | Android V1.8 | 2 | Press location sharing on radio, observed that location time stamp is not updated | [5 empty] | 100% |  |  |  |  | 7/8/2018 Andriod V2.2 | N/A | Closed | Yes |  | Yes | Escape to MSI | [13 empty] | Same
373 | On Boarding | 2018-07-03 | 2018-07-08 | 4 | SK | Android V1.9 | 3 | Country Code not follow alphapet (very hard to find the country code) | [5 empty] | 100% |  |  |  |  | 7/8/2018 Andriod V2.2 | N/A | Closed | Yes |  | Yes | Enhancement
374 | On Boarding | 2018-07-03 | 2018-08-10 | 29 | SK | Android V1.9 | 3 | Country Code not follow the phone setting as IOS (follow the country registered) | [5 empty] | 100% | [5 empty] | N/A | Duplicated | No |  |  |  |  | IOS is follow phone region setting Now Andriod follow Phone Language (to be defind) 24 Jul, CS: Duplicated to issue #280 |  |  | 1
375 | Radio Settings | 2018-07-03 | 2018-07-05 | 3 | SK | Android V1.9 | 1 | Radio Setting not ready: 1. changed Channel in APP, SubCode will auto changed to 255 (where the suncode only max to 121) 2. Change SubCode, the Channel on Radio Display will become abnormal, it showing something like "d5". | [5 empty] | 100% |  |  |  |  | 7/5/2018 Andriod V2.0 | N/A | Closed | Yes |  | Yes | Escape to MSI
376 | On Boarding | 2018-07-03 | 2018-08-10 | 29 | SK | Android V1.9 | 2 | No notification ask for App update if there is new release. | [5 empty] | 100% | [5 empty] | N/A | Closed | Yes |  | No | Not defect | maybe not a issue
377 | On Boarding | 2018-07-03 | 2018-08-10 | 29 | CS | Android V1.9 | 2 | App update causing app data to be erased. It supposed retain the existing app user data. | [5 empty] | 100% | [5 empty] | N/A | Closed | Yes |  | Yes | Escape to MSI | maybe not a issue
378 | Chat | 2018-07-03 | 2018-07-08 | 4 | CS | Android V1.9 | 2 | When App1 failed to send Chat across to App2, it showed RETRY. Keep tapping on RETRY the same message, will cause app to queue up the same message and send coninuously when connection is resumed. It supposed send only once if the message is the same, so that it won't cause the queue to be oveflow. | [5 empty] | 100% |  |  |  |  | 7/8/2018 Andriod V2.2 | N/A | Closed | Yes |  | Yes | Enhancement
379 | Maps | 2018-07-03 | 2018-08-10 | 29 | CS | Android V1.9 | 3 | "Radio Disconnected" only showed in Chat Mode, it should also show in MAPS screen | [5 empty] | 100% | [5 empty] | N/A | N/A | No |  |  |  |  | same issue #319 |  |  | 1
380 | Maps | 2018-07-03 | 2018-07-08 | 4 | CS | Android V1.9 | 2 | Without SIM registration, Track sharing is not available. But if go through 'MY MAPS' menu, it allow user to share track. This is wrong | [5 empty] | 100% |  |  |  |  | 7/8/2018 Andriod V2.2 | N/A | Closed | Yes |  | Yes | Escape to MSI
381 | Maps | 2018-07-03 | 2018-08-10 | 29 | CS | Android V1.9 | 3 | Start download offline maps, halfway through turn off Wifi and Data. Click to share the half downloaded maps, Observed that app allows user to share the incomplete maps. It should not allow incomplete map to be shared. | [5 empty] | 100% | [5 empty] | N/A | Closed | Yes |  | No | Not defect | [13 empty] | not an issue
382 | Maps | 2018-07-03 | 2018-07-08 | 4 | CS | Android V1.9 | 2 | App disconnected from Radio, go to Maps, tap on Set Location (last icon on the right), app still showing Location has been sent. | [5 empty] | 100% |  |  |  |  | 7/8/2018 Andriod V2.2 | N/A | Closed | Yes |  | Yes | Escape to MSI | [13 empty] | Same
383 | Radio Settings | 2018-07-03 | 2018-07-08 | 4 | SK | Android V1.9 | 1 | Andriod Phone not able to do pairing via APP. | [5 empty] | 100% |  |  |  |  | 7/8/2018 Andriod V2.2 | N/A | Closed | Yes |  | Yes | Escape to MSI
384 | Bluetooth Connection | 2018-07-03 | 2018-07-08 | 4 | SK | Android V1.9 | 3 | After ANDRIOD APP and Radio paired, to view in "BLUETOOTH CONNECTION", the 'TEST' button in white color? it should in Blue color. | [5 empty] | 100% |  |  |  |  | 7/8/2018 Andriod V2.2 | N/A | Closed | Yes |  | Yes | Enhancement
385 | Maps | 2018-07-03 | 2018-08-10 | 29 | CS | Android V1.9 | 2 | App 1 send a save track to App 2. Observed that the saved track data showed in App2 are not the same as App 1 | [5 empty] | 100% | [5 empty] | N/A | Closed | Yes |  | Yes | Escape to MSI |  | Total Ascent no info... received as 0 value. | [11 empty] | Same
386 | App Updates | 2018-07-03 | 2018-08-10 | 29 | CS | Android V1.9 | 2 | App automatically update to version 1.9 without having trigger update in Play Store. The Installation date still showing the old date. | [5 empty] | 100% | [5 empty] | N/A | Closed | Yes |  | Yes | Escape to MSI | maybe not a issue | [12 empty] | not an issue
387 | Radio Settings | 2018-07-03 | 2018-07-08 | 4 | SK | Android V1.9 | 1 | Cannot do Weather Setting in Radio Via App. | [5 empty] | 100% |  |  |  |  | 7/8/2018 Andriod V2.2 | N/A | Closed | Yes |  | Yes | Escape to MSI
388 | Chat | 2018-07-03 | 2018-07-08 | 4 | SK | Android V1.9 | 2 | Created a Group with N/Ame "Family Trip", Open to start chat, but the Group N/Ame display as Group ID#, it should display "Family Trip" | [5 empty] | 100% |  |  |  |  | 7/8/2018 Andriod V2.2 | N/A | Closed | Yes |  | Yes | Escape to MSI
389 | Chat | 2018-07-03 | 2018-08-10 | 29 | SK | Android V1.9 | 3 | Different behavior compare to IOS: -> added a new member, now tab to chat with him... but i did't type any message, just back to chat home page, i cannot see the new added member N/Ame display at Chat Home Page, but IOS has. | Y |  | N | Y |  | N/A | Open |  |  |  |  | N/A | Closed | Yes |  | Yes | Enhancement |  |  | 2018-08-03
390 | Bluetooth Connection | 2018-07-04 | 2018-07-26 | 17 | SK | iOS V1.2 (1244) | 2 | Bluetooth connection with Radio for a few times in RANGE. Step: Moving out of bluetooth connection range around 15m. Moving in and out for several time, sometimes App cannot auto reconnect back with Radio. User need to OFF then ON again bluetooth, or re-Pair again the Radio. | [5 empty] | 70% |  |  |  |  | 26 July 2018 IOS V1.2 (1248) Radio V03.08 | Closed | N/A | Yes |  | Yes | Escape to MSI |  | 18 jul, CS: app issue fixed 1.2 47 19 July still Fail to auto reconnect (1248)
391 | APP Settings | 2018-07-04 | 2018-07-08 | 3 | SK | Android V1.9 | 1 | In APP settings, OFF the "EN/Able Shout", i still can see the SHout eN/Abled in Chat page. | [5 empty] | 100% |  |  |  |  | 7/8/2018 Andriod V2.2 | N/A | Closed | Yes |  | Yes | Escape to MSI
392 | Bluetooth Connection | 2018-07-04 | 2018-08-10 | 28 | Marjon | iOS (1244) | 3 | If phone is paired to other radio, and you try to pair to new radio before unpairing, it will just try to pair but no notification comes up, just showing connecting and pairing visual on app. Not able to test. Can we get notification " phone is paired to other radio, unpair first to pair to new radio" | [5 empty] | 100% | [5 empty] | Closed | N/A | Yes |  | Yes | Enhancement |  | 18 jul, XY: new feature ,will not support. 20 Jul, CS: Marjon, if the phone was already paired, in Bluetooth Connection menu it will show "Unpair radio" at the text below. If otherwise, it shall show "Pair radio". With that, user can tell whether the phone was already paired or not. But if you were saying, withough going into Bluetooth Connection menu, when you get a paired phone and pair again with another new radio, and you wished to see a pop up message. Then this is a more complicated sceN/Ario. Imagine you have 10 new radios nearby the phone, the phone will see these 10 new radios in its bluetooth device list and try to ping each radio, user will keep getting 10 pop up messages on this alert. This shall repeat at a fixed interval (due to BT ping feature) in few seconds. Therefore it will be rather annoying if we introduce this enhancement. So far, as far as i can recall, there is no such alert feature in the BT market.
393 | Maps | 2018-07-04 | 2018-08-10 | 28 | Marjon | iOS (1244), Android | 3 | I am sending a track to a group, only other phone online is without account. The track is not received on the phone without account but the track shows successfully send on the sender phone | Y |  | N | Y |  | 100% | [5 empty] | Closed | Closed | Yes |  | Yes | Enhancement |  | 18 jul, XY: not duplicate 24 Jul, CS: This is an issue, not enhancement. 24 Jul, XY: 1249已经解决 | 2018-08-03
394 | Radio Settings | 2018-07-05 | 2018-07-08 | 2 | SK | Android V2.0 | 2 | Channel and Code setting not really effectively make action. | [5 empty] | 100% |  |  |  |  | 7/8/2018 Andriod V2.1 | N/A | Closed | Yes |  | Yes | Escape to MSI
395 | Maps | 2018-07-05 | 2018-07-09 | 3 | SK | Android V2.0 | 2 | Geofence set no notification out of boundary No alert to send Location Pin | [5 empty] | 100% |  |  |  |  | 7/9/2018 Andriod V2.3 | N/A | Closed | Yes |  | No | Duplicate to Auctus | duplicate 401 | 反应慢应该跟gps定位速度有关，可能是天气或者其他遮挡引起。
396 | Maps | 2018-07-05 | 2018-07-09 | 3 | SK | Android V2.0 | 2 | In Maps, eN/Abled a SK to show as member to view, an "S" icon displayed. OK Now, i go into View Member to HIDE the member SK, but the "S" icon still displaying. | [5 empty] | 100% |  |  |  |  | 7/9/2018 Andriod V2.2 | N/A | Closed | Yes |  | Yes | Escape to MSI
397 | Radio Settings | 2018-07-06 | 2018-07-08 | 1 | SK | Android V2.0 | 2 | No notification in APP after radio paired via APP setting. | [5 empty] | 80% |  |  |  |  | 7/8/2018 Andriod V2.1 | N/A | Closed | Yes |  | Yes | Escape to MSI | maybe not a issue
398 | Chat | 2018-07-06 | 2018-07-08 | 1 | SK | Android V2.0 | 2 | added group from Andriod phone’s App, members has IOS and Android user, one the Group Leader sent a message, only Andriod phone will received the message, IOS user cannot received the message. | [5 empty] | 100% |  |  |  |  | 7/8/2018 Andriod V2.2 | N/A | Closed | Yes |  | Yes | Escape to MSI
399 | Chat | 2018-07-06 | 2018-07-09 | 2 | SK | Android V2.0 | 3 | Not the Actual Track display as in Track Icon. (Chat) | [5 empty] | 100% |  |  |  |  | 7/9/2018 Andriod V2.2 | N/A | Closed | Yes |  | Yes | Escape to MSI
400 | Maps | 2018-07-06 | 2018-07-08 | 1 | SK | Android V2.0 | 1 | Track recorded info not valid. | [5 empty] | 100% |  |  |  |  | 7/8/2018 Andriod V2.2 | N/A | Closed | Yes |  | Yes | Escape to MSI
401 | Radio Settings | 2018-07-06 | 2018-07-07 | 1 | SK | Android V2.0 | 1 | Emergency Message cannot sent trougth via APP. | [5 empty] | 100% |  |  |  |  | 7/7/2018 Andriod V2.1 | N/A | Closed | Yes |  | Yes | Escape to MSI
402 | Chat | 2018-07-06 | 2018-07-07 | 1 | SK | Android V2.0 | 2 | Sent Offline Maps to Sumsung A8 from Iphone 8. Sumsung A8 received 2 offline maps, where i just pressed one to sent. | [5 empty] | 100% |  |  |  |  | 7/7/2018 Andriod V2.1 | N/A | Closed | Yes |  | Yes | Escape to MSI
403 | Chat | 2018-07-06 | 2018-07-07 | 1 | SK | Android V2.0 | 2 | Received offline maps cannot be download in Sumsung A8. | [5 empty] | 100% |  |  |  |  | 7/7/2018 Andriod V2.1 | N/A | Closed | Yes |  | Yes | Escape to MSI
404 | Chat | 2018-07-07 | 2018-07-18 | 8 | SK | IOS V1.2 (1244) Android V2.1 | 2 | Received Emergency message not complete in IOS, Emergency message trigger from Radio pared with Andriod phone. | [5 empty] | 100% |  |  |  |  | 18 July 2018 IOS V1.2 (1247) | Closed | N/A | Yes |  | No | Duplicate to Auctus | duplicate 436 | 18 jul, XY: fixed 1.2 47
405 | Radio Settings | 2018-07-07 | 2018-07-08 | 0 | SK | Android V2.1 | 2 | Download offline maps, IOS has show the "Delete" and "SAVE" button, but Andriod not showing when keyboard eN/Abled. | [5 empty] | 100% |  |  |  |  | 7/8/2018 Andriod V2.2 | N/A | Closed | Yes |  | Yes | Escape to MSI
406 | Bluetooth Connection | 2018-07-08 | 2018-07-25 | 13 | SK | Android V2.2 IOS V1.2 (1244) | 3 | Radios and Phone connected in standby Sometimes will auto disconnect then reconnect. heppened half hour once. | [5 empty] | 100% |  |  |  |  | 25 July 2018 Andriod V2.4 | N/A | Closed | Yes |  | Yes | Enhancement |  | to be monitor.
407 | Maps | 2018-07-08 | 2018-07-09 | 1 | SK | Android V2.2 | 2 | Easy pairing to send GPS, All members showing in the same time stamp even if i off some of the radio, the time stamp still can update like others members. | [5 empty] | 100% |  |  |  |  | 7/9/2018 Andriod V2.3 | N/A | Closed | Yes |  | Yes | Escape to MSI
408 | Bluetooth Connection | 2018-07-08 | 2018-07-24 | 12 | SK | Android V2.2 | 3 | Wording wrong: (Different with IOS) 1. When i just OFF the radio paired, in Hamberger menu IOS showing "Disconnected", but Andriod Show "Connecting" 2. In Bluetooth connection page, tried to unpair radio, the status showing different, IOS show "N/A", Andriod show "Connecting". | [5 empty] | 100% |  |  |  |  | 24 July 2018 Andriod V2.4 | N/A | Closed | Yes |  | Yes | Enhancement
409 | Maps | 2018-07-08 | 2018-07-24 | 12 | SK | Android V2.2 | 3 | In flight mode, the APP to view Maps select Maps Styles, Map Styles Box should show message as IOS: "This map styles is not available. Please connect to internet to view or download" | [5 empty] | 100% |  |  |  |  | 24 July 2018 Andriod V2.4 | N/A | Closed | Yes |  | Yes | Enhancement
410 | Maps | 2018-07-08 | 2018-07-09 | 1 | SK | Android V2.2 | 2 | Received a Location Pin (Shared) from Andriod, cannot view.. (app closed) | [5 empty] | 100% |  |  |  |  | 7/9/2018 Andriod V2.3 | N/A | Closed | Yes |  | Yes | Escape to MSI
411 | Bluetooth Connection | 2018-07-06 | 2018-07-19 | 10 | BETA | iOS 1244 | 1 | Bluetooth: during hike frequent chirping of radio (2 chirps) followed by bluetooth beep. radio and phone would not disconnect indefiN/Ate but very disturbing. 1 out of the 3 radio/app pairings did this for a short very frequent (every 5 min). Later was less frequent (maybe due to apple watch also using bluetooth? but defiN/Ately all radios did this. Radios all on lock and in same backpack as the phones so can not be because of bluetooth distance | [10 empty] | 19 July 2018 IOS V1.2 (1247) | Closed | N/A | Yes |  | No | Duplicate to Auctus | duplicate 426 | same issue found in issue 11, and issue 406, where XY said is due to phone bluetooth connectivity. 10 jul, XY: Radio BT will stay even radio is in idle mode. But if radio BT connection is lost, after certain duration, BT will be shut down. 11 Jul, Marjon: The most freuqent occurance was on iPhone 8 but also happened on iPhone 6s from the other two hikers but less frequent. 18 jul, XY: app issue fixed 1.2 47
412 | Bluetooth Connection | 2018-07-06 | 2018-07-19 | 10 | BETA | iOS 1244 | 1 | Bluetooth: During 4 hour hike radios all radios got disconnected and not reconnected to the point bluetooth on radio turned off. | [10 empty] | 19 July 2018 IOS V1.2 (1247) | Closed | N/A | Yes |  | Yes | Escape to MSI | maybe not a issue | not understand 10 Jul, CS: Radio BT will stay even radio is in idle mode. But if radio BT connection is lost, after certain duration, BT will be shut down. 11 Jul, Marjon: Radio and phone were in same backpack so should not have disconnected. 12 Jul, CS: Do you know what was the battery level for both radio and Phone ? Marjon: The 1300 mAH batteries where fully charged and since this started from beginning of hike I don't believe battery could have been the issue. 18 jul, XY: app issue fixed 1.2 47
413 | Location sharing | 2018-07-06 | 2018-08-10 | 26 | BETA | iOS 1244 | 2 | Location sharing: delay in showing gps on screen when you press the easy pairing button | [11 empty] | Closed | N/A | Yes |  | Yes | Escape to MSI | maybe not a issue | not duplicate. 10 jul, XY: This shd be radio fw issue, flw up with ZhuYong 24 Jul, XY: cannot duplicate
414 | Location sharing | 2018-07-06 | 2018-08-10 | 26 | BETA | iOS 1244 | 1 | Location sharing: even though GPS showed up, did not resulted in sharing my location with others in my group. | [11 empty] | Closed | N/A | Yes |  | Yes | Escape to MSI | maybe not a issue | not duplicate, while if in GROUP, where the MAP view displaying more than 1 or more members are activated, not nessecary all will recievied the GPS update. 10 jul, XY: Could be due to connection lost issue 12 Jul, CS: not able to reproduce the issue at the moment 24 Jul, XY: cannot duplicate
415 | Maps | 2018-07-06 | 2018-08-10 | 26 | BETA | iOS 1244 | 1 | Maps: not clear how to open share sheet or show on map. need to distinguish and explain how to do both. watching participants do this took at least 5 tries. | [11 empty] | Closed | N/A | Yes |  | Yes | Escape to MSI |  | not understand. need to get more info from Marjon 11 Jul, Marjon: If you want to share a map or track in my maps and click on it, in stead of the selection window of users to share with, it opens the map or track on the map. Only sometimes it does not, so not clear how to drive 'sharing' versus 'opening map" 11 Jul, SK: Kindly do review the demo of opening and sharing of the Track--> https://drive.google.com/drive/folders/1uNyaiRcHRmk3oKR9tIZsTx2Q_q-p2BUA 12 Jul, Marjon: 12 Jul, CS: When you are in offline Map, you won't see "Show on map" option. You can either click on the share icon to share or click anywhere in the offline map selection (besides the share icon) to open up the map. For "Show on map" option, it is only available in Select Track menu, where you can choose which tracks you want to see. This is correct behavior 17 Jul, LeeSun: Eye icon is to turn on and off the selected tracks, whereas for Maps, user can only view one map at one time, thus eyes icon does not apply here. Eye icons allow user to turn on multiple tracks within the same map, again this does not applicable to map view. To view the maps, user just need to tap on the map list item (not the Share icon), just like how they read the received message. 18 Jul, CS: Marjon showed us the difficulties in selecting sharing icon in iphone. Sensitivity of seelcting sharing icon has to be improved.
416 | Maps | 2018-07-06 | 2018-08-10 | 26 | BETA | iOS 1244 | ENH | Maps sharing: you can share maps without radios on but not pins. first of all this need to be both possible. Secondly even if this was by design, user expect to be able to do this since the same share icon is showing. | [11 empty] | N/A |  | No |  |  |  |  | Only offline Maps and Track can be share in server... Location Pin cannot by design. This is an enhancement feedback, need to detail out how to implement in App.
417 | Maps | 2018-07-06 |  | -30920 | BETA | iOS 1244 | 3 | Maps sharing: share icon on my maps uses not the standard share icon for IOS users (box with arrow out) forgot conclusion of this, but believe was discussed before. | N | Enh_D1 | N | Y | [7 empty] | Closed | Closed | Yes |  |  |  |  | not understand 10 Jul, CS: will standardize the icon 18 jul, XY: fixed 1.2 47 18 Jul, CS: icon still not the box with arrow out 26 Jul, XY, This is new feature , not reflecetd in latest VI 26 Jul, Marjon: UI no tclearly defined, Has to be updated to iOS N/Ative icon | 2018-08-03
418 | Maps | 2018-07-06 | 2018-07-18 | 9 | BETA | iOS 1244 | 1 | Maps sharing: sharing a pin showed me at that location even though pin was of different location | [10 empty] | 18 July 2018 IOS V1.2 (1247) | Closed |  | Yes |  | No | Duplicate to MSI | dupliate 351 | feedback in issue list #351. Needs time to fix. FT agreed. 10 Jul, CS: fixing is in progress. Will be available in next iOS release 18 jul, XY: finished 1.2 47
419 | Maps | 2018-07-06 | 2018-08-10 | 26 | BETA | iOS 1244 | 1 | Pin sharing: when trying to share my location and chat it wouldn't pull up map just black map with pin. Did send it and recipient pulled up a black map with pin | Y | [10 empty] | Closed |  | Yes |  | Yes | Escape to MSI |  | not sure is the same case as #316. where this is Map issue, feedback by XY. 11 Jul, Marjon: It is at street view 18 jul, XY: not duplicate 25 Jul, Marjon: it was a pin in Italy. I still have the pin. can I share with you if I add you as member over the internet? what is your phone number.
420 | Maps | 2018-07-06 | 2018-08-10 | 26 | BETA | iOS 1244 | 1 | Maps: the recording does not continue when the phone goes in standby, resulting in straight lines everywhere | [11 empty] | Closed |  | Yes |  | Yes | Escape to MSI |  | need to check... 10 Jul, CS: feedback to supplier 18 jul, XY: not duplicate
421 | Maps | 2018-07-06 | 2018-07-23 | 12 | BETA | iOS 1244, Android | 1 | Maps: track recording not according to actual trail, photos showed the GAIA GPS app location track and the Talkabout track. Talkabout was bouncing around between mountains resulting in unrealistic long distance and total ascent. 25% more than we actually ascented. | [10 empty] | 23 July 2018 IOS V1.2 (1248) 24 July 2018 Andriod V2.4 | Closed | Closed | Yes |  | No | Duplicate to MSI | duplicate 420 | i have no device to compare. 10 jul, XY: can be implemented 18 jul, XY: the algorithm need change ,need FT check
422 | Maps | 2018-07-06 | 2018-07-19 | 10 | BETA | iOS 1244 | 2 | Maps: total minutes should become hour, minutes, not just minutes. | [10 empty] | 19 July 2018 IOS V1.2 (1247) | Closed | N/A | Yes |  | Yes | Enhancement |  | 10 jul, XY: can be implemented 18 jul, XY: finished 1.2 47
423 | Maps | 2018-07-06 | 2018-08-10 | 26 | BETA | iOS 1244 | ENH | Maps: user should be able to change walker icon on track to bicycle for bike rides | [11 empty] | N/A | N/A | No |  |  |  |  | enhancement??? 10 jul, CS: This is new proposal, need to define detailed implementation.
424 | Maps | 2018-07-06 | 2018-08-10 | 26 | BETA | iOS 1244 | 2 | Maps: location pin does not show with correct N/Ame in chat, just as location pin,N/Ame should go with it. | [11 empty] | Closed |  | Yes |  | No | Duplicate to Auctus | duplicate 265 | not duplicate 10 jul SK: is it saved location pin or just the location pin opened in chat mode ? 11 Jul SK: We cannot duplicate.. Please do review the video captured in this Link --> https://drive.google.com/drive/folders/1uNyaiRcHRmk3oKR9tIZsTx2Q_q-p2BUA
425 | Maps | 2018-07-09 | 2018-08-10 | 25 | SK | Android V2.3 | 3 | Geofence Alert will disappear just click any place on screen, but not happen in IOS. | [11 empty] | N/A | Closed | Yes |  | Yes | Escape to MSI |  | Caveat
426 | Maps | 2018-07-09 | 2018-08-10 | 25 | SK | iOS V1.2 (1244) | 2 | Track can share by click "<" share button which without account registered. SHould have an error message as Andriod did. | [5 empty] | 19 July 2018 IOS V1.2 (1248) | [5 empty] | Closed | N/A | Yes |  | Yes | Enhancement |  | 10 jul, XY: can be implemented 18 jul, XY: finished 1.2 47 18 Jul, SK Track fixed, but sharing offline Maps same problem 19 Jul, SK fixed in 1.2 48
427 | Maps | 2018-07-09 |  | -30921 | FT | iOS V1.2 (1239), Android | 3 | Press radio easy pairing button OR press locate button(in map view) to send location is now following the FCC 30s rule. When user try to send location more than 1 time within 30s, the request to send location will be in queue. In current release all the send location request will be in queue and making the send message request need to wait long. We shall change it to only 1 location request will be in queue. Example: User press locate button 5 times within 30s, then followed by a text message. At 0s, first location will be sent; at 30th second 2nd location will be sent, at 60th second, text message will be sent. | N | Enh_PostD1 | N | [8 empty] | Open | Open | Yes |  |  |  |  | Already feedback in V.12(1239) but did not capture in issue list. 10 jul, XY: can be implemented 18 jul, XY: new feature ,will not support 26 Jul, Marjon: Still seeing the GPS location not updated issue. For this particular 30s rule request, it can be put as future Enh.
428 | Settings | 2018-07-13 | 2018-08-10 | 21 | BETA | iOS (1244), Android | 3 | Radio settings: Allow a touch and hold/slide left or right to scrub faster to higher numbers. Channel and Sub Code didn't always hold on choice after moving to next adjustment. Sometimes would "rubber band" to another number after release or pause.This also happened on Call tone and VOX. | Y |  | N | Y |  | Open | Open |  |  |  |  | Closed | Closed | Yes |  | Yes | Escape to MSI | duplicate264 | 18 jul, XY: app need follow radio , It's normal case 24 Jul CS: This is a Beta feedback issue, need to be fixed. Video uploaded at: https://drive.google.com/open?id=1yZSnE7TCkeLk_vrTPStu9YEf_6tmpmmH | 2018-08-10
429 | On Boarding | 2018-07-13 | 2018-08-10 | 21 | BETA | iOS (1244) | 2 | First make sure BT is disbaled at control center. Next go to Settings and eN/Able BT. Then Launch Talkabout app and observed that setup is stuck at EN/Abling BT page. | Y |  | N | Y |  | Open | N/A |  |  |  |  | Closed | N/A | Yes |  | Yes | Escape to MSI | maybe not a issue | 18 Jul, XY: iOS 11 bug, no workaround solution 18 Jul, SK: when issue is reproduced, try pair with other BT device, it can be paired 24 Jul, XY: 这个问题是IOS 系统的问题，参考https://forums.developer.apple.com/message/300002#300002 24 Jul, CS: We urge to look for workaround solution, as we did not see this issue when pairing with BT headset. 31 JUl, CS: request SK to send steps to XY 13 Aug, XY: This is same issue for other BLE app. Caused by iOS bug. | 2018-08-15
430 | Maps | 2018-07-17 |  | -30927 | BETA | iOS, Android | 3 | Change the View icon in Maps (second icon at right side) to Group Member icon. | N | Enh_D1 | N | P | [7 empty] | Closed | Closed | Yes |  |  |  |  | 17, Jul,XY: new feature, not supported 26 Jul, Marjon: Has to be fixed by D2 1 Aug, CS: This is not captured in the SRS or VI previously | needs 1 week after cost is locked down |  |  |  | android 0.25 week , iOS 0.25week, test 0.25week, document 0.05week
431 | Settings | 2018-07-18 | 2018-08-10 | 18 | CS | iOS, Android | 3 | Update Emergency settings wordings at the second paragraph: Long press Emergency Alert Button on your radio for 3 seconds to send audible siren on the radios within range (for 8 seconds) followed by 22 seconds of the channel to be opened to transmit any sound. This is followed by emergency message to be sent out. In addition to this, your current location will be sent and reflected in Group members Maps View. | Y |  | N | Y |  | Open | Open |  |  |  |  | Closed | Closed | Yes |  | Yes | Enhancement |  | 24 Jul, CS: Issue sent to Auctus but no commitment received yet. 24 Jul, XY: iOS 1.2 49 会解决，安卓2.5 会解决 | 2018-08-03
432 | Chat | 2018-07-20 | 2018-07-24 | 3 | SK | iOS V1.2 (1248), Android V2.3 | 2 | IOS (1248) add group member (Andriod V2.3) in the Group N/Ame as "Family Trip". Andriod phone (members) cannot see the group N/Ame added in his Group list. IOS uN/Able to send request to Andriod. | [10 empty] | 24 July 2018 IOS V1.2 (1248) 24 July 2018 Andriod V2.4 | Closed | Closed | Yes |  | Yes | Escape to MSI
433 | Settings | 2018-07-20 | 2018-07-24 | 3 | SK | Android V2.3 | 3 | Dual Channel can set to CHannel "0" which this is wrong. | [10 empty] | 24 July 2018 Andriod V2.4 | N/A | Closed | Yes |  | Yes | Escape to MSI
434 | General | 2018-07-23 |  | -30931 | CS | iOS, Android | 2 | French translation to be supported in Talkabout App | N | Enh_D1 | [9 empty] | Closed | Closed | Yes |  |  |  |  | 20 Jul, XT: Auctus not committed in delivering French translation
435 | Maps | 2018-07-24 | 2018-08-10 | 14 | SK | Android V2.4 | 2 | observed force shutdown while Geofence activated and out of boundary. with Andriod phone Huawei (Andriod 4.4.2) | Y |  | N | Y |  | N/A | Open |  |  |  |  | N/A | Closed | Yes |  | Yes | Escape to MSI |  |  | 2018-08-03
436 | Settings | 2018-07-25 | 2018-08-10 | 13 | SK | Android V2.4 | 3 | Radio disconnected and reconnect back in a short while when entering MYSELF open Camera, then return to menu. | [11 empty] | N/A | Closed | Yes |  | Yes | Escape to MSI
437 | Setup | 2018-07-26 | 2018-08-10 | 12 | BETA | iOS (1244), Android | 3 | first couple of onboarding screens are flashing too fast | Y |  | N | Y |  | Open | Open |  |  |  |  | Closed | Closed | Yes |  | Yes | Enhancement |  | 26 Jul, CS: confirmed it is an issue, video uploaded at Baidu 31 Jul, CS: Resend to XY | 2018-08-10
438 | maps | 2018-07-26 |  | -30934 | BETA | Android V2.3 | 4 | Difficulty with understanding on how to download maps, Add a tip about where to find help Include education tip as last tip in onboarding: Familiarize yourself with the app! Go to Help menu for FAQ’s and tutorial videos. | N | Enh_D1 | Y | P | [7 empty] | Closed | Closed | Yes |  |  |  |  | 26 Jul, CS: This is user familiarity issue. Adding note to FAQ? Jul 27:MM. This is crucial to ensure users accept the app as useful. I will send seperate email to Lee Sun asking her to work on this. 1 Aug, LiN/Ar: we will ask SiauFong to ask Auctus provide quotation based on one paragraph and 5 icons in FAQ | After cost and UI lock down, need 1.5 weeks
439 | keyboard | 2018-07-26 |  | -30934 | BETA | Android V2.3 |  | When the keyboard is pulled up, it covers the 'next' button, which user may not know they need to collapse the keyboard to find it. Either when user hit return on keyboard will bring them to the next step or bring the next button above the keyboard. | N | Enh_PostD1 | Y | [8 empty] | Open | Open | Yes |  |  |  |  | 26 Jul, CS: This involves new VI to be updated 26 Jul, MM: not crucial can be future
440 | onboarding | 2018-07-26 |  | -30934 | BETA | Android V2.3 | ENH | Allow user to go back to tips at later time (skip and go back) => for future | N | Enh_PostD1 | [9 empty] | Open | Open | Yes
441 | radio settings | 2018-07-26 | 2018-08-10 | 12 | BETA | Android V2.3 | 3 | Fix slider to go negative per alpha test | N |  | N | p | [7 empty] | Duplicated | Duplicated | No |  |  |  |  | 26 Jul, CS: Min and Max shall be truncated, follow the solution propsed in #120 | Same as #120 |  | 1
442 | menu | 2018-07-26 | 2018-08-10 | 12 | BETA | Android V2.3 |  | menu should be closed if I enter my member page and N/Avigate back | N |  | N | [8 empty] | Closed | Closed | Yes |  | Yes | Enhancement |  | 26 Jul, CS: This is current behavior, not quite understand the exact issue. 26 Jul. MM: sorry not sure what the beta tester meant on this one myself. Hoped the UI team did.
443 |  | 2018-07-26 | 2018-08-10 | 12 | BETA | Android V2.3, iOS | 3 | The notification badge (blue dot with count) is not centered on the list. | Y |  | N | Y |  | Open | Open |  |  |  |  | Closed | Closed | Yes |  | Yes | Enhancement |  | 26 Jul, CS: can clarify further? Right now is at bottom right corner, following VI. 26 Jul. MM coming from the UI/UX team (Maggie Wang) was hoping that Lee Sun speaks this language and understands what she meant. I send a follow up email to ask for clarification 27 Jul. See screen shot in consolidated list. seems a bug for some phones. 31 Jul, CS: Pixel 1, Android 8 | 2018-08-10
444 | FAQs | 2018-07-26 | 2018-08-10 | 12 | BETA | Android V2.3, iOS | 4 | FAQ's are not very clean and look a bit amateuristic, Improve lay out /font etc. | Y |  | Y | Y |  | Open | Open |  |  |  |  | Closed | Closed | Yes |  | Yes | Enhancement |  | 26 Jul, CS: redesign FAQ VI ? 1 Aug, CS: LeeSun will communicate with Auctus on the proposed layout. Font fixing and alignment should not charge for costing. For FAQ alignement, please refer to wireframe_20180718, page 131. | time TBD depends on new layout design to determine the effort
445 | Members | 2018-07-26 |  | -30934 | BETA | Android V2.3, iOS | 4 | Sections not understood: What is a group | N | Enh_D1 | N | N | [7 empty] | Closed | Closed | Yes |  |  |  |  | 26 Jul, CS: This is user familiarity issue. Adding note to FAQ? If yes, then FAQ contents MUST be locked down before 3-Aug-18 1 Aug, CS: | Pending MSI to lock down FAQ content |  | Marjon to provide complete FAQ content by 3-Aug-18
446 | Members | 2018-07-26 |  | -30934 | BETA | Android V2.3, iOS | 4 | Sections not understood: What is a member | N | Enh_D1 | N | N | [7 empty] | Closed | Closed | Yes |  |  |  |  | 26 Jul, CS: This is user familiarity issue. Adding note to FAQ? If yes, then FAQ contents MUST be locked down before 3-Aug-18 | Pending MSI to lock down FAQ content |  | Marjon to provide complete FAQ content by 3-Aug-18
447 | Maps | 2018-07-26 |  | -30934 | BETA | Android V2.3, iOS | 4 | Sections not understood: What is a geofence | N | Enh_D1 | N | N | [7 empty] | Closed | Closed | Yes |  |  |  |  | 26 Jul, CS:: This is user familiarity issue. Adding note to FAQ? If yes, then FAQ contents MUST be locked down before 3-Aug-18 | Pending MSI to lock down FAQ content |  | Marjon to provide complete FAQ content by 3-Aug-18
448 | Maps | 2018-07-26 |  | -30934 | BETA | Android V2.3, iOS | 4 | Sections not understood: How to download a map | N | Enh_D1 | N | N | [7 empty] | Closed | Closed | Yes |  |  |  |  | 26 Jul, CS:: This is user familiarity issue. Adding note to FAQ? If yes, then FAQ contents MUST be locked down before 3-Aug-18 | Pending MSI to lock down FAQ content |  | Marjon to provide complete FAQ content by 3-Aug-18
449 | Maps | 2018-07-26 |  | -30934 | BETA | Android V2.3, iOS | 4 | Sections not understood: How to reN/Ame tracks, maps, pins | N | Enh_D1 | N | N | [7 empty] | Closed | Closed | Yes |  |  |  |  | 26 Jul, CS:: This is user familiarity issue. Adding note to FAQ? If yes, then FAQ contents MUST be locked down before 3-Aug-18 | Pending MSI to lock down FAQ content |  | Marjon to provide complete FAQ content by 3-Aug-18
450 | Menu /N/Avigation | 2018-07-26 |  | -30934 | BETA | Android V2.3, iOS | 4 | Sections not understood: Multiple users indicated not to be able to figure out how to get back to chat menu | N | Enh_D1 | N | N | [7 empty] | Closed | Closed | Yes |  |  |  |  | 26 Jul, CS:: This is user familiarity issue. Adding note to FAQ? If yes, then FAQ contents MUST be locked down before 3-Aug-18 | Pending MSI to lock down FAQ content |  | Marjon to provide complete FAQ content by 3-Aug-18
451 | Maps | 2018-07-26 |  | -30934 | BETA | Android V2.3, iOS | 4 | Sections not understood: total ascent (how it is calculated) | N | Enh_D1 | N | N | [7 empty] | Closed | Closed | Yes |  |  |  |  | 26 Jul, CS: This is user familiarity issue. Adding note to FAQ? If yes, then FAQ contents MUST be locked down before 3-Aug-18 | Pending MSI to lock down FAQ content |  | Marjon to provide complete FAQ content by 3-Aug-18
452 | Maps | 2018-07-26 |  | -30934 | BETA | Android V2.3, iOS | 4 | Sections not understood: how to view the statistics (requires clicking on the icon) but not intuitive | N | Enh_D1 | N | N | [7 empty] | Closed | Closed | Yes |  |  |  |  | 26 Jul, CS: This is user familiarity issue. Adding note to FAQ? If yes, then FAQ contents MUST be locked down before 3-Aug-18 | Pending MSI to lock down FAQ content |  | Marjon to provide complete FAQ content by 3-Aug-18
453 | Maps | 2018-07-26 |  | -30934 | BETA | Android V2.3, iOS | 4 | Sections not understood: who receives my location when I tap on locate icon | N | Enh_D1 | N | N | [7 empty] | Closed | Closed | Yes |  |  |  |  | 26 Jul, CS: This is user familiarity issue. Adding note to FAQ? If yes, then FAQ contents MUST be locked down before 3-Aug-18 | Pending MSI to lock down FAQ content |  | Marjon to provide complete FAQ content by 3-Aug-18
454 | Maps | 2018-07-26 |  | -30934 | BETA | Android V2.3, iOS | 4 | Sections not understood: icon of offline map and track is confusing | N | Enh_D1 | N | N | [7 empty] | Closed | Closed | Yes |  |  |  |  | 26 Jul, CS: This is user familiarity issue. Adding note to FAQ? If yes, then FAQ contents MUST be locked down before 3-Aug-18 | Pending MSI to lock down FAQ content |  | Marjon to provide complete FAQ content by 3-Aug-18
455 | Maps | 2018-07-26 |  | -30934 | BETA | Android V2.3, iOS | 4 | Sections not understood: why are offline map and track features not available | N | Enh_D1 | N | N | [7 empty] | Closed | Closed | Yes |  |  |  |  | 26 Jul, CS: This is user familiarity issue. Adding note to FAQ? If yes, then FAQ contents MUST be locked down before 3-Aug-18 | Pending MSI to lock down FAQ content |  | Marjon to provide complete FAQ content by 3-Aug-18
456 | Maps | 2018-07-26 |  | -30934 | BETA | Android V2.3, iOS | 4 | Sections not understood: why they can not send an off line map off grid | N | Enh_D1 | N | N | [7 empty] | Closed | Closed | Yes |  |  |  |  | 26 Jul, CS: This is user familiarity issue. Adding note to FAQ? If yes, then FAQ contents MUST be locked down before 3-Aug-18 | Pending MSI to lock down FAQ content |  | Marjon to provide complete FAQ content by 3-Aug-18
457 | Chat | 2018-07-26 | 2018-08-10 | 12 | BETA | Android V2.3, iOS |  | Sections not understood: Delete chat vs delete chat history is confusing | N |  | N | [8 empty] | Closed | Closed | Yes |  | No | Not defect |  | 37 Jul, CS: This is user familiarity issue. Adding note to FAQ? If yes, then FAQ contents MUST be locked down before 3-Aug-18 27 Jul, MM: I reviewed this comment and I think UI already explains when you click on it. adding to FAQ is not needed.
458 | Maps | 2018-07-26 | 2018-08-10 | 12 | BETA | Android V2.3, iOS | 4 | Sections not understood: How to share a map (this was iOS user so hopefully fixing the area on where to click and using the familiar share icon will improve this | Y |  | N | N | [7 empty] | Duplicated | N/A | No |  |  |  |  | 26 Jul, CS: This is user familiarity issue. Adding note to FAQ? If yes, then FAQ contents MUST be locked down before 3-Aug-18 Jul 27: this is problem that can not be solved with FAQ. This has to be solved. 1 Aug, CS: share icon issue has been captured in #417 | Pending MSI to lock down FAQ content |  | 1
459 | Chat | 2018-07-26 |  | -30934 | BETA | Android V2.3, iOS |  | Make predefined messages visible in chat rather than keyboard (keyboard should be selection: . RatioN/Ale would be if you want to be quick you use predefined so should be easy accessible. Keyboard means involvement so one more stroke not an issue. | N | Enh_PostD1 | Y | [8 empty] | Open | Open | Yes |  |  |  |  | 26 Jul, CS: redesign current VI ? 27 Jul, MM should be done as soon as possible. But not gating D2
460 |  | 2018-07-26 |  | -30934 | BETA | Android V2.3, iOS |  | some unnecessary animation: overflow menu being fly in from the middle of screen. | N | Enh_PostD1 | Y | [8 empty] | Open | Open | Yes |  |  |  |  | 26 Jul, CS: can clarify further? 26 Jul. I have requested clarification and this is answer. I am thinking that it might be unique to Android as I still don't understand. "When you in a message view with someone and taps on the overflow icon: the overflow menu appears from the middle of the screen and float to the top. Typically stock Android just opens the menu right under the overflow icon. Adding animation is not a big deal but the speed of animation may need to be adjusted faster as it is a little slow now and user has to wait for the animation and then select the action." 27 Jul, CS: what does it mean by overflow icon? If not mistaken, we don;t have any animaton in the app. Could you please clarify ? 27 Jul, MM see clarification in email to Lee Sun. Up to Lee Sun to determine severity. I do not have android phone to see. but likely not gating item for D2
461 |  | 2018-07-26 | 2018-08-10 | 12 | BETA | Android V2.3, iOS | 3 | Minimum 3 members (appear in the toast) in a group is also not clear. I can select 2 people and the create group screen is saying Total 2 members and I'm allowed to proceed. Also N/Ame should be optioN/Al and I could always go back to add the N/Ame. | Y |  | N | Y |  | Open | Open |  |  |  |  | Closed | Closed | Yes |  | Yes | Enhancement |  | 26 Jul, CS: can clarify further? 26 Jul, mm: yes, when you create a group a pop up says you need minimum of 3 members but allos you to create a group while only 2 members are added, so message is not correct. Should say: Minim 3 members including yourself. Or Minimum 2 members. 27 Jul: Please change to: Minimum 2 members are required. (also corrects the grammar) | 2018-08-10
462 |  | 2018-07-26 |  | -30934 | BETA | Android V2.3 | ENH | allow more pre defined messages. future | N | Enh_PostD1 | [9 empty] | Open | Open | Yes
463 |  | 2018-07-26 |  | -30934 | BETA | Android V2.3, iOS |  | users seem to have difficulties finding maps in the search area is this controlled by map box or can we help to improve on this? | N | Enh_PostD1 | N | [8 empty] | Open | Open | Yes |  |  |  |  | 38 Jul, CS: This is user familiarity issue. Adding note to FAQ? If yes, then FAQ contents MUST be locked down before 3-Aug-18 27 Jul, mm: this is not user familiarity issue but many 'landmarks' or N/Ames are not found in map box. Is this map box map issue?
464 |  | 2018-07-26 |  | -30934 | BETA | Android V2.3, iOS |  | message for sharing offline maps in menu is pop up 'feature available when connected to internet). Why in chat when attaching message it just says: feature not available (does not help user understand why and negative) | N | Enh_D1 | N | [8 empty] | Closed | Closed | Yes |  |  |  |  | 38 Jul, CS: This is user familiarity issue. Adding note to FAQ? If yes, then FAQ contents MUST be locked down before 3-Aug-18 27 Jul, mm: not user familiarity issue, is issue of consistency,notification should be more clear. they already changed the message to: 'feature available when connected to internet' but it does not look very professioN/Al. can we not have the same white overlay as for the message pop up in the menu (same treatment 27 Aug, CS: Covered in #478
465 |  | 2018-07-26 |  | -30934 | BETA | Android V2.3, iOS |  | request to send location before sending and who to send to (currently not clear where it goes) | N | Enh_PostD1 | Y | [8 empty] | Open | Open | Yes |  |  |  |  | 38 Jul, CS: This is user familiarity issue. Adding note to FAQ? If yes, then FAQ contents MUST be locked down before 3-Aug-18 27 Jul, your suggetion is to send everything to FAQ😀. But obviously that is not good design. It should be intuitive. I don't see this as crucial now but we should think about future updates. If automatic becomes approved, we can elimiN/Ate that you send location out and just let it be a pan to your current location button as it is in google.
466 |  | 2018-07-26 |  | -30934 | BETA | Android V2.3, iOS |  | Request share sheet to export GPX files of maps and location pins is not available | N | Y | Y | [8 empty] | Open | Open | Yes |  |  |  |  | 38 Jul, CS: This is user familiarity issue. Adding note to FAQ? If yes, then FAQ contents MUST be locked down before 3-Aug-18 27 Jul, MM: not familiarity issue. Has always been a request. Should be implemented asap but not gating item.
467 |  | 2018-07-26 |  | -30934 | BETA | Android V2.3, iOS |  | it's not very clear that you have to go to menu to save a offline map. Usually people will go to map tab and try to find where to create offline map. | N | Enh_PostD1 | N | [8 empty] | Open | Open | Yes |  |  |  |  | 38 Jul, CS: This is user familiarity issue. Adding note to FAQ? If yes, then FAQ contents MUST be locked down before 3-Aug-18
468 |  | 2018-07-26 | 2018-08-10 | 12 | BETA | Android V2.3, iOS |  | after updating to new version, members that were added before are no longer there. Disappeared. | Y |  | N | [8 empty] | Closed | Closed | Yes |  | No | Not defect |  | 26 Jul, CS: update from which version? This issue has been resolved in recent versions 26 Jul, MM. I am not sure anymore if this happened before or after I deleted the app. Part of me thinks it was before but since I am not sure, will close and monitor if it happens again.
469 |  | 2018-07-26 |  | -30934 | BETA | Android V2.3, iOS | 3 | very unclear to various users what using an ID means. Various users tried to send messages using a phone number to users that chose to set up their account with an ID. The fact that that is not possible is not understood. some also wanted to type a N/Ame in field using ID and where frustrated that only the number keyboard comes up. They confused using ID with User ID or user N/Ame. At the very least we need to improve on the ADD NEW MEMBER screen to make it clear what using a phone number or using ID means (using ID is the account ID assigned to the user during set up) Also assign member N/Ame is not clear how that relates to the two above. This seems to be stumbling block for some of the beta users and they think it is not working whereas it is more an issue of not understanding the app. UI team needs to make proposal on how to make this more intuitive. | N | Enh_D1 | Y | N | [7 empty] | Closed | Closed | Yes |  |  |  |  | 26 Jul, CS: This is user familiarity issue. Adding note to FAQ? If yes, then FAQ contents MUST be locked down before 3-Aug-18 Otherwise, need to redefine a new VI to cater for new appearance. 27 Jul, mm: this is big issue for multiple beta testers. adding to FAQ will not solve. Need to redesign the adding member screen and also add wording when setting up the account. Will send email to Lee Sun 31 Jul, CS: breakdowns of these items are shown in #444, 485 and 487 to 491 | pending for ID lock down
470 |  | 2018-07-26 |  | -30934 | BETA | Android V2.3, iOS |  | Update tip on Put phone in airplane. Keep Bluetooth on. | N | Enh_PostD1 | Y | [8 empty] | Open | Open | Yes |  |  |  |  | 26 Jul, CS: request to update FAQ ? If yes, then FAQ contents MUST be locked down before 3-Aug-18 27 Jul, MM: more intuitive to do in tip.
471 |  | 2018-07-26 |  | -30934 | BETA | Android V2.3, iOS |  | some beta testers find the number of options on the map view overwhelming and think they should be regrouped. Also not always clear difference between pin and my location. I don't have a solution to simplify this and make differences more clear. UI team to think about this. | N | Enh_PostD1 | Y | [8 empty] | Open | Open | Yes |  |  |  |  | 26 Jul, CS: This is user familiarity issue. Adding note to FAQ? If yes, then FAQ contents MUST be locked down before 3-Aug-18. Otherwise, need to redefine a new VI to cater for new appearance. Jul 27 MM: we should not use FAQ as a cruch to fix issues with intuitiveness. this is something to consider for future app updates.
472 |  | 2018-07-26 | 2018-08-10 | 12 | BETA | Android V2.3, iOS |  | If I start walking downhill, how can the ascent increase before I go back uphill?=> seems that this functioN/Ality is not working properly | Y |  |  | Y |  | Open | Open |  |  |  |  | Closed | Closed | Yes |  | No | Duplicate to MSI | duplicate 227 | 26 Jul,CS: how many was the ascent increase? Can share reading before and after ? 27 Jul, MM: obviously it should not go up if someon goes down, is this a lag issue? Have we done sufficient comparison test to check accurate measurements? 31 Jul, CS: I compared with GAIA, the app is also showing increment in ascent when going down hill. request to share out the track file. my maps => my tracks =>click share icon => export by email or others
473 |  | 2018-07-26 |  | -30934 | BETA | Android V2.3, iOS |  | sharing location pin goes in to a loop => see this video | N | Enh_PostD1 | Y | [8 empty] | Open | Open | Yes |  |  |  |  | 26 Jul, CS: user needs to tap back arrow on the top left corner Jul 27: MM: good example for a close button for future updates |  | https://drive.google.com/open?id=19Ybiowyj1ckpy7Bw9XyOUaMRVjGmcTPu
474 |  | 2018-07-26 |  | -30934 | BETA | Android V2.3, iOS |  | when you select view members it won't show unless you send a message to each other successfully. User expects the moment you click view member to see them. So selecting view member should trigger a ping for location. | N | Enh_PostD1 | Y | [8 empty] | Open | Open | Yes |  |  |  |  | 26 Jul, CS: This is new requirement. 27 Jul, MM: for future updates
475 |  | 2018-07-26 |  | -30934 | BETA | Android V2.3, iOS |  | Trackrecording does not allow to move or zoom while recording | N | Enh_PostD1 | Y | [8 empty] | Open | Open | Yes |  |  |  |  | 26 Jul, CS: This is new requirement. 27 Jul, MM: this is useability issue, while recording you should be able to still look where you are going etc. It is possible if you click on the map and get out of the trackrecording notification screen. Just not intuitive so users think they are no longer to do this. How can we make this clearer?
476 |  | 2018-07-26 | 2018-08-10 | 12 | BETA | Android V2.3, iOS |  | Track recording not always show track during recording, only after saving. For instance I looked at the track recording during walk and only showed duration 3 min and no line from where I started recording but later on in the walk it does (coming in to view of the screen), not sure if it had to do with the fact that in the beginning I was using airplane mode and later no longer and that allowed it to show real time. But it should be working in airplane mode as that is the typcial use case. | Y | [10 empty] | Closed | Closed | Yes |  | Yes | Enhancement |  | 26 Jul, CS: So far we don't encounter this, we can try to replicate 27 Jul, SK: Kindly correct me if my step is wrong, because i still cannot see the problem at my side. 1- Set phone in Flight Mode. 2- Launch the Talkabout APP, and connect to the radio. 3- In Maps View, to start TRACK recording. 4- Moving and check the Track Line. (where i can see the Track moving in flight mode) 27 Jul, MM: as follows (no radios involved in this test) 1- Launch the Talkabout APP, and set phone to airplane mode 2- In Maps View, to start TRACK recording. 3- Moving no track line is displayed. Only after turning phone back to online mode, the track shows up. So it did not limit the phone to record it, just to display it. How is airplane mode related to displaying the track?
477 |  | 2018-07-26 | 2018-08-10 | 12 | BETA | Android V2.3, iOS |  | How to you indicate that user is no longer online? right now a user still shows even though off line. | N |  | N | [8 empty] | Closed | Closed | Yes |  | No | Not defect |  | 26 Jul, CS: If user is offline, the thumbN/Ail color will be dim. This is currently supported in both iOS and Android 26 Jul, Marjon: No, not for me. If you go offline it still is showing. even after pinging again to give system a chance to know they are offline it is still bright. Does not dim. I know we had discuss dimming so it seem that it was defined but not working. 27 Jul, Marjon: Ok. I now see that the color is slightly less bright but no-one will see this as an off line as you likely don't recall the brightness of the color to begin with (difference is very subtle). I suggest we find a better 'dim' indicator, e.g. initial is gray in stead of white.
478 |  | 2018-07-28 |  | -30935 | BETA | Android V2.3, iOS | 4 | location pin can only be shared over radio, not network but no indication in the app so users are confused by it. short term we have to have a pop up warning if they try to share without radio network that it can only be done with radio network. Vise versa when you share map and track we need to tell them network is required. | N | Enh_D1 | Y | p | [7 empty] | Closed | Closed | Yes |  |  |  |  | 31 Jul, XY: costing is required 1 Aug, CS: Only Track and offline maps can be shaerd without radio, since it is sent via cloud. For Location Pin, it would require radio network to be present. So propose to put up Pop Up msg for Location Pin sharing when radio is disconnected. | Needs 1 week after cost lock down.
479 |  | 2018-07-28 |  | -30935 | BETA | Android V2.3, iOS |  | Change the time stamp on the member icon to not have seconds, makes harder to understand what user is looking at and seems silly given the lag of transmission. | N | Enh_PostD1 | N | N | [7 empty] | Open | Open | Yes |  |  |  |  | Jul 27: can be future update.
480 |  | 2018-07-28 | 2018-08-10 | 10 | BETA | Android V2.3, iOS | 3 | Time stamps reflecting updated status even if offline | Y |  | N | Y | [7 empty] | Closed | Closed | Yes |  | Yes | Enhancement |  | What I don't understand is that the time stamp of my location, even though I am off line, is up to date to today? What is the behaviour of the time stamp supposed to be? Should it not reflect the most up to date and latest online status? So user can determine if the location is current and if user is offline when he went offline and where he was. On the other phone it does do that but on one of the phones it shows a recent online status without the radio connected (nor able to send member update to the other radio since that one was not connected either. Please explain. Seems like a bug needing fixing. If so, that bug should be a yes before D2. 31 Jul, XY: fixed in Android V2.4 SK please to confirm if it is fixed in Android 2.4 and for iOS check if this issue is seen. |  | image
481 |  | 2018-07-28 | 2018-08-10 | 10 | BETA | Android V2.3, iOS | 3 | redirect the link for NO T800 yet on the home welcome screen to: shop.motorolasolutions.com/T800 | Y |  | N | Y |  | Open | Open |  |  |  |  | Closed | Closed | Yes |  | Yes | Enhancement |  |  | 2018-08-10
482 | On Boarding | 2018-07-28 | 2018-08-10 | 10 | SK | Android V2.4 | 3 | Pop up Message/Notification different compared to IOS - No data/ internet - No Location service | Y |  | N | Y |  | N/A | Open | [5 empty] | Closed | Yes |  | Yes | Enhancement |  |  | 2018-08-10
483 | Maps | 2018-07-30 | 2018-08-10 | 10 | SK | Android V2.4, iOS | 3 | Location Pin icon displaying in Map not accurate. where the member already off line but icon not in dim colour. | Y |  | N | Y |  | N/A | Open |  |  |  |  | Closed | Closed | Yes |  | Yes | Escape to MSI |  |  | 2018-08-10
484 | Help and Support | 2018-07-31 | 2018-08-10 | 9 | CS | iOS, Android | 4 | Fonts under FAQ and Support need to be standardized using Roboto font | Y |  | N | Y |  | Open | Open |  |  |  |  | Closed | Closed | Yes |  | Yes | Enhancement |  |  | 2018-08-10
485 | Settings | 2018-07-31 |  | -30937 | LeeSun | iOS, Android | 4 | When adding member using non phone number, then you will move to next item which is adding ID. The missing link is the Cursor Bar would be better if it could jump down to Assign Member N/Ame and keyboard pop up after user done with ID number. | N | Enh_D1 | Y | p | [7 empty] | Closed | Closed | Yes | [5 empty] | waiting for costing (around 1.5 weeks effort)
486 | Bluetooth Connection | 2018-07-31 | 2018-08-10 | 9 | SK | Android V2.4 | 2 | Different behavior compare to IOS: -> Andriod - After kill APP, the bluetooth connection will auto connect back directly. -> IOS - After Kill the APP, the bluetooth connection will not connect back until App reopen (bluetooth connection in Radio showing pending to pairing). | Y |  | N | Y |  | N/A | Open |  |  |  |  | N/A | Closed | Yes |  | Yes | Enhancement |  | 31 Jul, XY: need to study further | 2018-08-10
487 | Add Members | 2018-07-31 |  | -30937 | Marjon | iOS, Android | 4 | if you pull from search phone contacts it is very hard to edit (usually delete the country code). Not critical issue but can we improve on ability to edit? | N | Enh_PostD1 | Y | N | [7 empty] | Open | Open | Yes |  |  |  |  | 31 Jul, LeeSun: We could work with Auctus to see if we could change the programming code to define the number as individual rather than block.
488 | Add members | 2018-07-31 |  | -30937 | LeeSun | iOS, Android | 4 | Add one liner below the ID field - "For members signed in without account, ask for their ID. " | N | Enh_D1 | Y | p | [7 empty] | Closed | Closed | Yes | [5 empty] | waiting for costing (around 1.5 weeks effort)
489 | On Boarding | 2018-07-31 |  | -30937 | Marjon | iOS, Android | 4 | Add a tip (last tip during onboarding): MSI will update VI / wireframes and share with Auctus, then Auctus shall add the screen accordingly | N | Enh_D1 | Y | N | [7 empty] | Closed | Closed | Yes |  |  |  |  | 31 July, M": Familiarize yourself with the app! Go to Help and Support menu for FAQ’s and tutorial videos. 31 July, LeeSun: Ok. Will consider and will be added new task for Right Click. Could be additioN/Al cost incured. 10 Aug, CS: please refer to VI doc "TALKABOUT_APP_VI_Design_20180809" slide #9 for new tip page display
490 | On Boarding | 2018-07-31 |  | -30937 | Marjon | iOS, Android | 4 | add tutorial videos (working with GCD team to create, just have to add the links to new section under Help and Support. I suggest to add Tutorials under FAQ and Troubleshooting (between that and Send Feedback). Aucus will just need to update FAQ content with video links when it is ready. | N | Enh_D1 | Y | N | [7 empty] | Closed | Closed | Yes |  |  |  |  | 31 Jul, LS: Tie to #1. Please work with GCD team on required video. Please share your thought on how you would envision this video. 1 Aug, M: I will share with you seperately.
491 | On Boarding | 2018-07-31 |  | -30937 | Marjon | iOS, Android | 4 | Improve on instant explaN/Ation for those things fed back during beta testing with pop up's rather than rely on FAQ's. Ultimately we take all the feedback given during beta testing in to account and try to solve the intuitiveness of the app so not having to lean on pop ups and FAQ's etc. but that will have to be done in phases, some as soon as possible others in new releases. MSI will update VI / wireframes and share with Auctus, then Auctus shall add the screen accordingly | N | Enh_D1 | Y | N | [7 empty] | Closed | Closed | Yes |  |  |  |  | 31 Jul, LS: Frequent pop up could cause annoyance to some user. We need to know what is the percentage of user is having problem with our apps. Did they really read through the tips or they just simply click away? 1 Aug, LS: My guess is the latter . I think it is key to strike a balance. FAQ's and Tips are not that common in apps, people expect it to be intuitive. However if something is really hard, we need to update them in the best possible way. Moderate use of pop ups is ok. 1 Aug CS: To Marjon, for those scene that require pop up messages, please identify in VI slides and poin point which flow require additioN/Al pop up, and spell out the exect message contents. |  |  | exclude this item for costing as it is unclear as of how many pop up messages are needed.
492 | Hamburger Menu | 2018-08-02 | 2018-08-25 | 17 | SK | Android | 3 | the offline maps layout please follow iOS layout. Background color, and no line at the bottom. | Y |  |  |  |  | N/A | Open | [5 empty] | Closed | Yes |  | Yes | Enhancement
493 | Maps | 2018-08-06 | 2018-08-25 | 15 | Marjon | iOS, Android | 2 | I walked out of my house with two phones in my hand. each had different measurement for total ascent: one had 29ft and the other 7 ft. I only walked 0,04 miles so that is a big delta for such a short distance explaining the extremely unrealistic total ascents I had before on my phone. see images of the two tracks.(note they were made with different phones and than shared). | Y | [10 empty] | Closed | Closed | Yes |  | Yes | Escape to MSI | maybe not a issue |  |  | https://drive.google.com/open?id=1Y4k8p1azBMinQVDlN9NcKLffjAiuNPoa
494 | FAQ | 2018-08-06 | 2018-08-25 | 15 | Marjon | iOS, Android | 3 | ​that the wrong icon was shown for emergency alert in the FAQ (they used Bluetooth icon in stead of the danger triangle) | Y | [10 empty] | Closed | Closed | Yes |  | Yes | Enhancement
495 | FAQ | 2018-08-06 | 2018-08-25 | 15 | Marjon | iOS, Android | 3 | ​ I need to press three or four times before it expands (very seldom works immediately). Can we improve that? It is very frustrating and users will think there is no answer. This is bug not enhancement! | Y | [10 empty] | Closed | Closed | Yes |  | Yes | Escape to MSI |  |  |  | https://drive.google.com/open?id=1vCyT_cTpvbntnEVYTmhhbr4mPOpesSkv
496 | Bluetooth Connection | 2018-08-06 | 2018-08-25 | 15 | FT | iOS V1.2(1248) | 2 | APP connected to P1B radio(V03.08), when P2 radoi(V04.02) power on, APP auto connected to P2 radio. And in P1B radio the BT icon still show connected, but actually it is not. APP connected to P2 radio(V04.03), when another P2 radio (V04.04) power on, APP auto connected to 2nd P2 radio. And in 1st P2 radio the BT icon still show connected, but actually it is not. | Y | [10 empty] | Closed | Closed | Yes |  | Yes | Escape to MSI
497 | UI/UX | 2018-08-07 |  | -30942 | LeeSun | iOS, Android | 4 | Offline member icon changed to Grey color, please refer to style guide (MaroonBell Style Guide v1.0 20180806). Blue dot unread message need to be adjusted little higher to besides arrow cursor. | N | Enh_PostD1 | [9 empty] | Open | Open | Yes | [6 empty] | https://drive.google.com/open?id=1U5GUz9E706UPNhTonj5EkFQ6luYz-Jgd
498 | Easy Pairing | 2018-08-14 | 2018-09-26 | 32 | SK | iOS V1.2 (1250), Android V2.6 | 2 | After Easy pairing success displaying correct CH and code in radio, but App try to get into Radio Setting, at the scroll bar still showing previous CH and code. then at this time, the Radio will changed immediately as setting in Radio setting Channel and code. | [11 empty] | Closed | Closed | Yes |  | Yes | Escape to MSI
499 | Easy Pairing | 2018-08-14 | 2018-09-26 | 32 | SK | iOS V1.2 (1250), Android V2.6 | 2 | Sometime after easy paring success, no pop up message indicate, and the countdown timer still displaying. | [11 empty] | Closed | Closed | Yes |  | Yes | Escape to MSI
500 | Maps | 2018-08-14 | 2018-09-26 | 32 | SK | iOS V1.2 (1250) | 3 | Satellite Maps View no street N/Ame. | [11 empty] | Closed | N/A | Yes |  | Yes | Enhancement
501 | Track | 2018-08-14 | 2018-09-26 | 32 | SK | Android V2.6 | 1 | Andriod Tracking no Total Ascent result. | [11 empty] | N/A | Closed | Yes |  | Yes | Escape to MSI
502 | Track | 2018-08-14 | 2018-09-26 | 32 | SK | iOS V1.2 (1250) | 3 | Sometimes when i select the Track (during Track recording) to check the total ascent or mile stone, the Tracking line on map is missing. | [11 empty] | Closed | N/A | Yes |  | Yes | Escape to MSI
503 | Maps | 2018-08-10 | 2018-09-26 | 34 | SK | Android V2.6 | 3 | during track recording, tap on recording icon will bring up statistic window. But after few seconds, it will disappear by itself. Same applied to view icon. (Sumsung A8 - Andriod 7) | [11 empty] | N/A | Closed | Yes |  | Yes | Escape to MSI
504 | Chat | 2018-08-10 | 2018-09-26 | 34 | SK | Android V2.6 | 3 | received message showed time stamp incorrect: where today received message show in time, yesterday or previous received message show in date. | [11 empty] | N/A | Closed | Yes |  | Yes | Escape to MSI
505 | Maps | 2018-08-16 | 2018-09-26 | 30 | CS | Android V2.6, iOS | 3 | Start track recording, and leave the phone idle overnight. Next morning it show accumulative ascent of 1668 ft. Besides, I need to click several times on the "Pause recording" alert message. | [11 empty] | Closed | Closed | Yes |  | Yes | Enhancement
506 | Track | 2018-08-16 | 2018-09-26 | 30 | SK | IOS 1251 | 3 | IOS in Tracking duration is not real-time.. it only starts tickling while I'm on the move. Once I stop moving, the duration timer will stop. experiment compared to Andriod-- Andriod timer will coninue counting even i stop moving (duing track recording). | [11 empty] | Closed | N/A | Yes |  | Yes | Enhancement
507 | On Boarding | 2018-08-17 |  | -30950 | CS | iOS, Android | 4 | Change the word "Account" to "Phone Number", as below: USE WITHOUT PHONE NUMBER If you don't have access to the internet or you don't want to register a phone number, you can proceed without an account linked to your phone number. However, you are not able to share and receive offline maps and saved tracks. | N | Enh_PostD1 | [9 empty] | Open | Open | Yes | [6 empty] | https://drive.google.com/drive/u/0/folders/177bu_0FgZv6yjqzfHfMAsijcDaLHUO8y
508 | Maps | 2018-08-20 | 2018-09-26 | 28 | CS | iOS, Android | 3 | Start track recording, and make sure recording starts. Kill the app and relaunch it. Observe that track recording still continue. Expect to stop recording when app is shut down. | Y | [10 empty] | Closed | Closed | Yes |  | No | Not defect |  | 20 Aug, XY: not an issue, work as designed.
509 | Bluetooth Connection | 2018-08-20 | 2018-09-26 | 28 | CS | iOS, Android | 3 | Still observing Bluetooth disconnect and reconnect intermittent issue | Y | [10 empty] | Closed | Closed | Yes |  | Yes | Escape to MSI
510 | Radio settings | 2018-08-20 | 2018-09-26 | 28 | CS | Android | 3 | change subcode via radio settings in the app. Observe misalignment between app and radio. subcode in app showing 104 but radio is showing 103 | Y | [10 empty] | N/A | Closed | Yes |  | Yes | Escape to MSI |  | 20 Aug, XY: fixing in progress, ETD: 24 Aug
511 | Maps | 2018-08-20 | 2018-09-26 | 28 | CS | iOS, Android | 2 | Sharing geofence, Select few members to share geofence. Most of the time failed to share geofence, either need to retry or after one or two then only able to send successfully. | Y | [10 empty] | Closed | Closed | Yes |  | Yes | Escape to MSI |  | 20 Aug, CS: smoothness of sending geofence need to be seriously looked into. However there is no issue sending individual chat or Shout message.
512 | Maps | 2018-08-27 | 2018-09-26 | 23 | CS | Android (3.0) | 3 | Failed to download offline map in the background. On iOS V1.2(1256) is ok. | [11 empty] | N/A | Closed | Yes |  | Yes | Escape to MSI
513 | Maps | 2018-08-27 | 2018-09-26 | 23 | CS | iOS V1.2(1256) | 3 | iOS has no notification when received track or offline map | [11 empty] | Closed | N/A | Yes |  | Yes | Escape to MSI
514 | Bluetooth Connection | 2018-08-29 | 2018-09-26 | 21 | FT | Android (3.0) | 3 | When press TEST, radio side is delay for few seconds. On iOS is ok. | [11 empty] | N/A | Closed | Yes |  | Yes | Enhancement
515 | Bluetooth Connection | 2018-08-29 | 2018-09-26 | 21 | FT | Android (3.0) | 3 | When press TEST, the TEST is not blink. UI is different from iOS. | [11 empty] | N/A | Closed | Yes |  | Yes | Enhancement |  |  | 2018-09-07
516 | Chat | 2018-08-29 | 2018-09-26 | 21 | FT | iOS V1.2 (1256) | 3 | When phone go to sleep, or when APP put at background, APP will stop sending message. Only SK 's iphone 8 will not stop sending. | [11 empty] | Closed | N/A | Yes |  | Yes | Enhancement
517 | Chat | 2018-08-29 | 2018-09-26 | 21 | FT | iOS V1.2 (1256) | 3 | Sometimes auto response is not sent out. Tested at outdoor. 1 out of 10 times observed radio screen does not show Tx, that means auto response not sent out. Radio SW is V05.03. | [11 empty] | Closed | Closed | Yes |  | Yes | Enhancement |  | Closed in V1.0.2 (1022), V3.2
518 | Chat | 2018-08-30 | 2018-09-26 | 20 | FT | iOS V1.2 (1256) | 3 | When try to scroll up in chat, app keep pull to bottom. Steps to duplicate: 1. APP put to background and let APP receive 5 messages. 2. After 5 messages receive, go into APP and go to chat window. | [11 empty] | Closed | N/A | Yes |  | Yes | Escape to MSI
519 | Maps | 2018-09-03 | 2018-10-01 | 21 | FT | iOS V1.2 (1259) | 3 | Typo on 'stoped'. When Offline map is donwloaded half way. | [11 empty] | Closed | Closed | Yes |  | Yes | Escape to MSI |  |  | 2018-09-07
520 | My Members | 2018-09-06 |  | -30964 | FT | iOS V1.2 (1259) | 3 | User is not able to edit member's ID/phone number from My Members. The only way is to add the member again. | N | Enh_PostD1 | [9 empty] | Open | Open | Yes
521 | Chat | 2018-09-06 | 2018-10-01 | 18 | FT | iOS V1.2 (1259) | 2 | SK created a group with CS and Dennis. After the group is formed, SK invited me to join. I receive and accepted the group invitation. In the group info, I can see my own phone number as 1 of the member, but I cannot see SK. There are 3 members in the group, myself, CS and Dennis. I do not see SK. But I can still receive message from SK in group. In Map view, I choose to view this group and I only able to see CS and Dennis. | [11 empty] | Closed | N/A | Yes |  | Yes | Escape to MSI |  | Closed in V1.2(1261)
522 | Maps | 2018-09-06 | 2018-10-01 | 18 | FT | iOS V1.2 (1259) | 3 | During track recording, I changed map style. After change map style I am not able to zoom in/out or move the map. I have to go to chat then return to map view in order to zoom. Or I have to double tap the map in order to zoom. | [11 empty] | Closed | N/A | Yes |  | Yes | Escape to MSI
523 | Maps | 2018-09-13 | 2018-10-08 | 18 | SK | Andriod V3.2 | 4 | Revert the Share icon in Andriod. | [11 empty] | NA | Closed | Yes |  | Yes | Enhancement
524 |  | 2018-09-13 | 2018-10-08 | 18 | SK | Andriod V3.2 | 3 | Andriod different behavior: App in Menu setting, kept App in phone background, then open App again Andriod - App start up again in Chat page, IOS - Opened and show at Menu Setting. | [11 empty] | NA | Closed | Yes |  | Yes | Enhancement
525 | FAQ | 2018-09-13 | 2018-10-08 | 18 | SK | IOS V1.0.2 (1023), Andriod V3.2 | 4 | remove the sentence “currently shows Bluetooth icon, should be triangle alert icon” in FAQ. | [11 empty] | Closed | Closed | Yes |  | Yes | Enhancement
526 | FAQ | 2018-09-13 | 2018-10-08 | 18 | SK | IOS V1.0.2 (1023), Andriod V3.2 | 4 | Purchase radio link to be add in FAQ, Question to of "Radio" | [11 empty] | Closed | Closed | Yes |  | Yes | Enhancement
527 | FAQ | 2018-09-14 |  | -30970 | CS | IOS V1.0.2 (1023), Andriod V3.2 | 4 | Improve FAQ format. Need to redraw VI |  | Enh_PostD1 | [9 empty] | Closed | Closed | Yes
528 | Chat | 2018-09-14 |  | -30970 | CS | IOS V1.0.2 (1023), Andriod V3.2 | 4 | Show pop up message when there are 3 failed transmission in a row. "The channel may be experiencing interference, or recipient is out of range. Please try different channel or move to different location. For more details please refer to Messaging FAQ." |  | Enh_PostD1 | [9 empty] | Closed | Closed | Yes
529 | Chat | 2018-09-20 |  | -30974 | CS | IOS V1.0.2 (1023), Andriod V3.2 | 4 | Type some words in chat window without sending out. Go to home screen and go in to previous contact again. Observed that text which was entered just now, has been wiped out. |  | Enh_PostD1 | [9 empty] | Open | Open | Yes
530 | Chat | 2018-09-24 | 2018-10-08 | 11 | CS | Android 1034 | 4 | In chat, keep sending at 9 message to invalid receipient. Observed that There are 3 overlapped pop up notifications being put up. Expect to have only 1 pop up. | [11 empty] | Closed | Closed | Yes |  | Yes | Enhancement
531 | Radio Setting | 2018-10-02 | 2018-10-15 | 10 | SK | IOS V1.0.2 (1025), Andriod 1036 | 4 | Language Changing, IOS and Andriod has different reboot behavior. | [11 empty] | Closed | Closed | Yes |  | No | Not defect |  | behave as expected
532 | Radio Setting | 2018-10-02 | 2018-10-15 | 10 | SK | IOS V1.0.2 (1025) | 4 | In English Language, go into Radio Setting, Weather mode, there is a line between Weather Channel Channel and Weather alert, but after chnaged to french, the line is missing. | [11 empty] | Closed | NA | Yes |  | Yes | Escape to MSI
533 | Radio Setting | 2018-10-02 | 2018-10-15 | 10 | SK | Andriod 1036 | 4 | In Radio Setting, Weather mode, the Weather Channel displaying by default? It is different from IOS. | [11 empty] | NA | Closed | Yes |  | Yes | Enhancement
534 | Chat | 2018-10-02 | 2018-10-15 | 10 | SK | IOS V1.0.2 (1025), Andriod 1036 | 4 | Notification for messaging fail to send still in English where the App system already changed in French | [11 empty] | Closed | Closed | Yes |  | No | Not defect
535 | Radio Setting | 2018-10-02 | 2018-10-15 | 10 | SK | Andriod 1036 | 4 | In frence language, Andriod phone showing "DISMISS", IOS showing "EFFACER" | [11 empty] | NA | Closed | Yes |  | Yes | Escape to MSI
536 | Chat | 2018-10-02 | 2018-10-15 | 10 | SK | IOS V1.0.2 (1025), Andriod 1036 | 4 | After Geofence Setting applied/ sent, in Chat mode Language not changed accordingly after setting Language changed. | [11 empty] | Closed | Closed | Yes |  | Yes | Enhancement |  | behave as expected
537 | Radio Setting | 2018-10-03 | 2018-10-15 | 9 | SK | Andriod 1036 | 3 | In easy pairing mode, select member. Once timer counter shows up, press home. Enter Talkabout app again, found that timer counter has disappeared but the timer is still taking effect. Expected behavior: Should show timer counter when re-entering the app, same as how iOS behaves. | [11 empty] | NA | Closed | Yes |  | Yes | Enhancement
Severity Guideline
Sev 1 – Safety related. Major function critically impacted. Radio could not power up / Rx / Tx. Occurrence is >10%.
Sev 2 – Major function is not meeting per requirements. Occurrence is >1%.
Sev 3 – Cosmetic issue. Does not impact major function but is noticeable by customer.
Sev 4 – Minor issue. Not noticeable by customer.
Formulas:
Cycle Time = NETWORKDAYS([Reporting Date],[Date Resolved])
Note on A1: +songkui.wong@motorolasolutions.com SK, for those non enhancement items, need your help to reproduce and verify if they are actual issue? Thanks -Lim Chee Seong Lim
Note on I7: +songkui.wong@motorolasolutions.com please help to verify -Lim Chee Seong Lim
Note on I12: would it happen only during idle time. -Lim Chee Seong Lim
Note on I86: all use Arial? if using this font , then need to provide the font doc. Color need to be double confirmed with LS -Lim Chee Seong Lim +leesun.ooi@motorolasolutions.com all use Arial? if using this font , then need to provide the font doc. Color need to be double confirmed if it is real issue. FT phone is able to reflect correct color. -Lim Chee Seong Lim +leesun.ooi@motorolasolutions.com Kindly do check on this in IOS V1.2 (1247) -SongKui Wong (SYNAPSYS TECHNOLOGY)
Note on AI94: +leesun.ooi@motorolasolutions.com LeeSun, Can you please help to review? -Lim Chee Seong Lim
Note on I121: XY: already followed the latest UI doc, LS pls confirm -Lim Chee Seong Lim +leesun.ooi@motorolasolutions.com XY: already followed the latest UI doc, LS pls confirm -Lim Chee Seong Lim
Note on AI121: +leesun.ooi@motorolasolutions.com LeeSun, Can you please help to review? -Lim Chee Seong Lim
Note on I124: XY will try to change same as Android. If unable to find the picture same as Android, he will get back to MSI. -Lim Chee Seong Lim +leesun.ooi@motorolasolutions.com Kindly do check on this in IOS V1.2 (1247) -SongKui Wong (SYNAPSYS TECHNOLOGY)
Note on I125: +leesun.ooi@motorolasolutions.com Can you help to verify this as well? -Lim Chee Seong Lim
Note on I135: To clarify with LS -Lim Chee Seong Lim +leesun.ooi@motorolasolutions.com LeeSun, can you please verify this? -Lim Chee Seong Lim +leesun.ooi@motorolasolutions.com In latest VI dated 13JUly, i saw there are lines at the last item of the list. please confirm, TQ -Lim Chee Seong Lim
Note on V135: +songkui.wong@motorolasolutions.com SK, can you pls verify this? -Lim Chee Seong Lim
Note on V140: +songkui.wong@motorolasolutions.com SK, can you pls verify this as well? -Lim Chee Seong Lim
Note on AI226: +fooiteng.gan@motorolasolutions.com Have we defined the time spec as of how long radio shall stay idle before poping up the message ? -Lim Chee Seong Lim
Note on I249: To be discussed with TzeLIn -Lim Chee Seong Lim
Note on I269: XY to fix it -Lim Chee Seong Lim
Note on I270: XY to confirm if this has been fixed for Android -Lim Chee Seong Lim
Note on AI270: +songkui.wong@motorolasolutions.com "No need change" means issue can be closed ? -Lim Chee Seong Lim Hi Chee Seong, No need change at the Beta release only.. will see if Beta had feedback this or not.. seen it is not the high sev issue. Thanks SKWong -SongKui Wong (SYNAPSYS TECHNOLOGY)
Note on V281: +songkui.wong@motorolasolutions.com SK, this is still issue in Android right? -Lim Chee Seong Lim
Note on I314: Already explained to SK. SK to confirm if this is still needed. -Lim Chee Seong Lim +songkui.wong@motorolasolutions.com XY already explained to SK. SK to confirm if this is still needed. -Lim Chee Seong Lim +songkui.wong@motorolasolutions.com SK, can you check with XY again, he said already talked to you. -Lim Chee Seong Lim
Note on I317: not source code issue -Lim Chee Seong Lim
Note on I320: XY: not illustrated in VI. LS to confirm -Lim Chee Seong Lim +leesun.ooi@motorolasolutions.com +songkui.wong@motorolasolutions.com XY: not illustrated in VI. LS to confirm. -Lim Chee Seong Lim
Note on I327: XY: need reference from other app how this is shown. At least implement for English at the moment. -Lim Chee Seong Lim +songkui.wong@motorolasolutions.com +cheeseong.lim@motorolasolutions.com I think there is no other way to solve this and current situation is ok for me. SK you have any better idea? -Ft Gan Gan
Note on U337: +songkui.wong@motorolasolutions.com SK, pls confirm that it has been fixed. Tq -Lim Chee Seong Lim actually it is not yet solved in 1240. will try again later in 1241. thanks. -SongKui Wong (SYNAPSYS TECHNOLOGY)
Note on I340: +fooiteng.gan@motorolasolutions.com XY said this has been reflected based on latest UI, please confirm. -Lim Chee Seong Lim
Note on I341: +fooiteng.gan@motorolasolutions.com Need to confirm this one as well. -Lim Chee Seong Lim +songkui.wong@motorolasolutions.com please check is this close -Ft Gan Gan +fooiteng.gan@motorolasolutions.com Not fix in IOS V1.2 (1248)-XY: new feature ,will not support -SongKui Wong (SYNAPSYS TECHNOLOGY)
Note on I344: Need to update UI doc to reflect this. -Lim Chee Seong Lim TALKABOUT_APP_VI_Design_20180620 page 10 already updated with this requirement. Already sent to Auctus and you on 20-Jun-18. -Ft Gan Gan
Note on I352: +songkui.wong@motorolasolutions.com originally, A and B are at same location is it ? -Lim Chee Seong Lim Yes, A and B at the same location originally. -SongKui Wong (SYNAPSYS TECHNOLOGY)
Note on I355: +fooiteng.gan@motorolasolutions.com I could not reproduce the issue in Iphone and Android phone -Lim Chee Seong Lim
Note on I371: XY to fix it -Lim Chee Seong Lim
Note on I372: +leesun.ooi@motorolasolutions.com Already implemented based on VI, please verify -Lim Chee Seong Lim +cheeseong.lim@motorolasolutions.com we haven't received latest IOS version for this fix.. now we have is 1244 which still having the problem. Kindly check which is the version fixed. Thanks. -SongKui Wong (SYNAPSYS TECHNOLOGY) +leesun.ooi@motorolasolutions.com Please do review in Latest App IOS 1.2.48 -SongKui Wong (SYNAPSYS TECHNOLOGY)
Note on I375: SK to confirm -Lim Chee Seong Lim
Note on I376: +songkui.wong@motorolasolutions.com already fixed, please confirm -Lim Chee Seong Lim
Note on I377: XY: should be Google play store issue -Lim Chee Seong Lim
Note on I379: XY to confirm this issue -Lim Chee Seong Lim
Note on I380: not shown in VI doc -Lim Chee Seong Lim +cheeseong.lim@motorolasolutions.com ask Lee Sun help to update VI slide#40 and #80. -Ft Gan Gan +fooiteng.gan@motorolasolutions.com +leesun.ooi@motorolasolutions.com XY commented This is not shown in VI, thus it is implemented as it is. -Lim Chee Seong Lim +cheeseong.lim@motorolasolutions.com yes it is not in existing VI thats why I said need Lee Sun to update VI to add it in. Then we can ask Auctus to add in. -Ft Gan Gan +leesun.ooi@motorolasolutions.com LeeSun, can you please update VI doc to reflect this ? Thanks -Lim Chee Seong Lim To flw up with LS -Lim Chee Seong Lim
Note on U380: duplicated to #319 -Lim Chee Seong Lim +cheeseong.lim@motorolasolutions.com same issue to 319 -SongKui Wong (SYNAPSYS TECHNOLOGY)
Note on I382: XY: this is same as iOS. -Lim Chee Seong Lim
Note on I383: CS to reconfirm -Lim Chee Seong Lim
Note on I384: +songkui.wong@motorolasolutions.com please explain to XY -Lim Chee Seong Lim
Note on I385: +songkui.wong@motorolasolutions.com already fixed, please verify -Lim Chee Seong Lim
Note on I386: XY to fix it -Lim Chee Seong Lim +songkui.wong@motorolasolutions.com Sk, please verify if this has been fixed -Lim Chee Seong Lim now i only have 1 radio with phone number registered.. cannot check Andriod to Andriod... but just Check bwtween 2 OS has problem whwere the total Ascent showing 0... XY tell me that IOS need to update also regarding this issue. -SongKui Wong (SYNAPSYS TECHNOLOGY) XY replied Andriod to Andriod solved. -SongKui Wong (SYNAPSYS TECHNOLOGY)
Note on I387: XY: should be google play store issue -Lim Chee Seong Lim
Note on I388: +songkui.wong@motorolasolutions.com should be fixed. -Lim Chee Seong Lim +cheeseong.lim@motorolasolutions.com Hi CheeSeong, Weather Channel can select, but cannot enable the Weather Alert. -SongKui Wong (SYNAPSYS TECHNOLOGY)
Note on I389: XY: will be fixed later -Lim Chee Seong Lim
Note on I391: +songkui.wong@motorolasolutions.com Please confirm this is Resolved ? -Lim Chee Seong Lim
Note on AB393: +marjon.manitius@motorolasolutions.com updated my comment. -Lim Chee Seong Lim ok, agree that current implimentation is ok and to leave. I did notice in verifying that after I unpaired and tried to pair again to same radio, first attempt failed. Only following attempt was successful. tried a few more times and it was fine on first try. Just showing that it is not always working smoothly..... -Marjon Manitius
Note on I394: +fooiteng.gan@motorolasolutions.com This is because the Track/ Offline Map sent in Server which can kept for 3 month. So after sent, the sender side will diplayed with TICK as sent. SAME in IOS. please inform Marjon. -SongKui Wong (SYNAPSYS TECHNOLOGY) +songkui.wong@motorolasolutions.com +cheeseong.lim@motorolasolutions.com If I remember correctly Chee Seong told me this can be fix but need 3 weeks time (same feedback from Marjon on iOS) Chee Seong can you confirm? I cannot find that issue capture in this list. -Ft Gan Gan
Note on I396: Duplicated to issue #370 -Lim Chee Seong Lim
Note on I405: XY to verify if issue happen in cross OS between iOS and Android -Lim Chee Seong Lim
Note on V407: +songkui.wong@motorolasolutions.com Do we still see this issue? -Lim Chee Seong Lim not happen in Andriod V2.4 so far -SongKui Wong (SYNAPSYS TECHNOLOGY)
Note on I408: +songkui.wong@motorolasolutions.com to verify -Lim Chee Seong Lim To be verify in V2.3 -SongKui Wong (SYNAPSYS TECHNOLOGY)
Note on I411: +songkui.wong@motorolasolutions.com please verify -Lim Chee Seong Lim to be verify in V2.3 -SongKui Wong (SYNAPSYS TECHNOLOGY)
Note on I412: Radio BT will stay even radio is in idle mode. But if radio BT connection is lost, after certain duration, BT will be shut down. -Lim Chee Seong Lim
Note on I414: This shd be radio fw issue, flw up with ZhuYong -Lim Chee Seong Lim
Note on I415: XY: Could be due to connection lost issue -Lim Chee Seong Lim
Note on I416: need to get more info from Marjon -Lim Chee Seong Lim
Note on I417: This is an enhancement feedback, need to detail out how to implement in App. -Lim Chee Seong Lim
Note on I418: XY to verify for iOS share icon, try to make it standardize. -Lim Chee Seong Lim +leesun.ooi@motorolasolutions.com Do you agree to change the share icon to iOS standard share icon ? -Lim Chee Seong Lim
Note on I419: SK: Same as issue #351, XY is fixing. -Lim Chee Seong Lim
Note on AB420: +marjon.manitius@motorolasolutions.com Marjon, can You please where is the exact location point you observed this issue ? We could not replicate the issue here. -Lim Chee Seong Lim it was a pin in Italy. I still have the pin. can I share with you if I add you as member over the internet? what is your phone number. -Marjon Manitius +60174631217 -Lim Chee Seong Lim Hi CS, I lost all the data I had when I reinstalled the app to record screen flashing. sorry. -Marjon Manitius PS just shared a map with you. I was not able to share between two iphones today so checking with you if you are receiving. -Marjon Manitius +marjon.manitius@motorolasolutions.com you have shared to my hp ? in which app? watsapp or wechat? I have not received it. please share again, Thanks. -Lim Chee Seong Lim perhaps you can just let me know the location / region name. Then i will feedback to Mapbox. It has nothing to do with Talkabout App as the map data rendering is provided by Mapbox. -Lim Chee Seong Lim _Marked as resolved_ -Marjon Manitius _Re-opened_ I have res-hared a map with you since you said you nrver received the original one. I hope you get it. -Marjon Manitius map name is : My neighborhood. My phone number if you want something back: +16785759181 -Marjon Manitius i Got it Thanks -Lim Chee Seong Lim
Note on I421: This could be due to hill signal lost. XY to reconfirm. -Lim Chee Seong Lim
Note on I422: Should be same root cause as issue #420. XY to confirm -Lim Chee Seong Lim +songkui.wong@motorolasolutions.com please confirm if this has been resolved in both Android and iOS. Thanks -Lim Chee Seong Lim
Note on AB422: +fooiteng.gan@motorolasolutions.com item needs your attention -Lim Chee Seong Lim
Note on I423: XY: can be implemented. -Lim Chee Seong Lim
Note on I424: This is new proposal, need to define detailed implementation. -Lim Chee Seong Lim
Note on I425: SK to help confirm this issue. -Lim Chee Seong Lim SK: is it saved location pin or just the location pin opened in chat mode ? -Lim Chee Seong Lim
Note on V426: +songkui.wong@motorolasolutions.com fixed already ? -Lim Chee Seong Lim
Note on I444: +songkui.wong@motorolasolutions.com what do you understand by blue dot not centered ? -Lim Chee Seong Lim
Note on AB473: +marjon.manitius@motorolasolutions.com I compared with GAIA, the app is also showing increment in ascent when going down hill. request to share out the track file. my maps => my tracks =>click share icon => export by email or others -Lim Chee Seong Lim not sure what you mean. regardless total ascent should only add up the uphill. -Marjon Manitius
Note on AB477: +marjon.manitius@motorolasolutions.com +songkui.wong@motorolasolutions.com +fooiteng.gan@motorolasolutions.com We turned on airplance mode in both iPhone and Android phones, the track recording is able to plot the track line real-time. Even toggle airplane mode in between, there is no impact to the track recording. Was your phone gps turned on during the recording? shall I close this issue for now? -Lim Chee Seong Lim
Note on AB481: +marjon.manitius@motorolasolutions.com The moment app goes offline, it will send out the last timestamp update to other member's app, thus you will notice there is timestamp updates reflected. However, once the app is gone / killed, there is No way for it to send out any timestamp updates to member's radio, since it is not present. We've also tried to just turned off the radio but leave the app stay on, observed that the icon will not dim in member's app. This is because when we turn off the radio only, the app is not able to send out offline notification to rx radio. That's explained why icon is not dim. So, is this still an issue? -Lim Chee Seong Lim
Note on AB492: +marjon.manitius@motorolasolutions.com Marjon, for those scenes that require pop up messages, please identify in VI slides and point out which flow require additional pop up, and spell out the exact message contents. -Lim Chee Seong Lim
Note on V513: +cheeseong.lim@motorolasolutions.com can u check on this? _Assigned to Lim Chee Seong Lim_ -Ft Gan Gan
Note on U514: +cheeseong.lim@motorolasolutions.com pls check is this close _Assigned to Lim Chee Seong Lim_ -Ft Gan Gan
Note on V516: +cheeseong.lim@motorolasolutions.com pls check is this close -Ft Gan Gan
Note on U520: +cheeseong.lim@motorolasolutions.com pls check is this close _Assigned to Lim Chee Seong Lim_ -Ft Gan Gan

## Enh_D1 (hidden)
No | Area | Reporting Date | Reported By | Observed Point | Severity | Issue | Required To Fix by 20-Sep-18 | Enhancement | ID Team | Green Light | Convert to test case | Closed version | Status IOS | Status Andriod | comment | Planned Close Date | Links | Next To Do | Estimation | reply comment | 工作量 | APP feedback (XiangYang) 7 June 2018 | Feedback SK (8 June 2018)(1235) | Feedback SK (13 June 2018)(1236) | Feedback SK (16 June 2018)(1237) | Feedback SK (17 June 2018)(1238) | Android 1.9 3 July | Android 2.0 4 July | Android 2.2 7 July | Android 2.4 24 July
120 | Radio Settings | 2018-02-20 | LS | iOS V1.1(20), Android V2.3 | 3 | The Channel, Sub Code & Call Tone scroll bar is hard to know what is the upper and lower limit. May need N/A to suggest | Yes | Y | N | P | N |  | Closed | Closed | Still not correct 6/29 4 Jul, XY: XY: already followed the latest UI doc, LS pls confirm 18 jul, XY: new feature , will not support 24 Jul, FT: we have feedback this on 20-Feb-18 together with ID feedback file (see attached slide#18). You should not come back now saying you will not fix it. 26 Jul, XY: Denied and come back that this is Enh 31 Jul, XY: APP independent, not related to radio SW. 1 Aug CS: This should not considered as Enhget email from LeeSun on the evidence. Please refer to links for email evidences. | needs 2 weeks after cost is locked down | https://drive.google.com/open?id=1MlZzceu4eNHeSXCuLgQlgm_RB7sBmjJk |  | medium | 这一项，之前已经反复跟设计公司的反复确认过，设计公司也确认就是这样做。邮件为证。 后续这个部分设计公司并没有更新文档。遇到冲突，我们只能以 TALKABOUT_APP_VI_Design TALKABOUT_APP_Wireframes 为准。 comment 提到的文档UI APPS Feedback IOS V1.1 (20) 20180220.pptx 这个文档只能作为moto跟设计公司讨论的初稿，并不能作为我们开发的依据，因为这个文档跟最终设计本来就很多不一样。如第8页 slider bar。 | android 1 week , iOS 1 week, test 0.5week, document 0.2week | This situation is defined in the radio document | LS will review
345 | Hamburger Menu | 2018-06-20 | Marjon | iOS V1.2 (1238) | 3 | File N/Ame cannot be seen in full. Please change to 2 rows. | Yes | Y | N | P | Y | V1.0.2 (1023), V3.2 | CLosed | Closed | Still same in 1240 Still same in 1243 18 jul, XY: new feature ,will not support 24 Jul, FT: the file N/Ame cannot seen in full and we only request to change to 2 lines. This is solving issue to eN/Able user can see the file N/Ame. 26 Jul, CS: Denied and come back that this is Enh | needs 1 week after cost is locked down |  |  | easy |  | android 0.25 week , iOS 0.25week, test 0.25week, document 0.05week
417 | Maps | 2018-07-06 | BETA | Android, iOS 1244 | 3 | Maps sharing: share icon on my maps uses not the standard share icon for IOS users (box with arrow out) forgot conclusion of this, but believe was discussed before. | Yes | Y | N | Y |  | 1259 | Closed | NA | not understand 10 Jul, CS: will standardize the icon 18 jul, XY: fixed 1.2 47 18 Jul, CS: icon still not the box with arrow out 26 Jul, XY, This is new feature , not reflecetd in latest VI 26 Jul, Marjon: UI no tclearly defined, Has to be updated to iOS N/Ative icon 30 Jul, Auctus: 未跟客户收费 | 2018-08-03 |  |  | easy
430 | Maps | 2018-07-17 | BETA | iOS, Android | 3 | Change the View icon in Maps (second icon at right side) to Group Member icon. | Yes | Y | N | P |  | V1.0.2, V3.2 | Closed | Closed | 17, Jul,XY: new feature, not supported 26 Jul, Marjon: Has to be fixed by D2 1 Aug, CS: This is not captured in the SRS or VI previously 10 Aug, CS: refer to TALKABOUT_APP_VI_Design_20180809 | needs 1 week after cost is locked down | VI doc uploaded at Baidu app > VI & Wireframes |  | easy |  | android 0.25 week , iOS 0.25week, test 0.25week, document 0.05week
438 | maps | 2018-07-26 | BETA | Android V2.3 | 4 | Difficulty with understanding on how to download maps, Add a tip about where to find help Include education tip as last tip in onboarding: Familiarize yourself with the app! Go to Help menu for FAQ’s and tutorial videos. | Yes | Y | Y | P |  | V1.0.2 (1023), V3.2 | CLosed | CLosed | 26 Jul, CS: This is user familiarity issue. Adding note to FAQ? Jul 27:MM. This is crucial to ensure users accept the app as useful. I will send seperate email to Lee Sun asking her to work on this. 1 Aug, LiN/Ar: we will ask SiauFong to ask Auctus provide quotation based on one paragraph and 5 icons in FAQ 10 Aug, CS: refer to TALKABOUT_APP_VI_Design_20180809 | After cost and UI lock down, need 1.5 weeks | VI doc uploaded at Baidu app > VI & Wireframes |  | easy
445 | Members | 2018-07-26 | BETA | Android V2.3, iOS | 4 | Sections not understood: What is a group | Yes | Y | N | N |  | V1.0.2 (1023), V3.2 | CLosed | CLosed | 26 Jul, CS: This is user familiarity issue. Adding note to FAQ? If yes, then FAQ contents MUST be locked down before 3-Aug-18 10 Aug, CS: Refer to App Content V2.1 |  | Uploaded at Baidu app > App Content |  | easy
446 | Members | 2018-07-26 | BETA | Android V2.3, iOS | 4 | Sections not understood: What is a member | Yes | Y | N | N |  | V1.0.2 (1023), V3.2 | CLosed | CLosed | 26 Jul, CS: This is user familiarity issue. Adding note to FAQ? If yes, then FAQ contents MUST be locked down before 3-Aug-18 10 Aug, CS: Refer to App Content V2.1 |  | Uploaded at Baidu app > App Content |  | easy
447 | Maps | 2018-07-26 | BETA | Android V2.3, iOS | 4 | Sections not understood: What is a geofence | Yes | Y | N | N |  | V1.0.2 (1023), V3.2 | CLosed | CLosed | 26 Jul, CS:: This is user familiarity issue. Adding note to FAQ? If yes, then FAQ contents MUST be locked down before 3-Aug-18 10 Aug, CS: Refer to App Content V2.1 |  | Uploaded at Baidu app > App Content |  | easy
448 | Maps | 2018-07-26 | BETA | Android V2.3, iOS | 4 | Sections not understood: How to download a map | Yes | Y | N | N |  | V1.0.2 (1023), V3.2 | CLosed | CLosed | 26 Jul, CS:: This is user familiarity issue. Adding note to FAQ? If yes, then FAQ contents MUST be locked down before 3-Aug-18 10 Aug, CS: Refer to App Content V2.1 |  | Uploaded at Baidu app > App Content |  | easy
449 | Maps | 2018-07-26 | BETA | Android V2.3, iOS | 4 | Sections not understood: How to reN/Ame tracks, maps, pins | Yes | Y | N | N |  | V1.0.2 (1023), V3.2 | CLosed | CLosed | 26 Jul, CS:: This is user familiarity issue. Adding note to FAQ? If yes, then FAQ contents MUST be locked down before 3-Aug-18 10 Aug, CS: Refer to App Content V2.1 |  | Uploaded at Baidu app > App Content |  | easy
450 | Menu /N/Avigation | 2018-07-26 | BETA | Android V2.3, iOS | 4 | Sections not understood: Multiple users indicated not to be able to figure out how to get back to chat menu | Yes | Y | N | N |  | V1.0.2 (1023), V3.2 | CLosed | CLosed | 26 Jul, CS:: This is user familiarity issue. Adding note to FAQ? If yes, then FAQ contents MUST be locked down before 3-Aug-18 10 Aug, CS: Refer to App Content V2.1 |  | Uploaded at Baidu app > App Content |  | easy
451 | Maps | 2018-07-26 | BETA | Android V2.3, iOS | 4 | Sections not understood: total ascent (how it is calculated) | Yes | Y | N | N |  | V1.0.2 (1023), V3.2 | CLosed | CLosed | 26 Jul, CS: This is user familiarity issue. Adding note to FAQ? If yes, then FAQ contents MUST be locked down before 3-Aug-18 10 Aug, CS: Refer to App Content V2.1 |  | Uploaded at Baidu app > App Content |  | easy
452 | Maps | 2018-07-26 | BETA | Android V2.3, iOS | 4 | Sections not understood: how to view the statistics (requires clicking on the icon) but not intuitive | Yes | Y | N | N |  | V1.0.2 (1023), V3.2 | CLosed | CLosed | 26 Jul, CS: This is user familiarity issue. Adding note to FAQ? If yes, then FAQ contents MUST be locked down before 3-Aug-18 10 Aug, CS: Refer to App Content V2.1 |  | Uploaded at Baidu app > App Content |  | easy
453 | Maps | 2018-07-26 | BETA | Android V2.3, iOS | 4 | Sections not understood: who receives my location when I tap on locate icon | Yes | Y | N | N |  | V1.0.2 (1023), V3.2 | CLosed | CLosed | 26 Jul, CS: This is user familiarity issue. Adding note to FAQ? If yes, then FAQ contents MUST be locked down before 3-Aug-18 10 Aug, CS: Refer to App Content V2.1 |  | Uploaded at Baidu app > App Content |  | easy
454 | Maps | 2018-07-26 | BETA | Android V2.3, iOS | 4 | Sections not understood: icon of offline map and track is confusing | Yes | Y | N | N |  | V1.0.2 (1023), V3.2 | CLosed | CLosed | 26 Jul, CS: This is user familiarity issue. Adding note to FAQ? If yes, then FAQ contents MUST be locked down before 3-Aug-18 10 Aug, CS: Refer to App Content V2.1 |  | Uploaded at Baidu app > App Content |  | easy
455 | Maps | 2018-07-26 | BETA | Android V2.3, iOS | 4 | Sections not understood: why are offline map and track features not available | Yes | Y | N | N |  | V1.0.2 (1023), V3.2 | CLosed | CLosed | 26 Jul, CS: This is user familiarity issue. Adding note to FAQ? If yes, then FAQ contents MUST be locked down before 3-Aug-18 |  | Uploaded at Baidu app > App Content |  | easy
456 | Maps | 2018-07-26 | BETA | Android V2.3, iOS | 4 | Sections not understood: why they can not send an off line map off grid | Yes | Y | N | N |  | V1.0.2 (1023), V3.2 | CLosed | CLosed | 26 Jul, CS: This is user familiarity issue. Adding note to FAQ? If yes, then FAQ contents MUST be locked down before 3-Aug-18 10 Aug, CS: Refer to App Content V2.1 |  | Uploaded at Baidu app > App Content |  | easy
469 |  | 2018-07-26 | BETA | Android V2.3, iOS | 3 | very unclear to various users what using an ID means. Various users tried to send messages using a phone number to users that chose to set up their account with an ID. The fact that that is not possible is not understood. some also wanted to type a N/Ame in field using ID and where frustrated that only the number keyboard comes up. They confused using ID with User ID or user N/Ame. At the very least we need to improve on the ADD NEW MEMBER screen to make it clear what using a phone number or using ID means (using ID is the account ID assigned to the user during set up) Also assign member N/Ame is not clear how that relates to the two above. This seems to be stumbling block for some of the beta users and they think it is not working whereas it is more an issue of not understanding the app. UI team needs to make proposal on how to make this more intuitive. | Yes | Y | Y | N |  |  | Closed | Closed | 26 Jul, CS: This is user familiarity issue. Adding note to FAQ? If yes, then FAQ contents MUST be locked down before 3-Aug-18 Otherwise, need to redefine a new VI to cater for new appearance. 27 Jul, mm: this is big issue for multiple beta testers. adding to FAQ will not solve. Need to redesign the adding member screen and also add wording when setting up the account. Will send email to Lee Sun 31 Jul, CS: breakdowns of these items are shown in #444, 485 and 487 to 491 10 Aug, CS: refer to TALKABOUT_APP_VI_Design_20180809 |  | VI doc uploaded at Baidu app > VI & Wireframes |  | easy
478 |  | 2018-07-28 | BETA | Android V2.3, iOS | 4 | location pin can only be shared over radio, not network but no indication in the app so users are confused by it. short term we have to have a pop up warning if they try to share without radio network that it can only be done with radio network. Vise versa when you share map and track we need to tell them network is required. | Yes | Y | Y | p |  | V1.0.2 (1023), V3.2 | Closed | Closed | 31 Jul, XY: costing is required 1 Aug, CS: Only Track and offline maps can be shaerd without radio, since it is sent via cloud. For Location Pin, it would require radio network to be present. So propose to put up Pop Up msg for Location Pin sharing when radio is disconnected. 10 Aug: If user trying to share Location Pin without connecting to BT, show a pop up message " Feature available over radio network; pair phone to Talkabout radio in order to proceed and transmit to other radio/phone.". If user trying to share maps and tracks without wifi or mobile data, show a pop up message "Feature available over internet; turn on wifi or mobile data to proceed with sharing." | Needs 1 week after cost lock down. |  |  | easy
485 | Settings | 2018-07-31 | LeeSun | iOS, Android | 4 | When adding member using non phone number, then you will move to next item which is adding ID. The missing link is the Cursor Bar would be better if it could jump down to Assign Member N/Ame and keyboard pop up after user done with ID number. | Yes | Y | Y | p |  | V1.0.2 (1023) Andriod 1034 | Closed | Closed |  | waiting for costing (around 1.5 weeks effort) |  |  | medium
488 | Add members | 2018-07-31 | LeeSun | iOS, Android | 4 | Add one liner below the ID field - "For members signed in without account, ask for their ID. " | Yes | Y | Y | p |  | V1.0.2 (1023), V3.2 | Closed | Closed | 10 Aug, CS: refer to TALKABOUT_APP_VI_Design_20180809 | waiting for costing (around 1.5 weeks effort) | VI doc uploaded at Baidu app > VI & Wireframes |  | easy
489 | On Boarding | 2018-07-31 | Marjon | iOS, Android | 4 | Add a tip (last tip during onboarding): MSI will update VI / wireframes and share with Auctus, then Auctus shall add the screen accordingly | Yes | Y | Y | N |  | V1.0.2 (1023), V3.2 | Closed | Closed | 31 July, M": Familiarize yourself with the app! Go to Help and Support menu for FAQ’s and tutorial videos. 31 July, LeeSun: Ok. Will consider and will be added new task for Right Click. Could be additioN/Al cost incured. 10 Aug, CS: please refer to VI doc "TALKABOUT_APP_VI_Design_20180809" slide #9 for new tip page display |  | https://drive.google.com/open?id=1drrvQ3aqZcJu_CNg75BKwMnw7_afovAl VI doc uploaded at Baidu app > VI & Wireframes |  | easy
490 | On Boarding | 2018-07-31 | Marjon | iOS, Android | 4 | add tutorial videos (working with GCD team to create, just have to add the links to new section under Help and Support. I suggest to add Tutorials under FAQ and Troubleshooting (between that and Send Feedback). Aucus will just need to update FAQ content with video links when it is ready. | Yes | Y | Y | N |  | V1.0.2 (1023), V3.2 | Closed | Closed | 31 Jul, LS: Tie to #1. Please work with GCD team on required video. Please share your thought on how you would envision this video. 1 Aug, M: I will share with you seperately. 10 Aug, CS: Video Tutorials should go under HELP and Support. (before FAQ). See the App Content doc V2.1 (Uploaded at Baidu app > App Content) |  | Uploaded at Baidu app > App Content |  | easy
491 | On Boarding | 2018-07-31 | Marjon | iOS, Android | 4 | Improve on instant explaN/Ation for those things fed back during beta testing with pop up's rather than rely on FAQ's. Ultimately we take all the feedback given during beta testing in to account and try to solve the intuitiveness of the app so not having to lean on pop ups and FAQ's etc. but that will have to be done in phases, some as soon as possible others in new releases. MSI will update VI / wireframes and share with Auctus, then Auctus shall add the screen accordingly | Yes | Y | Y | N |  |  | Open | Open | 31 Jul, LS: Frequent pop up could cause annoyance to some user. We need to know what is the percentage of user is having problem with our apps. Did they really read through the tips or they just simply click away? 1 Aug, LS: My guess is the latter . I think it is key to strike a balance. FAQ's and Tips are not that common in apps, people expect it to be intuitive. However if something is really hard, we need to update them in the best possible way. Moderate use of pop ups is ok. 1 Aug CS: To Marjon, for those scene that require pop up messages, please identify in VI slides and poin point which flow require additioN/Al pop up, and spell out the exect message contents. | waiting for costing |  | exclude this item for costing as it is unclear as of how many pop up messages are needed. | medium
507 | On Boarding | 2018-08-17 | CS | iOS, Android | 4 | Change the word "Account" to "Phone Number", as below: USE WITHOUT PHONE NUMBER If you don't have access to the internet or you don't want to register a phone number, you can proceed without an account linked to your phone number. However, you are not able to share and receive offline maps and saved tracks. | N | Y | Y |  |  | Y | Closed | Closed | [7 empty] | https://drive.google.com/drive/u/0/folders/177bu_0FgZv6yjqzfHfMAsijcDaLHUO8y
527 | FAQ | 2018-09-14 | CS | IOS V1.0.2 (1023), Andriod V3.2 | 4 | Improve FAQ format. Need to redraw VI | N | Y | Y |  |  |  | Closed | Closed
528 | Chat | 2018-09-14 | CS | IOS V1.0.2 (1023), Andriod V3.2 | 4 | Show pop up message when there are 3 failed transmission in a row. "The channel may be experiencing interference, or recipient is out of range. Please try different channel or move to different location. For more details please refer to Messaging FAQ." | N | Y | N |  |  |  | Closed | Closed
iOS
| Severity | iOS | Unresolved | Resolved
| 1 | 0 | 0 | 0
| 2 | 0 | 0 | 0
| 3 | 5 | 0 | 5
| 4 | 21 | 1 | 21
| TOTAL | 26 | 1 | 26
Android
| Severity | Android | Unresolved | Resolved
| 1 | 0 | 0 | 0
| 2 | 0 | 0 | 0
| 3 | 3 | 0 | 1
| 4 | 20 | 1 | 16
| TOTAL | 23 | 1 | 17
Note on P20: +marjon.manitius@motorolasolutions.com +fooiteng.gan@motorolasolutions.com +leesun.ooi@motorolasolutions.com please see if these pop up messages are OK -> If user trying to share Location Pin without connecting to BT, show a pop up message " Connect to radio Bluetooth". If user trying to share maps and tracks without wifi or mobile data, show a pop up message "Turn on wifi or mobile data to proceed" -Lim Chee Seong Lim Not sure if Connect to radio Bluetooth is understood. Are we limited in space /characters for a pop up? If we can, we should try to explain better. A visual of phone /radio to other radio/phone same as used on packaging is best but otherwise in words. Feature available over radio network; pair phone to Talkabout radio in order to proceed and transmit to other radio/phone. -Marjon Manitius +marjon.manitius@motorolasolutions.com, +fooiteng.gan@motorolasolutions.com, +leesun.ooi@motorolasolutions.com Marjon, please see latest correction below: If user trying to share Location Pin without connecting to BT, show a pop up message " Feature available over radio network; pair phone to Talkabout radio in order to proceed and transmit to other radio/phone.". If user trying to share maps and tracks without wifi or mobile data, show a pop up message "Feature available over internet; turn on wifi or mobile data to proceed with sharing." Please confirm. Thanks -Lim Chee Seong Lim +marjon.manitius@motorolasolutions.com please verify it. -Lim Chee Seong Lim yes, this is good. Please proceed. -Marjon Manitius
Note on P25: +marjon.manitius@motorolasolutions.com Marjon, has the number of pop ups been finalized? we need to identify where to show and define the messages before we trigger for French translation. Thanks! -Lim Chee Seong Lim +marjon.manitius@motorolasolutions.com Do provide your comment on this. -Lim Chee Seong Lim other than the ones we have been working on, I will not add more for now. If more are needed will be in the post D1 phase. -Marjon Manitius

## Defects_D2 (hidden)
No | Area | Reporting Date | Reported By | Observed Point | Severity | Issue | Root Cause | Resolution details | Impacted Features | Test execution time | Breakage | Required To Fix by D2 (20-Aug-18) | Enhancement | ID Team | Green Light | Convert to test case | Status IOS | Status Andriod | Closed Version | comment | Planned Close Date | Links | Next To Do | reply comment | 工作量 | APP feedback (XiangYang) 7 June 2018 | Feedback SK (8 June 2018)(1235) | Feedback SK (13 June 2018)(1236) | Feedback SK (16 June 2018)(1237) | Feedback SK (17 June 2018)(1238) | Android 1.9 3 July | Android 2.0 4 July | Android 2.2 7 July | Android 2.4 24 July
124 | On Boarding | 2018-02-21 | LS | Android V1.4(20) | 3 | Term and Conditions - the background color is wrong. The last sentence will blink when I tap. It should not be. If we just want the user to tap AGREE button. | UI color error | Change the last sentence into plain text | Display of the boarding page |  |  | Yes | N | N | Y |  | N/A | Closed | 2.6 | LS to review 26 Jul, CS: Android still showing greyish, requested Auctus to change color. Please change the DECLINE button background color to be same as Terms and condition background color. 26 Jul, CS: was not fixed yet. Please change "DECLINE" button background color to be same as Terms and Conditions background color.​ 31 Jul, XY: APP independent, not related to radio SW. | 2018-08-10
225 | Maps | 2018-02-27 | Marjon | iOS V1.1(20), Android V1.4(20) | 3 | My Maps --> My Tracks --> for track recording can we alert user if they have not moved for a while? E.g. Would you like to pause recording? | New requirement | The application will pop up a alert dialog if user have not moved for 5 minutes. | Record track | OK |  | Yes | N | N | Y | N | Closed | Closed | 1250 | 5/31/2018 How long will the App pop up the message? i stayed at the same place for around 10 mins, but still no message pop up. 12 Jul, CS: are we fine to set to 10 mins? 18 jul, XY: new feature ,will not support 24 Jul, FT: we also shared as early as 27-Feb-18. How can you say is new request? 24 Jul, XY: agree to fix without additioN/Al cost. 31 Jul, XY: APP independent, not related to radio SW. 16 Aug, XY: Android to be ready by 24 Aug | iOS: 3-Aug-18 Android: 10-Aug-18 |  |  | SK: Alert appeared (Andriod).. but user cannot cancel? if he want to continue the recording? Also, if i click "OK", the recoring not stop?? i seen like it still in recording. (fixed in IOS 1251, Andriod V2.8) |  | This is new demand | no pop up message. | pop up message every 10mins if no movement. | pop up message every 10mins if no movement.
321 | Hamburger Menu | 2018-06-14 | SK | iOS V1.2 (1236), Android | 3 | in FAQ the icons are not added in but instead shows my text e.g. (show icon of hamburger menu) | No icons were provided | use the corresponding icon to replace | Display of the boarding page | OK |  | Yes | N | N | Y |  | Closed | Closed | 1250, 2.6 | 24 Jul, CS: this was not fixed properly. Hence this issue is re-opened. 14 Aug, CS: Need to standardize BT icon image fixed in IOS 1251, Andriod V2.7 | 2018-08-03
389 | Chat | 2018-07-03 | SK | Android V1.9 | 3 | Different behavior compare to IOS: -> added a new member, now tab to chat with him... but i did't type any message, just back to chat home page, i cannot see the new added member N/Ame display at Chat Home Page, but IOS has. | Ambiguous requirement | Add a talk item, and display at chat home page | Display of the chat home page | OK |  | Yes | N | N | Y |  | N/A | Closed | 1250, 2.6 | Andriod 2.6 | 2018-08-03
428 | Settings | 2018-07-13 | BETA | iOS (1244), Android | 3 | Radio settings: Allow a touch and hold/slide left or right to scrub faster to higher numbers. Channel and Sub Code didn't always hold on choice after moving to next adjustment. Sometimes would "rubber band" to another number after release or pause.This also happened on Call tone and VOX. | Code debt | Fix code bugs | Radio settings | OK |  | Yes | N | N | Y |  | Closed | Closed | 1250, 2.6 |  | 2018-08-15 |  |  |  |  | 18 jul, XY: app need follow radio , It's normal case 24 Jul CS: This is a Beta feedback issue, need to be fixed. Video uploaded at: https://drive.google.com/open?id=1yZSnE7TCkeLk_vrTPStu9YEf_6tmpmmH | 2018-08-10
429 | On Boarding | 2018-07-13 | BETA | iOS (1244) | 2 | First make sure BT is disbaled at control center. Next go to Settings and eN/Able BT. Then Launch Talkabout app and observed that setup is stuck at EN/Abling BT page. | [5 empty] | Yes | N | N | Y |  | Closed | N/A | 1250, 2.6 | 18 Jul, XY: iOS 11 bug, no workaround solution 18 Jul, SK: when issue is reproduced, try pair with other BT device, it can be paired 24 Jul, XY: 这个问题是IOS 系统的问题，参考https://forums.developer.apple.com/message/300002#300002 24 Jul, CS: We urge to look for workaround solution, as we did not see this issue when pairing with BT headset. 31 JUl, CS: request SK to send steps to XY | 2018-08-15 |  |  | Here i found another way to duplicate: 1. DO the same way to disable and eN/Able the BT in iphone setting. 2. Operate the APP, proceed the step until step to asked for pair Radio page. Then now kill the APP. 3. Now Operate the APP to paired BT again, same issue appear.
431 | Settings | 2018-07-18 | CS | iOS, Android | 3 | Update Emergency settings wordings at the second paragraph: Long press Emergency Alert Button on your radio for 3 seconds to send audible siren on the radios within range (for 8 seconds) followed by 22 seconds of the channel to be opened to transmit any sound. This is followed by emergency message to be sent out. In addition to this, your current location will be sent and reflected in Group members Maps View. | Ambiguous requirement | Update emergency settings wordings at the second paragraph according to the requirement | Display of the emergency page | OK |  | Yes | N | N | Y |  | Closed | Closed | 1250, 2.6 | IOS 1.2 (1250) Andriod 2.6 | 2018-08-10 |  |  |  |  | 24 Jul, CS: Issue sent to Auctus but no commitment received yet. 24 Jul, XY: iOS 1.2 49 会解决，安卓2.5 会解决 | 2018-08-03
435 | Maps | 2018-07-24 | SK | Android V2.4 | 2 | observed force shutdown while Geofence activated and out of boundary. with Andriod phone Huawei (Andriod 4.4.2) | Code debt | Add relevant permissions | Geofence | OK |  | Yes | N | N | Y |  | N/A | Closed | 2.6 |  | 2018-08-10 | [5 empty] | 2018-08-03
437 | Setup | 2018-07-26 | BETA | iOS (1244), Android | 3 | first couple of onboarding screens are flashing too fast | [5 empty] | Yes | N | N | Y |  | Closed | Closed | 1250, 2.6 | 26 Jul, CS: confirmed it is an issue, video uploaded at Baidu 31 Jul, CS: Resend to XY | 2018-08-10
443 |  | 2018-07-26 | BETA | Android V2.3, iOS | 3 | The notification badge (blue dot with count) is not centered on the list. | Code debt | Modify the layout of the chat home page | Display of the chat home page | OK |  | Yes | N | N | Y |  | Closed | Closed | 1250, 2.6 | 26 Jul, CS: can clarify further? Right now is at bottom right corner, following VI. 26 Jul. MM coming from the UI/UX team (Maggie Wang) was hoping that Lee Sun speaks this language and understands what she meant. I send a follow up email to ask for clarification 27 Jul. See screen shot in consolidated list. seems a bug for some phones. 31 Jul, CS: Pixel 1, Android 8 | 2018-08-10 | https://drive.google.com/file/d/1MhO70qTeM0gyucaFi3zNjPQdA1XsmGv-/view |  | SK: The dot with number not in center yet. Also, found the time/ date recived has error, where today's received message should show in time, then message received yesterday/ previous hould show in date at Main Chat page.
444 | FAQs | 2018-07-26 | BETA | Android V2.3, iOS | 4 | FAQ's are not very clean and look a bit amateuristic, Improve lay out /font etc. | Code debt | Modify the layout of the FAQ page | Display of the FAQ page | OK |  | Yes | N | Y | Y |  | Closed | Closed | 1250, 2.6 | 26 Jul, CS: redesign FAQ VI ? 1 Aug, CS: LeeSun will communicate with Auctus on the proposed layout. Font fixing and alignment should not charge for costing. For FAQ alignement, please refer to wireframe_20180718, page 131. | 2018-08-10
461 |  | 2018-07-26 | BETA | Android V2.3, iOS | 3 | Minimum 3 members (appear in the toast) in a group is also not clear. I can select 2 people and the create group screen is saying Total 2 members and I'm allowed to proceed. Also N/Ame should be optioN/Al and I could always go back to add the N/Ame. | Code debt | Modify relevant text, change toast to alertdialog | Display of the alert text | OK |  | Yes | N | N | Y |  | CLosed | Closed | 1250 | 26 Jul, CS: can clarify further? 26 Jul, mm: yes, when you create a group a pop up says you need minimum of 3 members but allos you to create a group while only 2 members are added, so message is not correct. Should say: Minim 3 members including yourself. Or Minimum 2 members. 27 Jul: Please change to: Minimum 2 members are required. (also corrects the grammar) | 2018-08-10 |  |  | SK: messgae appeared at different state, where IOS appear when click DONE, Andriod appear when selecting members. (Please follow IOS)
472 |  | 2018-07-26 | BETA | Android V2.3, iOS | 3 | If I start walking downhill, how can the ascent increase before I go back uphill?=> seems that this functioN/Ality is not working properly | GPS is not stable, and The algorithm is not very reasoN/Able | optimize algorithm | Track recording datas | OK |  | Yes | N |  | Y |  | Closed | Closed | 1250, 2.6 |  | 2018-08-15 |  |  |  |  | 26 Jul,CS: how many was the ascent increase? Can share reading before and after ? 27 Jul, MM: obviously it should not go up if someon goes down, is this a lag issue? Have we done sufficient comparison test to check accurate measurements? 31 Jul, CS: I compared with GAIA, the app is also showing increment in ascent when going down hill. request to share out the track file. my maps => my tracks =>click share icon => export by email or others
481 |  | 2018-07-28 | BETA | Android V2.3, iOS | 3 | redirect the link for NO T800 yet on the home welcome screen to: shop.motorolasolutions.com/T800 | New requirement | Modify the link on the home page | Display of the home page | OK |  | Yes | N | N | Y |  | Closed | Closed | 1250, 2.6 |  | 2018-08-10 | [5 empty] | 2018-08-10
482 | On Boarding | 2018-07-28 | SK | Android V2.4 | 3 | Pop up Message/Notification different compared to IOS - No data/ internet - No Location service | Code debt | Modify relevant text | Display of the alert text | OK |  | Yes | N | N | Y |  | N/A | CLosed | 2.6 |  | 2018-08-15 | [5 empty] | 2018-08-10
483 | Maps | 2018-07-30 | SK | Android V2.4, iOS | 3 | Location Pin icon displaying in Map not accurate. where the member already off line but icon not in dim colour. | Code debt | Modify the marker view according to member status | Display of the member view marker | OK |  | Yes | N | N | Y |  | Closed | Closed | 1250, 2.6 | 13 Aug, XY: 自动连接的场景包括： APP与对讲机的距离从很远到很近，或者对讲机重启等。 APP 无法判断当前对讲机是从远处移动过来的，还是对讲机主动开机 导致的重新连接，APP只知道发现已经连接过的对讲机。所以 3和5的场景无法与自动连接的场景区分的。 蓝牙打开或者APP启动 这两种场景 是连接对讲机的先决条件，但是并不能保证APP的本次连接就是这两个动作引起的。 也有可能打开蓝牙后，隔一段时间后对讲机从很远地方移动过来，APP自动与它连接上。 蓝牙连接是一个异步的过程，所以，用户打开蓝牙后，可能有多种状态，能找到对讲机，找不到对讲机，或者一段时间后发现对讲机，或者对讲机连接失败，APP无法准确判断本次连接与打开蓝牙有必然联系，必然会导致误判。 | 2018-08-10 |  |  | SK: Issue dim after members offline solved. BUT, when members Online, while origiN/Ally the icon is dim, the icon should light when members going Online. |  |  | 2018-08-10
484 | Help and Support | 2018-07-31 | CS | iOS, Android | 4 | Fonts under FAQ and Support need to be standardized using Roboto font | Code debt | Modify the font of the FAQ page | Display of the FAQ page | OK |  | Yes | N | N | Y |  | Closed | Closed | 1250, 2.6 |  | 2018-08-10 | [5 empty] | 2018-08-10
486 | Bluetooth Connection | 2018-07-31 | SK | Android V2.4 | 2 | Different behavior compare to IOS: -> Andriod - After kill APP, the bluetooth connection will auto connect back directly. -> IOS - After Kill the APP, the bluetooth connection will not connect back until App reopen (bluetooth connection in Radio showing pending to pairing). | Bluetooth maN/Ager not exit properly | Update bluetooth stat upon exit | Bluetooth Connectivity | 2 hours of stress test on bluetooth connect and disconnect. Test Passed. |  | Yes | N | N | Y |  | N/A | Closed | 2.6 | [6 empty] | 31 Jul, XY: need to study further | 2018-08-10
492 | Hamburger Menu | 2018-08-02 | SK | Android | 3 | the offline maps layout please follow iOS layout. Background color, and no line at the bottom. | Ambiguous requirement | Modify the layout of the offline maps according to ios | Display of the offline map page | OK |  | Yes | N |  |  |  | N/A | Closed | 2.6 |  | 2018-08-10
493 | Maps | 2018-08-06 | Marjon | iOS, Android | 2 | I walked out of my house with two phones in my hand. each had different measurement for total ascent: one had 29ft and the other 7 ft. I only walked 0,04 miles so that is a big delta for such a short distance explaining the extremely unrealistic total ascents I had before on my phone. see images of the two tracks.(note they were made with different phones and than shared). | Hardware differences of mobile phones | optimize algorithm | Track recording datas | OK |  | Yes | N |  |  |  | Closed | Closed | 1250, 2.6 |  | 2018-08-15 | https://drive.google.com/open?id=1Y4k8p1azBMinQVDlN9NcKLffjAiuNPoa | [5 empty] | https://drive.google.com/open?id=1Y4k8p1azBMinQVDlN9NcKLffjAiuNPoa
494 | FAQ | 2018-08-06 | Marjon | iOS, Android | 3 | ​that the wrong icon was shown for emergency alert in the FAQ (they used Bluetooth icon in stead of the danger triangle) | No icon was provided | Modify the emergency icon | Display of the FAQ page | OK |  | Yes | N |  |  |  | Closed | Closed | 1250, 2.6 |  | 2018-08-10
495 | FAQ | 2018-08-06 | Marjon | iOS, Android | 3 | ​ I need to press three or four times before it expands (very seldom works immediately). Can we improve that? It is very frustrating and users will think there is no answer. This is bug not enhancement! | Code debt | Expend the clickable area | Operating experience | OK |  | Yes | N |  |  |  | Closed | Closed | 1250, 2.6 |  | 2018-08-15 | https://drive.google.com/open?id=1vCyT_cTpvbntnEVYTmhhbr4mPOpesSkv | [5 empty] | https://drive.google.com/open?id=1vCyT_cTpvbntnEVYTmhhbr4mPOpesSkv
496 | Bluetooth Connection | 2018-08-06 | FT | iOS V1.2(1248), Android | 2 | APP connected to P1B radio(V03.08), when P2 radoi(V04.02) power on, APP auto connected to P2 radio. And in P1B radio the BT icon still show connected, but actually it is not. APP connected to P2 radio(V04.03), when another P2 radio (V04.04) power on, APP auto connected to 2nd P2 radio. And in 1st P2 radio the BT icon still show connected, but actually it is not. | Code debt | Fix code bugs | Bluetooth Connectivity | OK |  | Yes | N |  |  |  | Closed | Closed | 1250, 2.6 |  | 2018-08-10
498 | Easy Pairing | 2018-08-14 | SK | iOS V1.2 (1250), Android V2.6 | 2 | After Easy pairing success displaying correct CH and code in radio, but App try to get into Radio Setting, at the scroll bar still showing previous CH and code. then at this time, the Radio will changed immediately as setting in Radio setting Channel and code. | radio setting |  |  |  | Yes | [5 empty] | Closed | Closed | 1256, 2.6
499 | Easy Pairing | 2018-08-14 | SK | iOS V1.2 (1250), Android V2.6 | 2 | Sometime after easy paring success, no pop up message indicate, and the countdown timer still displaying. | message register |  |  | easy pairing | Yes | [5 empty] | Closed | Closed | 1251, 2.7 | fixed in IOS 1251, Andriod V2.7
500 | Maps | 2018-08-14 | SK | iOS V1.2 (1250) | 3 | Satellite Maps View no street N/Ame. | [10 empty] | Closed | N/A |  | fixed in IOS 1.2 (1252)
501 | Track | 2018-08-14 | SK | Android V2.6 | 1 | Andriod Tracking no Total Ascent result. |  |  |  |  | Yes | [5 empty] | N/A | Closed | 3 | 15 Aug, CS: I further looked into this issue. I found that Talkabout app will keep increment Ascent but GAIA app will not. I stay at my cube, the ascent increased to more than 2300ft ! App fiN/Ally restart. 16 Aug, SK: still seeing no Ascent in Huawei hp. Bringing iOS phones together, IOS ascent are not zero, but Huawei showing zero Ascent
502 | Track | 2018-08-14 | SK | iOS V1.2 (1250) | 3 | Sometimes when i select the Track (during Track recording) to check the total ascent or mile stone, the Tracking line on map is missing. |  |  |  |  | Yes | [5 empty] | Closed | N/A | 1254 | SK: is a bit slow the tracking line came out.
503 | Maps | 2018-08-15 | SK | Android V2.6 | 3 | during track recording, tap on recording icon will bring up statistic window. But after few seconds, it will disappear by itself. Same applied to view icon. (Sumsung A8 - Andriod 7) | dialog dismiss message | change message | map | ok | Yes | [5 empty] | N/A | Closed | 2.7 | fixed in Andriod V2.7
504 | Chat | 2018-08-15 | SK | Android V2.6 | 3 | received message showed time stamp incorrect: where today received message show in time, yesterday or previous received message show in date. | display | change time format | chat table | ok | [6 empty] | N/A | Closed | 2.7 | fixed in Andriod V2.7
505 | Maps | 2018-08-16 | CS | Android V2.6, iOS | 3 | Start track recording, and leave the phone idle overnight. Next morning it show accumulative ascent of 1668 ft. Besides, I need to click several times on the "Pause recording" alert message. | [10 empty] | Closed | Closed |  | 16 Aug, XY: to investigate why multiple pop ups issue. No closure date yet.
506 | Track | 2018-08-16 | SK | IOS 1251 | 3 | IOS in Tracking duration is not real-time.. it only starts tickling while I'm on the move. Once I stop moving, the duration timer will stop. experiment compared to Andriod-- Andriod timer will coninue counting even i stop moving (duing track recording). Expected behavior: iOS track duration should continue counting regardless of user movement, same as Android | [10 empty] | Closed | N/A | 1254 | 16 Aug, XY: investigate how to make iOS behave the same as Android. No closure date yet.
509 | Bluetooth Connection | 2018-08-20 | CS | iOS, Android | 3 | Still observing Bluetooth disconnect and reconnect intermittent issue | Y | N | [8 empty] | Closed | Closed
510 | Radio settings | 2018-08-20 | CS | Android | 3 | change subcode via radio settings in the app. Observe misalignment between app and radio. subcode in app showing 104 but radio is showing 103 | Y | N | [8 empty] | N/A | Closed | 3 | 20 Aug, XY: fixing in progress, ETD: 24 Aug
511 | Maps | 2018-08-20 | CS | iOS, Android | 2 | Sharing geofence, Select few members to share geofence. Most of the time failed to share geofence, either need to retry or after one or two then only able to send successfully. | Y | N | [8 empty] | Closed | Closed | 1256, 3.0 | 20 Aug, CS: smoothness of sending geofence need to be seriously looked into. However there is no issue sending individual chat or Shout message.
512 | Maps | 2018-08-27 | CS | Android (3.0) | 3 | Failed to download offline map in the background. On iOS V1.2(1256) is ok. | [10 empty] | N/A | Closed | 3.1
513 | Maps | 2018-08-27 | CS | iOS V1.2(1256) | 3 | iOS has no notification when received track or offline map | [10 empty] | Closed | N/A
514 | Bluetooth Connection | 2018-08-29 | FT | Android (3.0) | 3 | When press TEST, radio side is delay for few seconds. On iOS is ok. | [10 empty] | N/A | Closed
515 | Bluetooth Connection | 2018-08-29 | FT | Android (3.0) | 3 | When press TEST, the TEST is not blink. UI is different from iOS. | [10 empty] | N/A | Closed |  | ETD: 7 Sep
516 | Chat | 2018-08-29 | FT | iOS V1.2 (1256) | 3 | When phone go to sleep, or when APP put at background, APP will stop sending message. Only SK 's iphone 8 will not stop sending. | [10 empty] | Closed | N/A
517 | Chat | 2018-08-29 | FT | iOS V1.2 (1256) | 3 | Sometimes auto response is not sent out. Tested at outdoor. 1 out of 10 times observed radio screen does not show Tx, that means auto response not sent out. | [10 empty] | Closed | Closed | V1.0.2 (1022), V3.2
518 | Chat | 2018-08-30 | FT | iOS V1.2 (1256) | 3 | When try to scroll up in chat, app keep pull to bottom. Steps to duplicate: 1. APP put to background and let APP receive 5 messages. 2. After 5 messages receive, go into APP and go to chat window. | [10 empty] | Closed | N/A
519 | Maps | 2018-09-03 | FT | iOS V1.2 (1259) | 3 | Typo on 'stoped'. When Offline map is donwloaded half way. | [10 empty] | Closed | Closed |  | ETD: 7 Sep
521 | Chat | 2018-09-06 | FT | iOS V1.2 (1259) | 2 | SK created a group with CS and Dennis. After the group is formed, SK invited me to join. I receive and accepted the group invitation. In the group info, I can see my own phone number as 1 of the member, but I cannot see SK. There are 3 members in the group, myself, CS and Dennis. I do not see SK. But I can still receive message from SK in group. In Map view, I choose to view this group and I only able to see CS and Dennis. | [10 empty] | Closed | N/A | V1.0.2 (1022)
522 | Maps | 2018-09-06 | FT | iOS V1.2 (1259) | 3 | During track recording, I changed map style. After change map style I am not able to zoom in/out or move the map. I have to go to chat then return to map view in order to zoom. Or I have to double tap the map in order to zoom. | [10 empty] | Closed | N/A
523 | Maps | 2018-09-13 | SK | Andriod V3.2 | 4 | Revert the Share icon in Andriod. | [10 empty] | NA | Closed
524 |  | 2018-09-13 | SK | Andriod V3.2 | 3 | Andriod different behavior: App in Menu setting, kept App in phone background, then open App again Andriod - App start up again in Chat page, IOS - Opened and show at Menu Setting. | [10 empty] | NA | Closed
525 | FAQ | 2018-09-13 | SK | IOS V1.0.2 (1023), Andriod V3.2 | 4 | remove the sentence “currently shows Bluetooth icon, should be triangle alert icon” in FAQ. | [10 empty] | Closed | Closed
526 | FAQ | 2018-09-13 | SK | IOS V1.0.2 (1023), Andriod V3.2 | 4 | Purchase radio link to be add in FAQ, Question to of "Radio" | [10 empty] | Closed | Closed
530 | Chat | 2018-09-24 | CS | Android 1034 | 4 | In chat, keep sending at 9 message to invalid receipient. Observed that There are 3 overlapped pop up notifications being put up. Expect to have only 1 pop up. | [10 empty] | Closed | Closed
531 | Radio Setting | 2018-10-02 | SK | IOS V1.0.2 (1025), Andriod 1036 | 4 | Language Changing, IOS and Andriod has different reboot behavior. | [10 empty] | Closed | Closed |  | 3 Oct, cs: this probably is due to OS differences between android and iOS, thus may not be valid issue.. Need to further confirm with auctus.
532 | Radio Setting | 2018-10-02 | SK | IOS V1.0.2 (1025) | 4 | In English Language, go into Radio Setting, Weather mode, there is a line between Weather Channel Channel and Weather alert, but after changed to french, the line is missing. | [10 empty] | Closed | NA | IOS 1030 | 3 oct, cs: cosmetic issue.
533 | Radio Setting | 2018-10-02 | SK | Andriod 1036 | 4 | In Radio Setting, Weather mode, the Weather Channel displaying by default? It is different from IOS. | [10 empty] | NA | Closed |  | 3 oct, cs: behavior difference between android and ios, cosmetic issue.
534 | Chat | 2018-10-02 | SK | IOS V1.0.2 (1025), Andriod 1036 | 4 | Notification for messaging fail to send still in English where the App system already changed in French *after several messages RETRY. | [10 empty] | Closed | Closed | IOS 1030,1041 | 3 oct, cs: French translation not yet fully done.
535 | Radio Setting | 2018-10-02 | SK | Andriod 1036 | 4 | In frence language, Andriod phone showing "DISMISS", IOS showing "EFFACER" | [10 empty] | NA | Closed | 1041 | 3 oct, cs: Translation missed in android.
536 | Chat | 2018-10-02 | SK | IOS V1.0.2 (1025), Andriod 1036 | 4 | After Geofence Setting applied/ sent, in Chat mode Language not changed accordingly after setting Language changed. | [10 empty] | Closed | Closed | Behave as expected | 3 oct, cs: Language swtiching not properly reflected in chat mode history. picture has been shared to auctus.
537 | Radio Setting | 2018-10-03 | SK | Andriod 1036 | 3 | In easy pairing mode, select member. Once timer counter shows up, press home. Enter Talkabout app again, found that timer counter has disappeared but the timer is still taking effect. Expected behavior: Should show timer counter when re-entering the app, same as how iOS behaves. | [10 empty] | NA | Closed | 1041 | 3 oct, cs: same fixes done in iOS should be also applied to android.
iOS
| Severity | iOS | Unresolved | Resolved | [9 empty] | Resolved
| 1 | 0 | 0 | 0 | [9 empty] | 0
| 2 | 7 | 0 | 7 | [9 empty] | 0
| 3 | 23 | 0 | 23 | [9 empty] | 0
| 4 | 8 | 0 | 9 | [9 empty] | 0
| TOTAL | 38 | 0 | 39 | [9 empty] | 0
Android
| Severity | Android | Unresolved | Resolved
| 1 | 1 | 0 | 1
| 2 | 7 | 0 | 7
| 3 | 24 | 0 | 28
| 4 | 3 | 0 | 11
| TOTAL | 35 | 0 | 47
Note on G25: +cheeseong.lim@motorolasolutions.com did auctus commit to fix this without cost? This is actually change request from my point of view. If they can fix it without cost, is bonus. _Assigned to Lim Chee Seong Lim_ -Ft Gan Gan
Note on R51: +songkui.wong@motorolasolutions.com please verify close all opened items. Thanks -Lim Chee Seong Lim

## Enh_PostD1 (hidden)
No | Area | Reporting Date | Reported By | Observed Point | Severity | Issue | Required To Fix by D2 (20-Aug-18) | Enhancement | ID Team | Status IOS | Status Andriod | RC Support | comment | Design Effort required | Planned Close Date | Links | ID Proposals | reply comment | 工作量 | APP feedback (XiangYang) 7 June 2018 | Feedback SK (8 June 2018)(1235) | Feedback SK (13 June 2018)(1236) | Feedback SK (16 June 2018)(1237) | Feedback SK (17 June 2018)(1238) | Android 1.9 3 July | Android 2.0 4 July | Android 2.2 7 July | Android 2.4 24 July
248 | Chat | 2018-02-28 | Marjon | iOS V1.1(20), Android V1.4(20) | 3 | There is no notification on APP icon when there is new message. Please refer to latest wireframes/VI. | No | Y | N | Closed | Open | N | to be discuss with tzelin. XY, 9 July: not a defect, should be an enhancement. https://stackoverflow.com/questions/17565307/how-to-display-count-of-notifications-in-app-launcher-icon 24 Jul, XY: iOS已经解决了。安卓本来就不支持在app icon上显示消息数量，之前已经解释过，需要作为新功能评估成本。 25 Jul, CS: it was raised to Auctus way back in Feb, and was committed to be resolved by 13 Apr 2018 Please refer to screen captured below (Talkabout APP Issue Tracking 6-Mar-18). Therefore, It should not be still considered as New Enhancement and not to be fixed. Kindly take the necessary action and deliver Android solution not later than 3-Aug-18. 26 Jul, XY: Denied that this is not Enh. Request for costing 26 Jul, Marjon: Critical but not gating D2 Can be put as future enhancement, would be a running change for customer release.
319 | MAPS | 2018-06-14 | SK | iOS V1.2 (1236) | 3 | When radio is disconnected, the 'radio dissconnected' bar notification shall also show in map view. now it is only show in chat view. | No | Y | N | Open | Open | N | Still same in 1240 Still same in 1243 18 jul, XY: new feature ,will not support 26 Jul, Marjon: park under future enh (<3 mths) 8 Aug, Marjon: Crucial to be done soon after D1 8 Aug, CS: this was updated in current VI "TALKABOUT_APP_VI_Design_20180713.pptx" slide #40 |  |  | https://drive.google.com/open?id=1Qj9JRs039qt5K1XHC6pHJH_SS0Bq4PM1 | 7 Aug, CS: Update VI
340 | Maps | 2018-06-20 | FT | iOS V1.2 (1238) | 3 | This is not issue, this is UI enhancement. When user A is out of boundary, user A APP will pop up alert message and user A click on OK. User A location will then sent to user B and user B APP will have show a pop up message, and show user A updated location in map. Please follow TALKABOUT_APP_Wireframes_20180620. | No | Y | N | Open | Open | N | UI enhancement. 18 jul, XY: new feature ,will not support 26 Jul, Marjon: park under future enh (<3 mths)
343 | Chat | 2018-06-20 | Marjon | iOS V1.2 (1238) | 3 | This is not issue, this is UI enhancement: When you are in the map you don't get new message notification. Only shown if out of app or in the chat window | No | Y | Y | Open | Open | N | UI enhancement. 18 jul, XY: new feature ,will not support 26 Jul, Marjon: park under future enh (<3 mths) |  |  | https://drive.google.com/open?id=1bGVteb7rz_FCKQf-JhZVwwiaoVqpLBqJ | follow 7 Aug VI doc (TALKABOUT_APP_VI_Design_20180807) slide #10,
423 | Maps | 2018-07-06 | BETA | iOS 1244 | ENH | Maps: user should be able to change walker icon on track to bicycle for bike rides |  |  | Y | Open | Open | Y | enhancement??? 10 jul, CS: This is new proposal, need to define detailed implementation. | high |  |  | 17 Aug, N/A: It should be intelligent enough to switch between walking or cycling
427 | Maps | 2018-07-09 | FT | iOS V1.2 (1239), Android | 3 | Press radio easy pairing button OR press locate button(in map view) to send location is now following the FCC 30s rule. When user try to send location more than 1 time within 30s, the request to send location will be in queue. In current release all the send location request will be in queue and making the send message request need to wait long. We shall change it to only 1 location request will be in queue. Example: User press locate button 5 times within 30s, then followed by a text message. At 0s, first location will be sent; at 30th second 2nd location will be sent, at 60th second, text message will be sent. | No | Y | N | Open | Open | N | Already feedback in V.12(1239) but did not capture in issue list. 10 jul, XY: can be implemented 18 jul, XY: new feature ,will not support 26 Jul, Marjon: Still seeing the GPS location not updated issue. For this particular 30s rule request, it can be put as future Enh.
439 | keyboard | 2018-07-26 | BETA | Android V2.3, iOS |  | When the keyboard is pulled up, it covers the 'next' button, which user may not know they need to collapse the keyboard to find it. Either when user hit return on keyboard will bring them to the next step or bring the next button above the keyboard. | No | Y | Y | Open | Open | N | 26 Jul, CS: This involves new VI to be updated 26 Jul, MM: not crucial can be future | low |  |  | In Add member screen, Keyboard "Return" button changed to "ADD" . Need to check with Auctus if this is doable.
440 | onboarding | 2018-07-26 | BETA | Android V2.3, iOS | ENH | Allow user to go back to tips at later time (skip and go back) => for future | No | Y | Y | Open | Open | Y |  | medium |  |  | Add a "Tips" section in Help and Support screen. To be first in menu, need N/A to update wireframes.
459 | Chat | 2018-07-26 | BETA | Android V2.3, iOS |  | Make predefined messages visible in chat rather than keyboard (keyboard should be selection: . RatioN/Ale would be if you want to be quick you use predefined so should be easy accessible. Keyboard means involvement so one more stroke not an issue. | No | Y | Y | Open | Open | Y | 26 Jul, CS: redesign current VI ? 27 Jul, MM should be done as soon as possible. But not gating D2 | high |  |  | Suggest to always show pre-defined messages, then the predefined messages icon will change to keyboard icon. When user tap to switch to keyboard input then the icon shall change to predefined messages icon again.
460 |  | 2018-07-26 | BETA | Android V2.3, iOS |  | some unnecessary animation: overflow menu being fly in from the middle of screen. | No | Y | Y | Open | Open | N | 26 Jul, CS: can clarify further? 26 Jul. I have requested clarification and this is answer. I am thinking that it might be unique to Android as I still don't understand. "When you in a message view with someone and taps on the overflow icon: the overflow menu appears from the middle of the screen and float to the top. Typically stock Android just opens the menu right under the overflow icon. Adding animation is not a big deal but the speed of animation may need to be adjusted faster as it is a little slow now and user has to wait for the animation and then select the action." 27 Jul, CS: what does it mean by overflow icon? If not mistaken, we don;t have any animaton in the app. Could you please clarify ? 27 Jul, MM see clarification in email to Lee Sun. Up to Lee Sun to determine severity. I do not have android phone to see. but likely not gating item for D2 | high |  | https://drive.google.com/open?id=1WJN2D3uPnNkAhqlCo8gteQyA9wZA6-do | Need to be consistent with iOS. Menu need to come up from top instead of flying from bottom.
462 |  | 2018-07-26 | BETA | Android V2.3, iOS | ENH | allow more customizable messages. future | No | Y | Y | Open | Open | Y |  |  |  |  | add one more customizable meesage row
463 |  | 2018-07-26 | BETA | Android V2.3, iOS |  | users seem to have difficulties finding maps in the search area is this controlled by map box or can we help to improve on this? | No | Y | N | Open | Open | N | 38 Jul, CS: This is user familiarity issue. Adding note to FAQ? If yes, then FAQ contents MUST be locked down before 3-Aug-18 27 Jul, mm: this is not user familiarity issue but many 'landmarks' or N/Ames are not found in map box. Is this map box map issue?
465 | Maps | 2018-07-26 | BETA | Android V2.3, iOS |  | request to send location before sending and who to send to (currently not clear where it goes) | No | Y | Y | Open | Open | N | 38 Jul, CS: This is user familiarity issue. Adding note to FAQ? If yes, then FAQ contents MUST be locked down before 3-Aug-18 27 Jul, your suggetion is to send everything to FAQ😀. But obviously that is not good design. It should be intuitive. I don't see this as crucial now but we should think about future updates. If automatic becomes approved, we can elimiN/Ate that you send location out and just let it be a pan to your current location button as it is in google. 8 Aug, Marjon: Crucial to be done soon after D1 |  |  |  | Suggest to change pop up message from "Location has been sent" to " Location has been sent to members"
466 |  | 2018-07-26 | BETA | Android V2.3, iOS |  | Request share sheet to export GPX files of maps and location pins is not available | N | Y | Y | Open | Open | [8 empty] | 38 Jul, CS: This is user familiarity issue. Adding note to FAQ? If yes, then FAQ contents MUST be locked down before 3-Aug-18 27 Jul, MM: not familiarity issue. Has always been a request. Should be implemented asap but not gating item.
467 |  | 2018-07-26 | BETA | Android V2.3, iOS |  | it's not very clear that you have to go to menu to save a offline map. Usually people will go to map tab and try to find where to create offline map. | No | Y | Y | Open | Open | N | 38 Jul, CS: This is user familiarity issue. Adding note to FAQ? If yes, then FAQ contents MUST be locked down before 3-Aug-18 |  |  |  | 9 Aug, LS:The current icons that appearing in maps view are rather functioN/Alities that user can use within the map view. However offline map is a separate map to be called out to replace your current live map.
470 | On boarding | 2018-07-26 | BETA | Android V2.3, iOS |  | Update tip on Put phone in airplane. Keep Bluetooth on. | No | Y | Y | Open | Open | N | 26 Jul, CS: request to update FAQ ? If yes, then FAQ contents MUST be locked down before 3-Aug-18 27 Jul, MM: more intuitive to do in tip. | low/medium |  |  | Warning message saying that "Radio Discoonected" when BT is off, so user is actually being notified and they can go and turn on BT.
471 | Add Members | 2018-07-26 | BETA | Android V2.3, iOS |  | some beta testers find the number of options on the map view overwhelming and think they should be regrouped. Also not always clear difference between pin and my location. I don't have a solution to simplify this and make differences more clear. UI team to think about this. | No | Y | Y | Open | Open | N | 26 Jul, CS: This is user familiarity issue. Adding note to FAQ? If yes, then FAQ contents MUST be locked down before 3-Aug-18. Otherwise, need to redefine a new VI to cater for new appearance. Jul 27 MM: we should not use FAQ as a cruch to fix issues with intuitiveness. this is something to consider for future app updates. | high |  |  | 9 Aug, LeeSun: The display resolution on the phone does affect how the floating menus appearing on the screen, if the resolution is low, it will seem that menus are occupying too much space thus it looks overwhelming.
473 | Maps | 2018-07-26 | BETA | Android V2.3, iOS |  | sharing location pin goes in to a loop => see this video | No | Y | Y | Open | Open | Y | 26 Jul, CS: user needs to tap back arrow on the top left corner Jul 27: MM: good example for a close button for future updates | medium |  | https://drive.google.com/open?id=19Ybiowyj1ckpy7Bw9XyOUaMRVjGmcTPu | We felt it should not directly jumping out of the screen, it could be annoying to user who wish to share multiple maps. But instead we felt is lacking of pop up message to indicate confirmation of sharing the map. So, one pop up screen is required.
474 |  | 2018-07-26 | BETA | Android V2.3, iOS |  | when you select view members it won't show unless you send a message to each other successfully. User expects the moment you click view member to see them. So selecting view member should trigger a ping for location. | No | Y | N | Open | Open | N | 26 Jul, CS: This is new requirement. 27 Jul, MM: for future updates
475 |  | 2018-07-26 | BETA | Android V2.3, iOS |  | Trackrecording does not allow to move or zoom while recording | No | Y | N | Open | Open | N | 26 Jul, CS: This is new requirement. 27 Jul, MM: this is useability issue, while recording you should be able to still look where you are going etc. It is possible if you click on the map and get out of the trackrecording notification screen. Just not intuitive so users think they are no longer to do this. How can we make this clearer?
479 |  | 2018-07-28 | BETA | Android V2.3, iOS |  | Change the time stamp on the member icon to not have seconds, makes harder to understand what user is looking at and seems silly given the lag of transmission. | No | Y | N | Open | Open | N | Jul 27: can be future update.
487 | Add Members | 2018-07-31 | Marjon | iOS, Android | 4 | if you pull from search phone contacts it is very hard to edit (usually delete the country code). Not critical issue but can we improve on ability to edit? | No | Y | N | Open | Open | N | 31 Jul, LeeSun: We could work with Auctus to see if we could change the programming code to define the number as individual rather than block.
497 | UI/UX | 2018-08-07 | LeeSun | iOS, Android | 4 | Offline member icon changed to Gray color, please refer to style guide (MaroonBell Style Guide v1.0 20180806). Blue dot unread message need to be adjusted little higher to besides arrow cursor. Note: FAQ need to update as well. | No | Y | N | Open | Open | N | [7 empty] | 15 Aug, XY: need costing |  | https://drive.google.com/open?id=1U5GUz9E706UPNhTonj5EkFQ6luYz-Jgd
520 | My Members | 2018-09-06 | FT | iOS V1.2 (1259) | 3 | User is not able to edit member's ID/phone number from My Members. The only way is to add the member again.
529 | Chat | 2018-09-20 | CS | IOS V1.0.2 (1023), Andriod V3.2 | 4 | Type some words in chat window without sending out. Go to home screen and go in to previous contact again. Observed that text which was entered just now, has been wiped out. | N | Y | N | Open | Open
Note on A1: +marjon.manitius@motorolasolutions.com Please capture all post D1 items here. -Lim Chee Seong Lim
Note on N12: +marjon.manitius@motorolasolutions.com Is this the same issue as #459 ? -Lim Chee Seong Lim No, this is requesting more customizable options, but not urgent. #459 makes the predefined ones visible rahter than the keyboard when you select chat. -Marjon Manitius PS I changed the wording, from predefined to customizable, that must have been confusing, my mistake. -Marjon Manitius

## xy_d2 (hidden)
No | Area | Reporting Date | Reported By | Observed Point | Severity | Issue | Required To Fix by D2 (20-Aug-18) | Enhancement | Green Light | Status IOS | Status Andriod | comment | Planned Close Date | Links
120 | Radio Settings | 2018-02-20 | LS | iOS V1.1(20), Android V2.3 | 3 | The Channel, Sub Code & Call Tone scroll bar is hard to know what is the upper and lower limit. May need N/A to suggest | Yes | Y | P | Open | N/A | Still not correct 6/29 4 Jul, XY: XY: already followed the latest UI doc, LS pls confirm 18 jul, XY: new feature , will not support 24 Jul, FT: we have feedback this on 20-Feb-18 together with ID feedback file (see attached slide#18). You should not come back now saying you will not fix it. 26 Jul, XY: Denied and come back that this is Enh 31 Jul, XY: APP independent, not related to radio SW. 1 Aug CS: This should not considered as Enhget email from LeeSun on the evidence. Please refer to links for email evidences. | needs 2 weeks after cost is locked down | https://drive.google.com/open?id=1MlZzceu4eNHeSXCuLgQlgm_RB7sBmjJk
124 | On Boarding | 2018-02-21 | LS | Android V1.4(20) | 3 | Term and Conditions - the background color is wrong. The last sentence will blink when I tap. It should not be. If we just want the user to tap AGREE button. | Yes | N | Y | N/A | Open | LS to review 26 Jul, CS: Android still showing greyish, requested Auctus to change color. Please change the DECLINE button background color to be same as Terms and condition background color. 26 Jul, CS: was not fixed yet. Please change "DECLINE" button background color to be same as Terms and Conditions background color.​ 31 Jul, XY: APP independent, not related to radio SW. | 2018-08-10
225 | Maps | 2018-02-27 | Marjon | iOS V1.1(20), Android V1.4(20) | 3 | My Maps --> My Tracks --> for track recording can we alert user if they have not moved for a while? E.g. Would you like to pause recording? | Yes | N | Y | Open | Open | 5/31/2018 How long will the App pop up the message? i stayed at the same place for around 10 mins, but still no message pop up. 12 Jul, CS: are we fine to set to 10 mins? 18 jul, XY: new feature ,will not support 24 Jul, FT: we also shared as early as 27-Feb-18. How can you say is new request? 24 Jul, XY: agree to fix without additioN/Al cost. 31 Jul, XY: APP independent, not related to radio SW. | iOS: 3-Aug-18 Android: 10-Aug-18
321 | Hamburger Menu | 2018-06-14 | SK | iOS V1.2 (1236), Android | 3 | in FAQ the icons are not added in but instead shows my text e.g. (show icon of hamburger menu) | Yes | N | Y | Open | Open | 24 Jul, CS: this was not fixed properly. Hence this issue is re-opened. | 2018-08-03
345 | Hamburger Menu | 2018-06-20 | Marjon | iOS V1.2 (1238) | 3 | File N/Ame cannot be seen in full. Please change to 2 rows. | Yes | N | P | Open | N/A | Still same in 1240 Still same in 1243 18 jul, XY: new feature ,will not support 24 Jul, FT: the file N/Ame cannot seen in full and we only request to change to 2 lines. This is solving issue to eN/Able user can see the file N/Ame. 26 Jul, CS: Denied and come back that this is Enh | needs 1 week after cost is locked down
389 | Chat | 2018-07-03 | SK | Android V1.9 | 3 | Different behavior compare to IOS: -> added a new member, now tab to chat with him... but i did't type any message, just back to chat home page, i cannot see the new added member N/Ame display at Chat Home Page, but IOS has. | Yes | N | Y | N/A | Open |  | 2018-08-03
393 | Maps | 2018-07-04 | Marjon | iOS (1244), Android | 3 | I am sending a track to a group, only other phone online is without account. The track is not received on the phone without account but the track shows successfully send on the sender phone | Yes | N | Y | Pending verification | Open | 18 jul, XY: not duplicate 24 Jul, CS: This is an issue, not enhancement. 24 Jul, XY: 1249已经解决 | 2018-08-03
417 | Maps | 2018-07-06 | BETA | iOS 1244 | 3 | Maps sharing: share icon on my maps uses not the standard share icon for IOS users (box with arrow out) forgot conclusion of this, but believe was discussed before. | Yes | Y | Y | Open | N/A | not understand 10 Jul, CS: will standardize the icon 18 jul, XY: fixed 1.2 47 18 Jul, CS: icon still not the box with arrow out 26 Jul, XY, This is new feature , not reflecetd in latest VI 26 Jul, Marjon: UI no tclearly defined, Has to be updated to iOS N/Ative icon | 2018-08-03
428 | Settings | 2018-07-13 | BETA | iOS (1244), Android | 3 | Radio settings: Allow a touch and hold/slide left or right to scrub faster to higher numbers. Channel and Sub Code didn't always hold on choice after moving to next adjustment. Sometimes would "rubber band" to another number after release or pause.This also happened on Call tone and VOX. | Yes | N | Y | Open | Open | 18 jul, XY: app need follow radio , It's normal case 24 Jul CS: This is a Beta feedback issue, need to be fixed. Video uploaded at: https://drive.google.com/open?id=1yZSnE7TCkeLk_vrTPStu9YEf_6tmpmmH | 2018-08-10
429 | On Boarding | 2018-07-13 | BETA | iOS (1244) | 2 | First make sure BT is disbaled at control center. Next go to Settings and eN/Able BT. Then Launch Talkabout app and observed that setup is stuck at EN/Abling BT page. | Yes | N | Y | Open | N/A | 18 Jul, XY: iOS 11 bug, no workaround solution 18 Jul, SK: when issue is reproduced, try pair with other BT device, it can be paired 24 Jul, XY: 这个问题是IOS 系统的问题，参考https://forums.developer.apple.com/message/300002#300002 24 Jul, CS: We urge to look for workaround solution, as we did not see this issue when pairing with BT headset. 31 JUl, CS: request SK to send steps to XY | 2018-08-15
430 | Maps | 2018-07-17 | BETA | iOS, Android | 3 | Change the View icon in Maps (second icon at right side) to Group Member icon. | Yes | Y | P | Open | Open | 17, Jul,XY: new feature, not supported 26 Jul, Marjon: Has to be fixed by D2 1 Aug, CS: This is not captured in the SRS or VI previously | needs 1 week after cost is locked down
431 | Settings | 2018-07-18 | CS | iOS, Android | 3 | Update Emergency settings wordings at the second paragraph: Long press Emergency Alert Button on your radio for 3 seconds to send audible siren on the radios within range (for 8 seconds) followed by 22 seconds of the channel to be opened to transmit any sound. This is followed by emergency message to be sent out. In addition to this, your current location will be sent and reflected in Group members Maps View. | Yes | N | Y | Open | Open | 24 Jul, CS: Issue sent to Auctus but no commitment received yet. 24 Jul, XY: iOS 1.2 49 会解决，安卓2.5 会解决 | 2018-08-03
435 | Maps | 2018-07-24 | SK | Android V2.4 | 2 | observed force shutdown while Geofence activated and out of boundary. with Andriod phone Huawei (Andriod 4.4.2) | Yes | N | Y | N/A | Open |  | 2018-08-03
437 | Setup | 2018-07-26 | BETA | iOS (1244) | 3 | first couple of onboarding screens are flashing too fast | Yes | N | Y | Open | Open | 26 Jul, CS: confirmed it is an issue, video uploaded at Baidu 31 Jul, CS: Resend to XY
438 | maps | 2018-07-26 | BETA | Android V2.3 | 4 | Difficulty with understanding on how to download maps, Add a tip about where to find help Include education tip as last tip in onboarding: Familiarize yourself with the app! Go to Help menu for FAQ’s and tutorial videos. | Yes | Y | P | Open | Open | 26 Jul, CS: This is user familiarity issue. Adding note to FAQ? Jul 27:MM. This is crucial to ensure users accept the app as useful. I will send seperate email to Lee Sun asking her to work on this. 1 Aug, LiN/Ar: we will ask SiauFong to ask Auctus provide quotation based on one paragraph and 5 icons in FAQ | After cost and UI lock down, need 1.5 weeks
443 |  | 2018-07-26 | BETA | Android V2.3 | 3 | The notification badge (blue dot with count) is not centered on the list. | Yes | N | Y | Open | Open | 26 Jul, CS: can clarify further? Right now is at bottom right corner, following VI. 26 Jul. MM coming from the UI/UX team (Maggie Wang) was hoping that Lee Sun speaks this language and understands what she meant. I send a follow up email to ask for clarification 27 Jul. See screen shot in consolidated list. seems a bug for some phones. 31 Jul, CS: Pixel 1, Android 8 | 2018-08-10
444 | FAQs | 2018-07-26 | BETA | Android V2.3, iOS | 4 | FAQ's are not very clean and look a bit amateuristic, Improve lay out /font etc. | Yes | N | Y | Open | Open | 26 Jul, CS: redesign FAQ VI ? 1 Aug, CS: LeeSun will communicate with Auctus on the proposed layout. Font fixing and alignment should not charge for costing. For FAQ alignement, please refer to wireframe_20180718, page 131. | time TBD depends on new layout design to determine the effort
461 |  | 2018-07-26 | BETA | Android V2.3, iOS | 3 | Minimum 3 members (appear in the toast) in a group is also not clear. I can select 2 people and the create group screen is saying Total 2 members and I'm allowed to proceed. Also N/Ame should be optioN/Al and I could always go back to add the N/Ame. | Yes | N | Y | Open | Open | 26 Jul, CS: can clarify further? 26 Jul, mm: yes, when you create a group a pop up says you need minimum of 3 members but allos you to create a group while only 2 members are added, so message is not correct. Should say: Minim 3 members including yourself. Or Minimum 2 members. 27 Jul: Please change to: Minimum 2 members are required. (also corrects the grammar) | 2018-08-10
472 |  | 2018-07-26 | BETA | Android V2.3, iOS |  | If I start walking downhill, how can the ascent increase before I go back uphill?=> seems that this functioN/Ality is not working properly | Yes | N | Y |  |  | 26 Jul,CS: how many was the ascent increase? Can share reading before and after ? 27 Jul, MM: obviously it should not go up if someon goes down, is this a lag issue? Have we done sufficient comparison test to check accurate measurements? 31 Jul, CS: I compared with GAIA, the app is also showing increment in ascent when going down hill. request to share out the track file. my maps => my tracks =>click share icon => export by email or others
478 |  | 2018-07-28 | BETA | Android V2.3, iOS | 4 | location pin can only be shared over radio, not network but no indication in the app so users are confused by it. short term we have to have a pop up warning if they try to share without radio network that it can only be done with radio network. Vise versa when you share map and track we need to tell them network is required. | Yes | Y | p | Open | Open | 31 Jul, XY: costing is required | Needs 1 week after cost lock down.
480 |  | 2018-07-28 | BETA | Android V2.3, iOS | 3 | Time stamps reflecting updated status even if offline | Yes | N | Y | Open | Open | What I don't understand is that the time stamp of my location, even though I am off line, is up to date to today? What is the behaviour of the time stamp supposed to be? Should it not reflect the most up to date and latest online status? So user can determine if the location is current and if user is offline when he went offline and where he was. On the other phone it does do that but on one of the phones it shows a recent online status without the radio connected (nor able to send member update to the other radio since that one was not connected either. Please explain. Seems like a bug needing fixing. If so, that bug should be a yes before D2. 31 Jul, XY: fixed in Android V2.4 SK please to confirm if it is fixed in Android 2.4 and for iOS check if this issue is seen. |  | image
481 |  | 2018-07-28 | BETA | Android V2.3 | 3 | redirect the link for NO T800 yet on the home welcome screen to: shop.motorolasolutions.com/T800 | Yes | N | Y | Open | Open |  | 2018-08-10
482 | On Boarding | 2018-07-28 | SK | Android V2.4 | 3 | Pop up Message/Notification different compared to IOS - No data/ internet - No Location service | Yes | N | Y |  | Open |  | 2018-08-10
483 | Maps | 2018-07-30 | SK | Android V2.4 | 3 | Location Pin icon displaying in Map not accurate. where the member already off line but icon not in dim colour. | Yes | N | Y |  | Open |  | 2018-08-10
484 | Help and Support | 2018-07-31 | CS | iOS, Android | 4 | Fonts under FAQ and Support need to be standardized using Roboto font | Yes | N | Y | Open | Open |  | 2018-08-10
485 | Settings | 2018-07-31 | LeeSun | iOS, Android | 4 | When adding member using non phone number, then you will move to next item which is adding ID. The missing link is the Cursor Bar would be better if it could jump down to Assign Member N/Ame and keyboard pop up after user done with ID number. | Yes | Y | p | Open | Open |  | waiting for costing (around 1.5 weeks effort)
486 | Bluetooth Connection | 2018-07-31 | SK | Android V2.4 | 2 | Different behavior compare to IOS: -> Andriod - After kill APP, the bluetooth connection will auto connect back directly. -> IOS - After Kill the APP, the bluetooth connection will not connect back until App reopen (bluetooth connection in Radio showing pending to pairing). | Yes | N | Y |  | Open | 31 Jul, XY: need to study further | 2018-08-10
488 | Add members | 43312 | LeeSun | iOS, Android |  | Add one liner below the ID field - "ID numbers only available for user signed in without account." | Yes | Y | p | Open | Open |  | waiting for costing (around 1.5 weeks effort)

## D2 (hidden)
No | Area | Reporting Date | Reported By | Observed Point | Severity | Issue | Required To Fix by D2 (20-Aug-18) | Enhancement | Convert to test case | Occurrence % | Root Cause | Solution | Target Close Date | PIC | Status IOS | Status Andriod | comment | Planned Close Date | Links | reply comment | 工作量 | APP feedback (XiangYang) 7 June 2018 | Feedback SK (8 June 2018)(1235) | Feedback SK (13 June 2018)(1236) | Feedback SK (16 June 2018)(1237) | Feedback SK (17 June 2018)(1238) | Android 1.9 3 July | Android 2.0 4 July | Android 2.2 7 July | Android 2.4 24 July
120 | Radio Settings | 2018-02-20 | LS | iOS V1.1(20), Android V2.3 | 3 | The Channel, Sub Code, Call Tone & Dual Watch scroll bar is hard to know what is the upper and lower limit. May need N/A to suggest | Yes | Y | N | 100% |  |  | 2018-03-23 |  | Open | N/A | Still not correct 6/29 4 Jul, XY: XY: already followed the latest UI doc, LS pls confirm 18 jul, XY: new feature , will not support 24 Jul, FT: we have feedback this on 20-Feb-18 together with ID feedback file (see attached slide#18). You should not come back now saying you will not fix it. 26 Jul, XY: Denied and come back that this is Enh 31 Jul, XY: APP independent, not related to radio SW. | needs 2 weeks after cost is locked down |  |  |  | This situation is defined in the radio document | LS will review
124 | On Boarding | 2018-02-21 | LS | Android V1.4(20) | 3 | Term and Conditions - the background color is wrong. The last sentence will blink when I tap. It should not be. If we just want the user to tap AGREE button. | Yes | N |  | 100% |  |  | 2018-03-23 |  | N/A | Open | LS to review 26 Jul, CS: Android still showing greyish, requested Auctus to change color. Please change the DECLINE button background color to be same as Terms and condition background color. 26 Jul, CS: was not fixed yet. Please change "DECLINE" button background color to be same as Terms and Conditions background color.​ 31 Jul, XY: APP independent, not related to radio SW. | 2018-08-10
225 | Maps | 2018-02-27 | Marjon | iOS V1.1(20), Android V1.4(20) | 3 | My Maps --> My Tracks --> for track recording can we alert user if they have not moved for a while? E.g. Would you like to pause recording? | Yes | N | N | 100% |  | Add pop up message if user not moved for a while. |  |  | Open | Open | 5/31/2018 How long will the App pop up the message? i stayed at the same place for around 10 mins, but still no message pop up. 12 Jul, CS: are we fine to set to 10 mins? 18 jul, XY: new feature ,will not support 24 Jul, FT: we also shared as early as 27-Feb-18. How can you say is new request? 24 Jul, XY: agree to fix without additioN/Al cost. 31 Jul, XY: APP independent, not related to radio SW. | iOS: 3-Aug-18 Android: 10-Aug-18 |  |  |  | This is new demand | no pop up message. | pop up message every 10mins if no movement. | pop up message every 10mins if no movement.
280 | Chat | 2018-03-04 | SK | iOS V1.1(20), Android V1.4(20) | 3 | >Chat > Add New member > Using phone number: (it's different between IOS and Andriod) IOS showing in +60 Andriod showing in +1 Please set default country to +1 | Yes | N |  | 100% |  |  | 2018-03-23 |  | Closed | Open | IOS is follow phone region setting Now Andriod follow Phone Language (to be defind) 24 Jul, CS: 已经解释过很多次，安卓和苹果本来就不一样，安卓的做法是语言和国家在一起切换，苹果是分开切换的。 24 JUl, CS: You can consider to use either of these API to address the issue: locale OR TelephonyMaN/Ager. Please refer to https://stackoverflow.com/questions/11293642/how-can-i-get-my-android-device-country-code-without-using-gps |  |  |  |  | The display of Country Code is selected according to the language and region in the common Settings of mobile phones | OK, follow phone setting
321 | Hamburger Menu | 2018-06-14 | SK | iOS V1.2 (1236), Android | 3 | in FAQ the icons are not added in but instead shows my text e.g. (show icon of hamburger menu) | Yes | N |  | 100% |  |  |  |  | Open | Open | 24 Jul, CS: this was not fixed properly. Hence this issue is re-opened. | 2018-08-03
341 | Maps | 2018-06-20 | Marjon | iOS V1.2 (1238) | 3 | In radio setting the scroll ruler need to change. When scroll to min and max value the ruler shall not show. Please follow TALKABOUT_APP_Wireframes_20180620 slide#119 | Yes | Y | N | 100% |  |  |  |  | Duplicated | N/A | Still same in 1240 Still same in 1243 18 jul, XY: new feature ,will not support Duplicated to #120 26 Jul, Marjon: Has to be fixed by D2 | Same as #120 |  | 这一项，之前已经反复跟设计公司的反复确认过，设计公司也确认就是这样做。邮件为证。 后续这个部分设计公司并没有更新文档。遇到冲突，我们只能以 TALKABOUT_APP_VI_Design TALKABOUT_APP_Wireframes 为准。 comment 提到的文档UI APPS Feedback IOS V1.1 (20) 20180220.pptx 这个文档只能作为moto跟设计公司讨论的初稿，并不能作为我们开发的依据，因为这个文档跟最终设计本来就很多不一样。如第8页 slider bar。
345 | Hamburger Menu | 2018-06-20 | Marjon | iOS V1.2 (1238) | 3 | File N/Ame cannot be seen in full. Please change to 2 rows. | Yes | N | Y | 100% |  |  |  |  | Open | N/A | Still same in 1240 Still same in 1243 18 jul, XY: new feature ,will not support 24 Jul, FT: the file N/Ame cannot seen in full and we only request to change to 2 lines. This is solving issue to eN/Able user can see the file N/Ame. 26 Jul, CS: Denied and come back that this is Enh | needs 1 week after cost is locked down
389 | Chat | 2018-07-03 | SK | Android V1.9 | 3 | Different behavior compare to IOS: -> added a new member, now tab to chat with him... but i did't type any message, just back to chat home page, i cannot see the new added member N/Ame display at Chat Home Page, but IOS has. | Yes | N |  | 100% |  |  |  |  | N/A | Open |  | 2018-08-03
393 | Maps | 2018-07-04 | Marjon | iOS (1244), Android | 3 | I am sending a track to a group, only other phone online is without account. The track is not received on the phone without account but the track shows successfully send on the sender phone | Yes | N |  | 100% |  |  |  |  | Pending verification | Open | 18 jul, XY: not duplicate 24 Jul, CS: This is an issue, not enhancement. 24 Jul, XY: 1249已经解决 | 2018-08-03
417 | Maps | 2018-07-06 | BETA | iOS 1244 | 3 | Maps sharing: share icon on my maps uses not the standard share icon for IOS users (box with arrow out) forgot conclusion of this, but believe was discussed before. | Yes | Y | [6 empty] | Open | N/A | not understand 10 Jul, CS: will standardize the icon 18 jul, XY: fixed 1.2 47 18 Jul, CS: icon still not the box with arrow out 26 Jul, XY, This is new feature , not reflecetd in latest VI 26 Jul, Marjon: UI no tclearly defined, Has to be updated to iOS N/Ative icon | 2018-08-03 |  | 未跟客户收费 | android 1 week , iOS 1 week, test 0.5week, document 0.2week
428 | Settings | 2018-07-13 | BETA | iOS (1244), Android | 3 | Radio settings: Allow a touch and hold/slide left or right to scrub faster to higher numbers. Channel and Sub Code didn't always hold on choice after moving to next adjustment. Sometimes would "rubber band" to another number after release or pause.This also happened on Call tone and VOX. | Yes | N | [6 empty] | Open | Open | 18 jul, XY: app need follow radio , It's normal case 24 Jul CS: This is a Beta feedback issue, need to be fixed. Video uploaded at: https://drive.google.com/open?id=1yZSnE7TCkeLk_vrTPStu9YEf_6tmpmmH | 2018-08-10
429 | On Boarding | 2018-07-13 | BETA | iOS (1244) | 2 | First make sure BT is disbaled at control center. Next go to Settings and eN/Able BT. Then Launch Talkabout app and observed that setup is stuck at EN/Abling BT page. | Yes | N | [6 empty] | Open | N/A | 18 Jul, XY: iOS 11 bug, no workaround solution 18 Jul, SK: when issue is reproduced, try pair with other BT device, it can be paired 24 Jul, XY: 这个问题是IOS 系统的问题，参考https://forums.developer.apple.com/message/300002#300002 24 Jul, CS: We urge to look for workaround solution, as we did not see this issue when pairing with BT headset. 31 JUl, CS: request SK to send steps to XY | 2018-08-15
430 | Maps | 2018-07-17 | BETA | iOS, Android | 3 | Change the View icon in Maps (second icon at right side) to Group Member icon. | Yes | Y | [6 empty] | Open | Open | 17, Jul,XY: new feature, not supported 26 Jul, Marjon: Has to be fixed by D2 | needs 1 week after cost is locked down
431 | Settings | 2018-07-18 | CS | iOS, Android | 3 | Update Emergency settings wordings at the second paragraph: Long press Emergency Alert Button on your radio for 3 seconds to send audible siren on the radios within range (for 8 seconds) followed by 22 seconds of the channel to be opened to transmit any sound. This is followed by emergency message to be sent out. In addition to this, your current location will be sent and reflected in Group members Maps View. | Yes | N | [6 empty] | Open | Open | 24 Jul, CS: Issue sent to Auctus but no commitment received yet. 24 Jul, XY: iOS 1.2 49 会解决，安卓2.5 会解决 | 2018-08-03
435 | Maps | 2018-07-24 | SK | Android V2.4 | 2 | observed force shutdown while Geofence activated and out of boundary. with Andriod phone Huawei (Andriod 4.4.2) | Yes | N | [6 empty] | N/A | Open |  | 2018-08-03
437 | Setup | 2018-07-26 | BETA | iOS (1244) | 3 | first couple of onboarding screens are flashing too fast | Yes | N | [6 empty] | Open | Open | 26 Jul, CS: confirmed it is an issue, video uploaded at Baidu 31 Jul, CS: Resend to XY
438 | maps | 2018-07-26 | BETA | Android V2.3 | 4 | Difficulty with understanding on how to download maps, Add a tip about where to find help Include education tip as last tip in onboarding: Familiarize yourself with the app! Go to Help menu for FAQ’s and tutorial videos. | Yes | Y | [6 empty] | Open | Open | 26 Jul, CS: This is user familiarity issue. Adding note to FAQ? Jul 27:MM. This is crucial to ensure users accept the app as useful. I will send seperate email to Lee Sun asking her to work on this. | After cost and UI lock down, need 1.5 weeks
441 | radio settings | 2018-07-26 | BETA | Android V2.3 | 3 | Fix slider to go negative per alpha test | Yes | Y | [6 empty] | Open | Open | 26 Jul, CS: Min and Max shall be truncated, follow the solution propsed in #120 | Same as #120
443 |  | 2018-07-26 | BETA | Android V2.3 | 3 | The notification badge (blue dot with count) is not centered on the list. | Yes | N | [6 empty] | Open | Open | 26 Jul, CS: can clarify further? Right now is at bottom right corner, following VI. 26 Jul. MM coming from the UI/UX team (Maggie Wang) was hoping that Lee Sun speaks this language and understands what she meant. I send a follow up email to ask for clarification 27 Jul. See screen shot in consolidated list. seems a bug for some phones. 31 Jul, CS: Pixel 1, Android 8 | 2018-08-10
444 | FAQs | 2018-07-26 | BETA | Android V2.3, iOS | 4 | FAQ's are not very clean and look a bit amateuristic, Improve lay out /font etc. | Yes | N | [6 empty] | Open | Open | 26 Jul, CS: redesign FAQ VI ? | time TBD depends on new layout design to determine the effort
445 | Members | 2018-07-26 | BETA | Android V2.3, iOS | 4 | Sections not understood: What is a group | Yes | N | [6 empty] | Open | Open | 26 Jul, CS: This is user familiarity issue. Adding note to FAQ? If yes, then FAQ contents MUST be locked down before 3-Aug-18 | Pending MSI to lock down FAQ content
446 | Members | 2018-07-26 | BETA | Android V2.3, iOS | 4 | Sections not understood: What is a member | Yes | N | [6 empty] | Open | Open | 26 Jul, CS: This is user familiarity issue. Adding note to FAQ? If yes, then FAQ contents MUST be locked down before 3-Aug-18 | Pending MSI to lock down FAQ content
447 | Maps | 2018-07-26 | BETA | Android V2.3, iOS | 4 | Sections not understood: What is a geofence | Yes | N | [6 empty] | Open | Open | 26 Jul, CS:: This is user familiarity issue. Adding note to FAQ? If yes, then FAQ contents MUST be locked down before 3-Aug-18 | Pending MSI to lock down FAQ content
448 | Maps | 2018-07-26 | BETA | Android V2.3, iOS | 4 | Sections not understood: How to download a map | Yes | N | [6 empty] | Open | Open | 26 Jul, CS:: This is user familiarity issue. Adding note to FAQ? If yes, then FAQ contents MUST be locked down before 3-Aug-18 | Pending MSI to lock down FAQ content
449 | Maps | 2018-07-26 | BETA | Android V2.3, iOS | 4 | Sections not understood: How to reN/Ame tracks, maps, pins | Yes | N | [6 empty] | Open | Open | 26 Jul, CS:: This is user familiarity issue. Adding note to FAQ? If yes, then FAQ contents MUST be locked down before 3-Aug-18 | Pending MSI to lock down FAQ content
450 | Menu /N/Avigation | 2018-07-26 | BETA | Android V2.3, iOS | 4 | Sections not understood: Multiple users indicated not to be able to figure out how to get back to chat menu | Yes | N | [6 empty] | Open | Open | 26 Jul, CS:: This is user familiarity issue. Adding note to FAQ? If yes, then FAQ contents MUST be locked down before 3-Aug-18 | Pending MSI to lock down FAQ content
451 | Maps | 2018-07-26 | BETA | Android V2.3, iOS | 4 | Sections not understood: total ascent (how it is calculated) | Yes | N | [6 empty] | Open | Open | 26 Jul, CS: This is user familiarity issue. Adding note to FAQ? If yes, then FAQ contents MUST be locked down before 3-Aug-18 | Pending MSI to lock down FAQ content
452 | Maps | 2018-07-26 | BETA | Android V2.3, iOS | 4 | Sections not understood: how to view the statistics (requires clicking on the icon) but not intuitive | Yes | N | [6 empty] | Open | Open | 26 Jul, CS: This is user familiarity issue. Adding note to FAQ? If yes, then FAQ contents MUST be locked down before 3-Aug-18 | Pending MSI to lock down FAQ content
453 | Maps | 2018-07-26 | BETA | Android V2.3, iOS | 4 | Sections not understood: who receives my location when I tap on locate icon | Yes | N | [6 empty] | Open | Open | 26 Jul, CS: This is user familiarity issue. Adding note to FAQ? If yes, then FAQ contents MUST be locked down before 3-Aug-18 | Pending MSI to lock down FAQ content
454 | Maps | 2018-07-26 | BETA | Android V2.3, iOS | 4 | Sections not understood: icon of offline map and track is confusing | Yes | N | [6 empty] | Open | Open | 26 Jul, CS: This is user familiarity issue. Adding note to FAQ? If yes, then FAQ contents MUST be locked down before 3-Aug-18 | Pending MSI to lock down FAQ content
455 | Maps | 2018-07-26 | BETA | Android V2.3, iOS | 4 | Sections not understood: why are offline map and track features not available | Yes | N | [6 empty] | Open | Open | 26 Jul, CS: This is user familiarity issue. Adding note to FAQ? If yes, then FAQ contents MUST be locked down before 3-Aug-18 | Pending MSI to lock down FAQ content
456 | Maps | 2018-07-26 | BETA | Android V2.3, iOS | 4 | Sections not understood: why they can not send an off line map off grid | Yes | N | [6 empty] | Open | Open | 26 Jul, CS: This is user familiarity issue. Adding note to FAQ? If yes, then FAQ contents MUST be locked down before 3-Aug-18 | Pending MSI to lock down FAQ content
458 | Maps | 2018-07-26 | BETA | Android V2.3, iOS | 4 | Sections not understood: How to share a map (this was iOS user so hopefully fixing the area on where to click and using the familiar share icon will improve this | Yes | N | [6 empty] | Open | Open | 26 Jul, CS: This is user familiarity issue. Adding note to FAQ? If yes, then FAQ contents MUST be locked down before 3-Aug-18 | Pending MSI to lock down FAQ content
461 |  | 2018-07-26 | BETA | Android V2.3, iOS | 3 | Minimum 3 members (appear in the toast) in a group is also not clear. I can select 2 people and the create group screen is saying Total 2 members and I'm allowed to proceed. Also N/Ame should be optioN/Al and I could always go back to add the N/Ame. | Yes | N | [6 empty] | Open | Open | 26 Jul, CS: can clarify further? 26 Jul, mm: yes, when you create a group a pop up says you need minimum of 3 members but allos you to create a group while only 2 members are added, so message is not correct. Should say: Minim 3 members including yourself. Or Minimum 2 members. 27 Jul: Please change to: Minimum 2 members are required. (also corrects the grammar) | 2018-08-10
469 |  | 2018-07-26 | BETA | Android V2.3, iOS | 3 | very unclear to various users what using an ID means. Various users tried to send messages using a phone number to users that chose to set up their account with an ID. The fact that that is not possible is not understood. some also wanted to type a N/Ame in field using ID and where frustrated that only the number keyboard comes up. They confused using ID with User ID or user N/Ame. At the very least we need to improve on the ADD NEW MEMBER screen to make it clear what using a phone number or using ID means (using ID is the account ID assigned to the user during set up) Also assign member N/Ame is not clear how that relates to the two above. This seems to be stumbling block for some of the beta users and they think it is not working whereas it is more an issue of not understanding the app. UI team needs to make proposal on how to make this more intuitive. | Yes | Y | [6 empty] | Open | Open | 26 Jul, CS: This is user familiarity issue. Adding note to FAQ? If yes, then FAQ contents MUST be locked down before 3-Aug-18 Otherwise, need to redefine a new VI to cater for new appearance. 27 Jul, mm: this is big issue for multiple beta testers. adding to FAQ will not solve. Need to redesign the adding member screen and also add wording when setting up the account. Will send email to Lee Sun 31 Jul, CS: breakdowns of these items are shown in #485 and 487 | pending for ID lock down
478 |  | 2018-07-28 | BETA | Android V2.3, iOS | 4 | location pin can only be shared over radio, not network but no indication in the app so users are confused by it. short term we have to have a pop up warning if they try to share without radio network that it can only be done with radio network. Vise versa when you share map and track we need to tell them network is required. | Yes | Y | [6 empty] | Open | Open | 31 Jul, XY: costing is required | Needs 1 week after cost lock down.
480 |  | 2018-07-28 | BETA | Android V2.3, iOS | 3 | Time stamps reflecting updated status even if offline | Yes | N | [6 empty] | Open | Open | What I don't understand is that the time stamp of my location, even though I am off line, is up to date to today? What is the behaviour of the time stamp supposed to be? Should it not reflect the most up to date and latest online status? So user can determine if the location is current and if user is offline when he went offline and where he was. On the other phone it does do that but on one of the phones it shows a recent online status without the radio connected (nor able to send member update to the other radio since that one was not connected either. Please explain. Seems like a bug needing fixing. If so, that bug should be a yes before D2. 31 Jul, XY: fixed in Android V2.4 SK please to confirm if it is fixed in Android 2.4 and for iOS check if this issue is seen. |  | image
481 |  | 2018-07-28 | BETA | Android V2.3 | 3 | redirect the link for NO T800 yet on the home welcome screen to: shop.motorolasolutions.com/T800 | Yes | N | [6 empty] | Open | Open |  | 2018-08-10
482 | On Boarding | 2018-07-28 | SK | Android V2.4 | 3 | Pop up Message/Notification different compared to IOS - No data/ internet - No Location service | Yes | N | N | [6 empty] | Open |  | 2018-08-10
483 | Maps | 2018-07-30 | SK | Android V2.4 | 3 | Location Pin icon displaying in Map not accurate. where the member already off line but icon not in dim colour. | Yes | N | N | [6 empty] | Open |  | 2018-08-10
484 | Help and Support | 2018-07-31 | CS | iOS, Android | 4 | Fonts under FAQ and Support need to be standardized using Roboto font | Yes | N | N | [5 empty] | Open | Open |  | 2018-08-10
485 | Settings | 2018-07-31 | LeeSun | iOS, Android | 4 | When adding member using non phone number, then you will move to next item which is adding ID. The missing link is the Cursor Bar would be better if it could jump down to Assign Member N/Ame and keyboard pop up after user done with ID number. | Yes | Y | N | [5 empty] | Open | Open |  | waiting for costing (around 1.5 weeks effort)
486 | Bluetooth Connection | 2018-07-31 | SK | Android V2.4 | 2 | Different behavior compare to IOS: -> Andriod - After kill APP, the bluetooth connection will auto connect back directly. -> IOS - After Kill the APP, the bluetooth connection will not connect back until App reopen (bluetooth connection in Radio showing pending to pairing). | Yes | N | [7 empty] | Open | 31 Jul, XY: need to study further | 2018-08-10
488 | Add members | 43312 | LeeSun | iOS, Android | 4 | Add one liner below the ID field - "ID numbers only available for user signed in without account." | Yes | Y | [6 empty] | Open | Open |  | waiting for costing (around 1.5 weeks effort)

## Costing_D2 (hidden)
No | Area | Reporting Date | Reported By | Observed Point | Severity | Issue | Required To Fix by D2 (20-Aug-18) | Enhancement | Green Light | Status IOS | Status Andriod | comment | Planned Close Date | Links | Next To Do | reply comment | 工作量
120 | Radio Settings | 2018-02-20 | LS | iOS V1.1(20), Android V2.3 | 3 | The Channel, Sub Code & Call Tone scroll bar is hard to know what is the upper and lower limit. May need N/A to suggest | Yes | Y | P | Open | N/A | Still not correct 6/29 4 Jul, XY: XY: already followed the latest UI doc, LS pls confirm 18 jul, XY: new feature , will not support 24 Jul, FT: we have feedback this on 20-Feb-18 together with ID feedback file (see attached slide#18). You should not come back now saying you will not fix it. 26 Jul, XY: Denied and come back that this is Enh 31 Jul, XY: APP independent, not related to radio SW. 1 Aug CS: This should not considered as Enhget email from LeeSun on the evidence. Please refer to links for email evidences. | needs 2 weeks after cost is locked down | https://drive.google.com/open?id=1MlZzceu4eNHeSXCuLgQlgm_RB7sBmjJk | SiauFong please mention to Auctus that this was highlighted to them back in Feb, as shown in email, thus may not be an Enh item. TQ | 这一项，之前已经反复跟设计公司的反复确认过，设计公司也确认就是这样做。邮件为证。 后续这个部分设计公司并没有更新文档。遇到冲突，我们只能以 TALKABOUT_APP_VI_Design TALKABOUT_APP_Wireframes 为准。 comment 提到的文档UI APPS Feedback IOS V1.1 (20) 20180220.pptx 这个文档只能作为moto跟设计公司讨论的初稿，并不能作为我们开发的依据，因为这个文档跟最终设计本来就很多不一样。如第8页 slider bar。 | android 1 week , iOS 1 week, test 0.5week, document 0.2week
345 | Hamburger Menu | 2018-06-20 | Marjon | iOS V1.2 (1238) | 3 | File N/Ame cannot be seen in full. Please change to 2 rows. | Yes | Y | P | Open | N/A | Still same in 1240 Still same in 1243 18 jul, XY: new feature ,will not support 24 Jul, FT: the file N/Ame cannot seen in full and we only request to change to 2 lines. This is solving issue to eN/Able user can see the file N/Ame. 26 Jul, CS: Denied and come back that this is Enh | needs 1 week after cost is locked down |  |  |  | android 0.25 week , iOS 0.25week, test 0.25week, document 0.05week
430 | Maps | 2018-07-17 | BETA | iOS, Android | 3 | Change the View icon in Maps (second icon at right side) to Group Member icon. | Yes | Y | P | Open | Open | 17, Jul,XY: new feature, not supported 26 Jul, Marjon: Has to be fixed by D2 1 Aug, CS: This is not captured in the SRS or VI previously | needs 1 week after cost is locked down |  |  |  | android 0.25 week , iOS 0.25week, test 0.25week, document 0.05week
438 | maps | 2018-07-26 | BETA | Android V2.3 | 4 | Difficulty with understanding on how to download maps, Add a tip about where to find help Include education tip as last tip in onboarding: Familiarize yourself with the app! Go to Help menu for FAQ’s and tutorial videos. | Yes | Y | P | Open | Open | 26 Jul, CS: This is user familiarity issue. Adding note to FAQ? Jul 27:MM. This is crucial to ensure users accept the app as useful. I will send seperate email to Lee Sun asking her to work on this. 1 Aug, LiN/Ar: we will ask SiauFong to ask Auctus provide quotation based on one paragraph and 5 icons in FAQ | After cost and UI lock down, need 1.5 weeks
445 | Members | 2018-07-26 | BETA | Android V2.3, iOS | 4 | Sections not understood: What is a group | Yes | N | N | Open | Open | 26 Jul, CS: This is user familiarity issue. Adding note to FAQ? If yes, then FAQ contents MUST be locked down before 3-Aug-18 1 Aug, CS: | Pending MSI to lock down FAQ content |  | Marjon to provide complete FAQ content by 3-Aug-18
446 | Members | 2018-07-26 | BETA | Android V2.3, iOS | 4 | Sections not understood: What is a member | Yes | N | N | Open | Open | 26 Jul, CS: This is user familiarity issue. Adding note to FAQ? If yes, then FAQ contents MUST be locked down before 3-Aug-18 | Pending MSI to lock down FAQ content |  | Marjon to provide complete FAQ content by 3-Aug-18
447 | Maps | 2018-07-26 | BETA | Android V2.3, iOS | 4 | Sections not understood: What is a geofence | Yes | N | N | Open | Open | 26 Jul, CS:: This is user familiarity issue. Adding note to FAQ? If yes, then FAQ contents MUST be locked down before 3-Aug-18 | Pending MSI to lock down FAQ content |  | Marjon to provide complete FAQ content by 3-Aug-18
448 | Maps | 2018-07-26 | BETA | Android V2.3, iOS | 4 | Sections not understood: How to download a map | Yes | N | N | Open | Open | 26 Jul, CS:: This is user familiarity issue. Adding note to FAQ? If yes, then FAQ contents MUST be locked down before 3-Aug-18 | Pending MSI to lock down FAQ content |  | Marjon to provide complete FAQ content by 3-Aug-18
449 | Maps | 2018-07-26 | BETA | Android V2.3, iOS | 4 | Sections not understood: How to reN/Ame tracks, maps, pins | Yes | N | N | Open | Open | 26 Jul, CS:: This is user familiarity issue. Adding note to FAQ? If yes, then FAQ contents MUST be locked down before 3-Aug-18 | Pending MSI to lock down FAQ content |  | Marjon to provide complete FAQ content by 3-Aug-18
450 | Menu /N/Avigation | 2018-07-26 | BETA | Android V2.3, iOS | 4 | Sections not understood: Multiple users indicated not to be able to figure out how to get back to chat menu | Yes | N | N | Open | Open | 26 Jul, CS:: This is user familiarity issue. Adding note to FAQ? If yes, then FAQ contents MUST be locked down before 3-Aug-18 | Pending MSI to lock down FAQ content |  | Marjon to provide complete FAQ content by 3-Aug-18
451 | Maps | 2018-07-26 | BETA | Android V2.3, iOS | 4 | Sections not understood: total ascent (how it is calculated) | Yes | N | N | Open | Open | 26 Jul, CS: This is user familiarity issue. Adding note to FAQ? If yes, then FAQ contents MUST be locked down before 3-Aug-18 | Pending MSI to lock down FAQ content |  | Marjon to provide complete FAQ content by 3-Aug-18
452 | Maps | 2018-07-26 | BETA | Android V2.3, iOS | 4 | Sections not understood: how to view the statistics (requires clicking on the icon) but not intuitive | Yes | N | N | Open | Open | 26 Jul, CS: This is user familiarity issue. Adding note to FAQ? If yes, then FAQ contents MUST be locked down before 3-Aug-18 | Pending MSI to lock down FAQ content |  | Marjon to provide complete FAQ content by 3-Aug-18
453 | Maps | 2018-07-26 | BETA | Android V2.3, iOS | 4 | Sections not understood: who receives my location when I tap on locate icon | Yes | N | N | Open | Open | 26 Jul, CS: This is user familiarity issue. Adding note to FAQ? If yes, then FAQ contents MUST be locked down before 3-Aug-18 | Pending MSI to lock down FAQ content |  | Marjon to provide complete FAQ content by 3-Aug-18
454 | Maps | 2018-07-26 | BETA | Android V2.3, iOS | 4 | Sections not understood: icon of offline map and track is confusing | Yes | N | N | Open | Open | 26 Jul, CS: This is user familiarity issue. Adding note to FAQ? If yes, then FAQ contents MUST be locked down before 3-Aug-18 | Pending MSI to lock down FAQ content |  | Marjon to provide complete FAQ content by 3-Aug-18
455 | Maps | 2018-07-26 | BETA | Android V2.3, iOS | 4 | Sections not understood: why are offline map and track features not available | Yes | N | N | Open | Open | 26 Jul, CS: This is user familiarity issue. Adding note to FAQ? If yes, then FAQ contents MUST be locked down before 3-Aug-18 | Pending MSI to lock down FAQ content |  | Marjon to provide complete FAQ content by 3-Aug-18
456 | Maps | 2018-07-26 | BETA | Android V2.3, iOS | 4 | Sections not understood: why they can not send an off line map off grid | Yes | N | N | Open | Open | 26 Jul, CS: This is user familiarity issue. Adding note to FAQ? If yes, then FAQ contents MUST be locked down before 3-Aug-18 | Pending MSI to lock down FAQ content |  | Marjon to provide complete FAQ content by 3-Aug-18
478 |  | 2018-07-28 | BETA | Android V2.3, iOS | 4 | location pin can only be shared over radio, not network but no indication in the app so users are confused by it. short term we have to have a pop up warning if they try to share without radio network that it can only be done with radio network. Vise versa when you share map and track we need to tell them network is required. | Yes | Y | p | Open | Open | 31 Jul, XY: costing is required 1 Aug, CS: Only Track and offline maps can be shaerd without radio, since it is sent via cloud. For Location Pin, it would require radio network to be present. So propose to put up Pop Up msg for Location Pin sharing when radio is disconnected. | Needs 1 week after cost lock down.
485 | Settings | 2018-07-31 | LeeSun | iOS, Android | 4 | When adding member using non phone number, then you will move to next item which is adding ID. The missing link is the Cursor Bar would be better if it could jump down to Assign Member N/Ame and keyboard pop up after user done with ID number. | Yes | Y | p | Open | Open |  | waiting for costing (around 1.5 weeks effort)
488 | Add members | 2018-07-31 | LeeSun | iOS, Android | 4 | Add one liner below the ID field - "For members signed in without account, ask for their ID. " | Yes | Y | p | Open | Open |  | waiting for costing (around 1.5 weeks effort)
489 | On Boarding | 2018-07-31 | Marjon | iOS, Android | 4 | Add a tip (last tip during onboarding): MSI will update VI / wireframes and share with Auctus, then Auctus shall add the screen accordingly | Yes | Y | N | Open | Open | 31 July, M": Familiarize yourself with the app! Go to Help and Support menu for FAQ’s and tutorial videos. 31 July, LeeSun: Ok. Will consider and will be added new task for Right Click. Could be additioN/Al cost incured.
490 | On Boarding | 2018-07-31 | Marjon | iOS, Android | 4 | add tutorial videos (working with GCD team to create, just have to add the links to new section under Help and Support. I suggest to add Tutorials under FAQ and Troubleshooting (between that and Send Feedback). Aucus will just need to update FAQ content with video links when it is ready. | Yes | N | N | Open | Open | 31 Jul, LS: Tie to #1. Please work with GCD team on required video. Please share your thought on how you would envision this video. 1 Aug, M: I will share with you seperately.
491 | On Boarding | 2018-07-31 | Marjon | iOS, Android | 4 | Improve on instant explaN/Ation for those things fed back during beta testing with pop up's rather than rely on FAQ's. Ultimately we take all the feedback given during beta testing in to account and try to solve the intuitiveness of the app so not having to lean on pop ups and FAQ's etc. but that will have to be done in phases, some as soon as possible others in new releases. MSI will update VI / wireframes and share with Auctus, then Auctus shall add the screen accordingly | Yes | Y | N | Open | Open | 31 Jul, LS: Frequent pop up could cause annoyance to some user. We need to know what is the percentage of user is having problem with our apps. Did they really read through the tips or they just simply click away? 1 Aug, LS: My guess is the latter . I think it is key to strike a balance. FAQ's and Tips are not that common in apps, people expect it to be intuitive. However if something is really hard, we need to update them in the best possible way. Moderate use of pop ups is ok. 1 Aug CS: To Marjon, for those scene that require pop up messages, please identify in VI slides and poin point which flow require additioN/Al pop up, and spell out the exect message contents. |  |  | exclude this item for costing as it is unclear as of how many pop up messages are needed.
438
445
446
447
448
449
450
451
452
453
454
455
456
469
478
485
488
489
490
491

## Sheet5 (hidden)
No | Area | Reporting Date | Reported By | Observed Point | Severity | Issue
414 | Location sharing | 2018-07-06 | BETA | iOS 1244 | 1 | Location sharing: even though GPS showed up, did not resulted in sharing my location with others in my group.
419 | Maps | 2018-07-06 | BETA | iOS 1244 | 1 | Pin sharing: when trying to share my location and chat it wouldn't pull up map just black map with pin. Did send it and recipient pulled up a black map with pin
390 | Bluetooth Connection | 2018-07-04 | SK | iOS V1.2 (1244) | 2 | Bluetooth connection with Radio for a few times in RANGE. Step: Moving out of bluetooth connection range around 15m. Moving in and out for several time, sometimes App cannot auto reconnect back with Radio. User need to OFF then ON again bluetooth, or re-Pair again the Radio.
413 | Location sharing | 2018-07-06 | BETA | iOS 1244 | 2 | Location sharing: delay in showing gps on screen when you press the easy pairing button
429 | On Boarding | 2018-07-13 | BETA | iOS (1244) | 2 | First make sure BT is disbaled at control center. Next go to Settings and eN/Able BT. Then Launch Talkabout app and observed that setup is stuck at EN/Abling BT page.
120 | Radio Settings | 2018-02-20 | LS | iOS V1.1(20) | 3 | The Channel, Sub Code & Call Tone scroll bar is hard to know what is the upper and lower limit. May need N/A to suggest
225 | Maps | 2018-02-27 | Marjon | iOS V1.1(20), Android V1.4(20) | 3 | My Maps --> My Tracks --> for track recording can we alert user if they have not moved for a while? E.g. Would you like to pause recording?
308 | Maps | 2018-05-31 | SK | iOS V1.2 (1231), Android | 3 | Before purchase the Dark and Light Maps view. I can see the Dark and Light selection in Download Offline Map (Selection Maps Styles)
316 | MAPS | 2018-06-05 | LiN/Ar | iOS V1.2 (1233) | 3 | Maps view in Satellite style, it will black out once zoom in. (Only PeN/Ang island)
321 | Hamburger Menu | 2018-06-14 | SK | iOS V1.2 (1236), Android | 3 | in FAQ the icons are not added in but instead shows my text e.g. (show icon of hamburger menu)
345 | Hamburger Menu | 2018-06-20 | Marjon | iOS V1.2 (1238) | 3 | File N/Ame cannot be seen in full. Please change to 2 rows.
371 | Chat | 2018-07-02 | LS | iOS V1.2 (1243), Android | 3 | The chat bubble corner radius are not perfect round. It is distorted/stretched.
393 | Maps | 2018-07-04 | Marjon | iOS (1244), Android | 3 | I am sending a track to a group, only other phone online is without account. The track is not received on the phone without account but the track shows successfully send on the sender phone
417 | Maps | 2018-07-06 | BETA | iOS 1244 | 3 | Maps sharing: share icon on my maps uses not the standard share icon for IOS users (box with arrow out) forgot conclusion of this, but believe was discussed before.
428 | Settings | 2018-07-13 | BETA | iOS (1244), Android | 3 | Radio settings: Allow a touch and hold/slide left or right to scrub faster to higher numbers. Channel and Sub Code didn't always hold on choice after moving to next adjustment. Sometimes would "rubber band" to another number after release or pause.This also happened on Call tone and VOX.
431 | Settings | 2018-07-18 | CS | iOS, Android | 3 | Update Emergency settings wordings at the second paragraph: Long press Emergency Alert Button on your radio for 3 seconds to send audible siren on the radios within range (for 8 seconds) followed by 22 seconds of the channel to be opened to transmit any sound. This is followed by emergency message to be sent out. In addition to this, your current location will be sent and reflected in Group members Maps View.
Android
No | Area | Reporting Date | Reported By | Observed Point | Severity | Issue
435 | Maps | 2018-07-24 | SK | Android V2.4 | 2 | observed force shutdown while Geofence activated and out of boundary. with Andriod phone Huawei (Andriod 4.4.2)
124 | On Boarding | 2018-02-21 | LS | Android V1.4(20) | 3 | Term and Conditions - the background color is wrong. The last sentence will blink when I tap. It should not be. If we just want the user to tap AGREE button.
134 | My Members | 2018-02-21 | LS | Android V1.4(20) | 3 | After click Dustbin, the member list should not have the line on the most bottom list item.
139 | Help and Support | 2018-02-21 | LS | Android V1.4(20) | 3 | Inside the list, the Help and Support list should not have icons. The last list menu should not show line.
225 | Maps | 2018-02-27 | Marjon | iOS V1.1(20), Android V1.4(20) | 3 | My Maps --> My Tracks --> for track recording can we alert user if they have not moved for a while? E.g. Would you like to pause recording?
280 | Chat | 2018-03-04 | SK | iOS V1.1(20), Android V1.4(20) | 3 | >Chat > Add New member > Using phone number: (it's different between IOS and Andriod) IOS showing in +60 Andriod showing in +1 Please set default country to +1
308 | Maps | 2018-05-31 | SK | iOS V1.2 (1231), Android | 3 | Before purchase the Dark and Light Maps view. I can see the Dark and Light selection in Download Offline Map (Selection Maps Styles)
316 | MAPS | 2018-06-05 | LiN/Ar | iOS V1.2 (1233) | 3 | Maps view in Satellite style, it will black out once zoom in. (Only PeN/Ang island)
321 | Hamburger Menu | 2018-06-14 | SK | iOS V1.2 (1236), Android | 3 | in FAQ the icons are not added in but instead shows my text e.g. (show icon of hamburger menu)
342 | Radio Settings | 2018-06-20 | Marjon | iOS V1.2 (1238), Android | 3 | This is not issue, this is UI enhancement: After set emergency message and click SAVE, the pop up message shall shows 'message saved' and OK. OrigiN/Ally was 'message saved' and DISMISS.
371 | Chat | 2018-07-02 | LS | iOS V1.2 (1243), Android | 3 | The chat bubble corner radius are not perfect round. It is distorted/stretched.
389 | Chat | 2018-07-03 | SK | Android V1.9 | 3 | Different behavior compare to IOS: -> added a new member, now tab to chat with him... but i did't type any message, just back to chat home page, i cannot see the new added member N/Ame display at Chat Home Page, but IOS has.
393 | Maps | 2018-07-04 | Marjon | iOS (1244), Android | 3 | I am sending a track to a group, only other phone online is without account. The track is not received on the phone without account but the track shows successfully send on the sender phone
406 | Bluetooth Connection | 2018-07-08 | SK | Android V2.2 IOS V1.2 (1244) | 3 | Radios and Phone connected in standby Sometimes will auto disconnect then reconnect. heppened half hour once.
425 | Maps | 2018-07-09 | SK | Android V2.3 | 3 | Geofence Alert will disappear just click any place on screen, but not happen in IOS.
428 | Settings | 2018-07-13 | BETA | iOS (1244), Android | 3 | Radio settings: Allow a touch and hold/slide left or right to scrub faster to higher numbers. Channel and Sub Code didn't always hold on choice after moving to next adjustment. Sometimes would "rubber band" to another number after release or pause.This also happened on Call tone and VOX.
431 | Settings | 2018-07-18 | CS | iOS, Android | 3 | Update Emergency settings wordings at the second paragraph: Long press Emergency Alert Button on your radio for 3 seconds to send audible siren on the radios within range (for 8 seconds) followed by 22 seconds of the channel to be opened to transmit any sound. This is followed by emergency message to be sent out. In addition to this, your current location will be sent and reflected in Group members Maps View.
436 | Settings | 2018-07-25 | SK | Android V2.4 | 3 | Radio disconnected and reconnect back in a short while when entering MYSELF open Camera, then return to menu.

## BETA (hidden)
No | Area | Reporting Date | Reported By | Observed Point | Severity | Issue | Required To Fix by D2 (20-Aug-18) | Enhancement | Close Date on version? | Status IOS | Status Andriod | comment | Planned Close Date | Links
411 | Bluetooth Connection | 2018-07-06 | BETA | iOS 1244 | 1 | Bluetooth: during hike frequent chirping of radio (2 chirps) followed by bluetooth beep. radio and phone would not disconnect indefiN/Ate but very disturbing. 1 out of the 3 radio/app pairings did this for a short very frequent (every 5 min). Later was less frequent (maybe due to apple watch also using bluetooth? but defiN/Ately all radios did this. Radios all on lock and in same backpack as the phones so can not be because of bluetooth distance | Yes |  | 19 July 2018 IOS V1.2 (1247) | Closed | N/A | same issue found in issue 11, and issue 406, where XY said is due to phone bluetooth connectivity. 10 jul, XY: Radio BT will stay even radio is in idle mode. But if radio BT connection is lost, after certain duration, BT will be shut down. 11 Jul, Marjon: The most freuqent occurance was on iPhone 8 but also happened on iPhone 6s from the other two hikers but less frequent. 18 jul, XY: app issue fixed 1.2 47
412 | Bluetooth Connection | 2018-07-06 | BETA | iOS 1244 | 1 | Bluetooth: During 4 hour hike radios all radios got disconnected and not reconnected to the point bluetooth on radio turned off. | Yes |  | 19 July 2018 IOS V1.2 (1247) | Closed | N/A | not understand 10 Jul, CS: Radio BT will stay even radio is in idle mode. But if radio BT connection is lost, after certain duration, BT will be shut down. 11 Jul, Marjon: Radio and phone were in same backpack so should not have disconnected. 12 Jul, CS: Do you know what was the battery level for both radio and Phone ? Marjon: The 1300 mAH batteries where fully charged and since this started from beginning of hike I don't believe battery could have been the issue. 18 jul, XY: app issue fixed 1.2 47
413 | Location sharing | 2018-07-06 | BETA | iOS 1244 | 2 | Location sharing: delay in showing gps on screen when you press the easy pairing button | Yes | N |  | Closed | N/A | not duplicate. 10 jul, XY: This shd be radio fw issue, flw up with ZhuYong 24 Jul, XY: cannot duplicate
414 | Location sharing | 2018-07-06 | BETA | iOS 1244 | 1 | Location sharing: even though GPS showed up, did not resulted in sharing my location with others in my group. | Yes | N |  | Closed | N/A | not duplicate, while if in GROUP, where the MAP view displaying more than 1 or more members are activated, not nessecary all will recievied the GPS update. 10 jul, XY: Could be due to connection lost issue 12 Jul, CS: not able to reproduce the issue at the moment 24 Jul, XY: cannot duplicate
415 | Maps | 2018-07-06 | BETA | iOS 1244 | 1 | Maps: not clear how to open share sheet or show on map. need to distinguish and explain how to do both. watching participants do this took at least 5 tries. | Yes |  |  | Closed | N/A | not understand. need to get more info from Marjon 11 Jul, Marjon: If you want to share a map or track in my maps and click on it, in stead of the selection window of users to share with, it opens the map or track on the map. Only sometimes it does not, so not clear how to drive 'sharing' versus 'opening map" 11 Jul, SK: Kindly do review the demo of opening and sharing of the Track--> https://drive.google.com/drive/folders/1uNyaiRcHRmk3oKR9tIZsTx2Q_q-p2BUA 12 Jul, Marjon: 12 Jul, CS: When you are in offline Map, you won't see "Show on map" option. You can either click on the share icon to share or click anywhere in the offline map selection (besides the share icon) to open up the map. For "Show on map" option, it is only available in Select Track menu, where you can choose which tracks you want to see. This is correct behavior 17 Jul, LeeSun: Eye icon is to turn on and off the selected tracks, whereas for Maps, user can only view one map at one time, thus eyes icon does not apply here. Eye icons allow user to turn on multiple tracks within the same map, again this does not applicable to map view. To view the maps, user just need to tap on the map list item (not the Share icon), just like how they read the received message. 18 Jul, CS: Marjon showed us the difficulties in selecting sharing icon in iphone. Sensitivity of seelcting sharing icon has to be improved.
416 | Maps | 2018-07-06 | BETA | iOS 1244 | ENH | Maps sharing: you can share maps without radios on but not pins. first of all this need to be both possible. Secondly even if this was by design, user expect to be able to do this since the same share icon is showing. | Yes |  |  | N/A |  | Only offline Maps and Track can be share in server... Location Pin cannot by design. This is an enhancement feedback, need to detail out how to implement in App.
417 | Maps | 2018-07-06 | BETA | iOS 1244 | 3 | Maps sharing: share icon on my maps uses not the standard share icon for IOS users (box with arrow out) forgot conclusion of this, but believe was discussed before. | Yes | Y |  | Open | Open | not understand 10 Jul, CS: will standardize the icon 18 jul, XY: fixed 1.2 47 18 Jul, CS: icon still not the box with arrow out 26 Jul, XY, This is new feature , not reflecetd in latest VI 26 Jul, Marjon: UI no tclearly defined, Has to be updated to iOS N/Ative icon | 2018-08-03
418 | Maps | 2018-07-06 | BETA | iOS 1244 | 1 | Maps sharing: sharing a pin showed me at that location even though pin was of different location | Yes |  | 18 July 2018 IOS V1.2 (1247) | Closed |  | feedback in issue list #351. Needs time to fix. FT agreed. 10 Jul, CS: fixing is in progress. Will be available in next iOS release 18 jul, XY: finished 1.2 47
419 | Maps | 2018-07-06 | BETA | iOS 1244 | 1 | Pin sharing: when trying to share my location and chat it wouldn't pull up map just black map with pin. Did send it and recipient pulled up a black map with pin | Yes | N |  | Closed |  | not sure is the same case as #316. where this is Map issue, feedback by XY. 11 Jul, Marjon: It is at street view 18 jul, XY: not duplicate 25 Jul, Marjon: it was a pin in Italy. I still have the pin. can I share with you if I add you as member over the internet? what is your phone number.
420 | Maps | 2018-07-06 | BETA | iOS 1244 | 1 | Maps: the recording does not continue when the phone goes in standby, resulting in straight lines everywhere | Yes |  |  | Closed |  | need to check... 10 Jul, CS: feedback to supplier 18 jul, XY: not duplicate
421 | Maps | 2018-07-06 | BETA | iOS 1244, Android | 1 | Maps: track recording not according to actual trail, photos showed the GAIA GPS app location track and the Talkabout track. Talkabout was bouncing around between mountains resulting in unrealistic long distance and total ascent. 25% more than we actually ascented. | Yes | N | 23 July 2018 IOS V1.2 (1248) 24 July 2018 Andriod V2.4 | Closed | Closed | i have no device to compare. 10 jul, XY: can be implemented 18 jul, XY: the algorithm need change ,need FT check
422 | Maps | 2018-07-06 | BETA | iOS 1244 | 2 | Maps: total minutes should become hour, minutes, not just minutes. | Yes |  | 19 July 2018 IOS V1.2 (1247) | Closed | N/A | 10 jul, XY: can be implemented 18 jul, XY: finished 1.2 47
423 | Maps | 2018-07-06 | BETA | iOS 1244 | ENH | Maps: user should be able to change walker icon on track to bicycle for bike rides | Yes |  |  | N/A | N/A | enhancement??? 10 jul, CS: This is new proposal, need to define detailed implementation.
424 | Maps | 2018-07-06 | BETA | iOS 1244 | 2 | Maps: location pin does not show with correct N/Ame in chat, just as location pin,N/Ame should go with it. |  |  |  | Closed |  | not duplicate 10 jul SK: is it saved location pin or just the location pin opened in chat mode ? 11 Jul SK: We cannot duplicate.. Please do review the video captured in this Link --> https://drive.google.com/drive/folders/1uNyaiRcHRmk3oKR9tIZsTx2Q_q-p2BUA
428 | Settings | 2018-07-13 | BETA | iOS (1244), Android | 3 | Radio settings: Allow a touch and hold/slide left or right to scrub faster to higher numbers. Channel and Sub Code didn't always hold on choice after moving to next adjustment. Sometimes would "rubber band" to another number after release or pause.This also happened on Call tone and VOX. | Yes | N |  | Closed | Closed | 18 jul, XY: app need follow radio , It's normal case 24 Jul CS: This is a Beta feedback issue, need to be fixed. Video uploaded at: https://drive.google.com/open?id=1yZSnE7TCkeLk_vrTPStu9YEf_6tmpmmH | 2018-08-10
429 | On Boarding | 2018-07-13 | BETA | iOS (1244) | 2 | First make sure BT is disbaled at control center. Next go to Settings and eN/Able BT. Then Launch Talkabout app and observed that setup is stuck at EN/Abling BT page. | Yes | N |  | Closed | N/A | 18 Jul, XY: iOS 11 bug, no workaround solution 18 Jul, SK: when issue is reproduced, try pair with other BT device, it can be paired 24 Jul, XY: 这个问题是IOS 系统的问题，参考https://forums.developer.apple.com/message/300002#300002 24 Jul, CS: We urge to look for workaround solution, as we did not see this issue when pairing with BT headset. 31 JUl, CS: request SK to send steps to XY 13 Aug, XY: This is same issue for other BLE app. Caused by iOS bug. | 2018-08-15
430 | Maps | 2018-07-17 | BETA | iOS, Android | 3 | Change the View icon in Maps (second icon at right side) to Group Member icon. | Yes | Y |  | Open | Open | 17, Jul,XY: new feature, not supported 26 Jul, Marjon: Has to be fixed by D2 1 Aug, CS: This is not captured in the SRS or VI previously | needs 1 week after cost is locked down
437 | Setup | 2018-07-26 | BETA | iOS (1244), Android | 3 | first couple of onboarding screens are flashing too fast | Yes | N |  | Closed | Closed | 26 Jul, CS: confirmed it is an issue, video uploaded at Baidu 31 Jul, CS: Resend to XY | 2018-08-10
438 | maps | 2018-07-26 | BETA | Android V2.3 | 4 | Difficulty with understanding on how to download maps, Add a tip about where to find help Include education tip as last tip in onboarding: Familiarize yourself with the app! Go to Help menu for FAQ’s and tutorial videos. | Yes | Y |  | Open | Open | 26 Jul, CS: This is user familiarity issue. Adding note to FAQ? Jul 27:MM. This is crucial to ensure users accept the app as useful. I will send seperate email to Lee Sun asking her to work on this. 1 Aug, LiN/Ar: we will ask SiauFong to ask Auctus provide quotation based on one paragraph and 5 icons in FAQ | After cost and UI lock down, need 1.5 weeks
439 | keyboard | 2018-07-26 | BETA | Android V2.3 |  | When the keyboard is pulled up, it covers the 'next' button, which user may not know they need to collapse the keyboard to find it. Either when user hit return on keyboard will bring them to the next step or bring the next button above the keyboard. | No | Y |  | Open | Open | 26 Jul, CS: This involves new VI to be updated 26 Jul, MM: not crucial can be future
440 | onboarding | 2018-07-26 | BETA | Android V2.3 | ENH | Allow user to go back to tips at later time (skip and go back) => for future | No | Y |  | Open | Open
441 | radio settings | 2018-07-26 | BETA | Android V2.3 | 3 | Fix slider to go negative per alpha test | Yes | Y |  | Duplicated | Duplicated | 26 Jul, CS: Min and Max shall be truncated, follow the solution propsed in #120 | Same as #120
442 | menu | 2018-07-26 | BETA | Android V2.3 |  | menu should be closed if I enter my member page and N/Avigate back | No | N |  | Closed | Closed | 26 Jul, CS: This is current behavior, not quite understand the exact issue. 26 Jul. MM: sorry not sure what the beta tester meant on this one myself. Hoped the UI team did.
443 |  | 2018-07-26 | BETA | Android V2.3, iOS | 3 | The notification badge (blue dot with count) is not centered on the list. | Yes | N |  | Closed | Closed | 26 Jul, CS: can clarify further? Right now is at bottom right corner, following VI. 26 Jul. MM coming from the UI/UX team (Maggie Wang) was hoping that Lee Sun speaks this language and understands what she meant. I send a follow up email to ask for clarification 27 Jul. See screen shot in consolidated list. seems a bug for some phones. 31 Jul, CS: Pixel 1, Android 8 | 2018-08-10
444 | FAQs | 2018-07-26 | BETA | Android V2.3, iOS | 4 | FAQ's are not very clean and look a bit amateuristic, Improve lay out /font etc. | Yes | N |  | Closed | Closed | 26 Jul, CS: redesign FAQ VI ? 1 Aug, CS: LeeSun will communicate with Auctus on the proposed layout. Font fixing and alignment should not charge for costing. For FAQ alignement, please refer to wireframe_20180718, page 131. | time TBD depends on new layout design to determine the effort
445 | Members | 2018-07-26 | BETA | Android V2.3, iOS | 4 | Sections not understood: What is a group | Yes | Y |  | Open | Open | 26 Jul, CS: This is user familiarity issue. Adding note to FAQ? If yes, then FAQ contents MUST be locked down before 3-Aug-18 1 Aug, CS: | Pending MSI to lock down FAQ content
446 | Members | 2018-07-26 | BETA | Android V2.3, iOS | 4 | Sections not understood: What is a member | Yes | Y |  | Open | Open | 26 Jul, CS: This is user familiarity issue. Adding note to FAQ? If yes, then FAQ contents MUST be locked down before 3-Aug-18 | Pending MSI to lock down FAQ content
447 | Maps | 2018-07-26 | BETA | Android V2.3, iOS | 4 | Sections not understood: What is a geofence | Yes | Y |  | Open | Open | 26 Jul, CS:: This is user familiarity issue. Adding note to FAQ? If yes, then FAQ contents MUST be locked down before 3-Aug-18 | Pending MSI to lock down FAQ content
448 | Maps | 2018-07-26 | BETA | Android V2.3, iOS | 4 | Sections not understood: How to download a map | Yes | Y |  | Open | Open | 26 Jul, CS:: This is user familiarity issue. Adding note to FAQ? If yes, then FAQ contents MUST be locked down before 3-Aug-18 | Pending MSI to lock down FAQ content
449 | Maps | 2018-07-26 | BETA | Android V2.3, iOS | 4 | Sections not understood: How to reN/Ame tracks, maps, pins | Yes | Y |  | Open | Open | 26 Jul, CS:: This is user familiarity issue. Adding note to FAQ? If yes, then FAQ contents MUST be locked down before 3-Aug-18 | Pending MSI to lock down FAQ content
450 | Menu /N/Avigation | 2018-07-26 | BETA | Android V2.3, iOS | 4 | Sections not understood: Multiple users indicated not to be able to figure out how to get back to chat menu | Yes | Y |  | Open | Open | 26 Jul, CS:: This is user familiarity issue. Adding note to FAQ? If yes, then FAQ contents MUST be locked down before 3-Aug-18 | Pending MSI to lock down FAQ content
451 | Maps | 2018-07-26 | BETA | Android V2.3, iOS | 4 | Sections not understood: total ascent (how it is calculated) | Yes | Y |  | Open | Open | 26 Jul, CS: This is user familiarity issue. Adding note to FAQ? If yes, then FAQ contents MUST be locked down before 3-Aug-18 | Pending MSI to lock down FAQ content
452 | Maps | 2018-07-26 | BETA | Android V2.3, iOS | 4 | Sections not understood: how to view the statistics (requires clicking on the icon) but not intuitive | Yes | Y |  | Open | Open | 26 Jul, CS: This is user familiarity issue. Adding note to FAQ? If yes, then FAQ contents MUST be locked down before 3-Aug-18 | Pending MSI to lock down FAQ content
453 | Maps | 2018-07-26 | BETA | Android V2.3, iOS | 4 | Sections not understood: who receives my location when I tap on locate icon | Yes | Y |  | Open | Open | 26 Jul, CS: This is user familiarity issue. Adding note to FAQ? If yes, then FAQ contents MUST be locked down before 3-Aug-18 | Pending MSI to lock down FAQ content
454 | Maps | 2018-07-26 | BETA | Android V2.3, iOS | 4 | Sections not understood: icon of offline map and track is confusing | Yes | Y |  | Open | Open | 26 Jul, CS: This is user familiarity issue. Adding note to FAQ? If yes, then FAQ contents MUST be locked down before 3-Aug-18 | Pending MSI to lock down FAQ content
455 | Maps | 2018-07-26 | BETA | Android V2.3, iOS | 4 | Sections not understood: why are offline map and track features not available | Yes | Y |  | Open | Open | 26 Jul, CS: This is user familiarity issue. Adding note to FAQ? If yes, then FAQ contents MUST be locked down before 3-Aug-18 | Pending MSI to lock down FAQ content
456 | Maps | 2018-07-26 | BETA | Android V2.3, iOS | 4 | Sections not understood: why they can not send an off line map off grid | Yes | Y |  | Open | Open | 26 Jul, CS: This is user familiarity issue. Adding note to FAQ? If yes, then FAQ contents MUST be locked down before 3-Aug-18 | Pending MSI to lock down FAQ content
457 | Chat | 2018-07-26 | BETA | Android V2.3, iOS |  | Sections not understood: Delete chat vs delete chat history is confusing | No | N |  | Closed | Closed | 37 Jul, CS: This is user familiarity issue. Adding note to FAQ? If yes, then FAQ contents MUST be locked down before 3-Aug-18 27 Jul, MM: I reviewed this comment and I think UI already explains when you click on it. adding to FAQ is not needed.
458 | Maps | 2018-07-26 | BETA | Android V2.3, iOS | 4 | Sections not understood: How to share a map (this was iOS user so hopefully fixing the area on where to click and using the familiar share icon will improve this | Yes | N |  | Duplicated | N/A | 26 Jul, CS: This is user familiarity issue. Adding note to FAQ? If yes, then FAQ contents MUST be locked down before 3-Aug-18 Jul 27: this is problem that can not be solved with FAQ. This has to be solved. 1 Aug, CS: share icon issue has been captured in #417 | Pending MSI to lock down FAQ content
459 | Chat | 2018-07-26 | BETA | Android V2.3, iOS |  | Make predefined messages visible in chat rather than keyboard (keyboard should be selection: . RatioN/Ale would be if you want to be quick you use predefined so should be easy accessible. Keyboard means involvement so one more stroke not an issue. | No | Y |  | Open | Open | 26 Jul, CS: redesign current VI ? 27 Jul, MM should be done as soon as possible. But not gating D2
460 |  | 2018-07-26 | BETA | Android V2.3, iOS |  | some unnecessary animation: overflow menu being fly in from the middle of screen. | No | Y |  | Open | Open | 26 Jul, CS: can clarify further? 26 Jul. I have requested clarification and this is answer. I am thinking that it might be unique to Android as I still don't understand. "When you in a message view with someone and taps on the overflow icon: the overflow menu appears from the middle of the screen and float to the top. Typically stock Android just opens the menu right under the overflow icon. Adding animation is not a big deal but the speed of animation may need to be adjusted faster as it is a little slow now and user has to wait for the animation and then select the action." 27 Jul, CS: what does it mean by overflow icon? If not mistaken, we don;t have any animaton in the app. Could you please clarify ? 27 Jul, MM see clarification in email to Lee Sun. Up to Lee Sun to determine severity. I do not have android phone to see. but likely not gating item for D2
461 |  | 2018-07-26 | BETA | Android V2.3, iOS | 3 | Minimum 3 members (appear in the toast) in a group is also not clear. I can select 2 people and the create group screen is saying Total 2 members and I'm allowed to proceed. Also N/Ame should be optioN/Al and I could always go back to add the N/Ame. | Yes | N |  | Closed | Open | 26 Jul, CS: can clarify further? 26 Jul, mm: yes, when you create a group a pop up says you need minimum of 3 members but allos you to create a group while only 2 members are added, so message is not correct. Should say: Minim 3 members including yourself. Or Minimum 2 members. 27 Jul: Please change to: Minimum 2 members are required. (also corrects the grammar) | 2018-08-10
462 |  | 2018-07-26 | BETA | Android V2.3 | ENH | allow more pre defined messages. future | No | Y |  | Open | Open
463 |  | 2018-07-26 | BETA | Android V2.3, iOS |  | users seem to have difficulties finding maps in the search area is this controlled by map box or can we help to improve on this? | No | Y |  | Open | Open | 38 Jul, CS: This is user familiarity issue. Adding note to FAQ? If yes, then FAQ contents MUST be locked down before 3-Aug-18 27 Jul, mm: this is not user familiarity issue but many 'landmarks' or N/Ames are not found in map box. Is this map box map issue?
464 |  | 2018-07-26 | BETA | Android V2.3, iOS |  | message for sharing offline maps in menu is pop up 'feature available when connected to internet). Why in chat when attaching message it just says: feature not available (does not help user understand why and negative) | No | Y |  | Open | Open | 38 Jul, CS: This is user familiarity issue. Adding note to FAQ? If yes, then FAQ contents MUST be locked down before 3-Aug-18 27 Jul, mm: not user familiarity issue, is issue of consistency,notification should be more clear. they already changed the message to: 'feature available when connected to internet' but it does not look very professioN/Al. can we not have the same white overlay as for the message pop up in the menu (same treatment
465 |  | 2018-07-26 | BETA | Android V2.3, iOS |  | request to send location before sending and who to send to (currently not clear where it goes) | No | Y |  | Open | Open | 38 Jul, CS: This is user familiarity issue. Adding note to FAQ? If yes, then FAQ contents MUST be locked down before 3-Aug-18 27 Jul, your suggetion is to send everything to FAQ😀. But obviously that is not good design. It should be intuitive. I don't see this as crucial now but we should think about future updates. If automatic becomes approved, we can elimiN/Ate that you send location out and just let it be a pan to your current location button as it is in google.
466 |  | 2018-07-26 | BETA | Android V2.3, iOS |  | Request share sheet to export GPX files of maps and location pins is not available | No | Y |  | Closed | Closed | 38 Jul, CS: This is user familiarity issue. Adding note to FAQ? If yes, then FAQ contents MUST be locked down before 3-Aug-18 27 Jul, MM: not familiarity issue. Has always been a request. Should be implemented asap but not gating item.
467 |  | 2018-07-26 | BETA | Android V2.3, iOS |  | it's not very clear that you have to go to menu to save a offline map. Usually people will go to map tab and try to find where to create offline map. | No | Y |  | Open | Open | 38 Jul, CS: This is user familiarity issue. Adding note to FAQ? If yes, then FAQ contents MUST be locked down before 3-Aug-18
468 |  | 2018-07-26 | BETA | Android V2.3, iOS |  | after updating to new version, members that were added before are no longer there. Disappeared. | No | N |  | Closed | Closed | 26 Jul, CS: update from which version? This issue has been resolved in recent versions 26 Jul, MM. I am not sure anymore if this happened before or after I deleted the app. Part of me thinks it was before but since I am not sure, will close and monitor if it happens again.
469 |  | 2018-07-26 | BETA | Android V2.3, iOS | 3 | very unclear to various users what using an ID means. Various users tried to send messages using a phone number to users that chose to set up their account with an ID. The fact that that is not possible is not understood. some also wanted to type a N/Ame in field using ID and where frustrated that only the number keyboard comes up. They confused using ID with User ID or user N/Ame. At the very least we need to improve on the ADD NEW MEMBER screen to make it clear what using a phone number or using ID means (using ID is the account ID assigned to the user during set up) Also assign member N/Ame is not clear how that relates to the two above. This seems to be stumbling block for some of the beta users and they think it is not working whereas it is more an issue of not understanding the app. UI team needs to make proposal on how to make this more intuitive. | Yes | Y |  | Open | Open | 26 Jul, CS: This is user familiarity issue. Adding note to FAQ? If yes, then FAQ contents MUST be locked down before 3-Aug-18 Otherwise, need to redefine a new VI to cater for new appearance. 27 Jul, mm: this is big issue for multiple beta testers. adding to FAQ will not solve. Need to redesign the adding member screen and also add wording when setting up the account. Will send email to Lee Sun 31 Jul, CS: breakdowns of these items are shown in #444, 485 and 487 to 491 | pending for ID lock down
470 |  | 2018-07-26 | BETA | Android V2.3, iOS |  | Update tip on Put phone in airplane. Keep Bluetooth on. | No | Y |  | Open | Open | 26 Jul, CS: request to update FAQ ? If yes, then FAQ contents MUST be locked down before 3-Aug-18 27 Jul, MM: more intuitive to do in tip.
471 |  | 2018-07-26 | BETA | Android V2.3, iOS |  | some beta testers find the number of options on the map view overwhelming and think they should be regrouped. Also not always clear difference between pin and my location. I don't have a solution to simplify this and make differences more clear. UI team to think about this. | No | Y |  | Open | Open | 26 Jul, CS: This is user familiarity issue. Adding note to FAQ? If yes, then FAQ contents MUST be locked down before 3-Aug-18. Otherwise, need to redefine a new VI to cater for new appearance. Jul 27 MM: we should not use FAQ as a cruch to fix issues with intuitiveness. this is something to consider for future app updates.
472 |  | 2018-07-26 | BETA | Android V2.3, iOS |  | If I start walking downhill, how can the ascent increase before I go back uphill?=> seems that this functioN/Ality is not working properly | Yes | N |  | Closed | Closed | 26 Jul,CS: how many was the ascent increase? Can share reading before and after ? 27 Jul, MM: obviously it should not go up if someon goes down, is this a lag issue? Have we done sufficient comparison test to check accurate measurements? 31 Jul, CS: I compared with GAIA, the app is also showing increment in ascent when going down hill. request to share out the track file. my maps => my tracks =>click share icon => export by email or others
473 |  | 2018-07-26 | BETA | Android V2.3, iOS |  | sharing location pin goes in to a loop => see this video | No | Y |  | Open | Open | 26 Jul, CS: user needs to tap back arrow on the top left corner Jul 27: MM: good example for a close button for future updates |  | https://drive.google.com/open?id=19Ybiowyj1ckpy7Bw9XyOUaMRVjGmcTPu
474 |  | 2018-07-26 | BETA | Android V2.3, iOS |  | when you select view members it won't show unless you send a message to each other successfully. User expects the moment you click view member to see them. So selecting view member should trigger a ping for location. | No | Y |  | Open | Open | 26 Jul, CS: This is new requirement. 27 Jul, MM: for future updates
475 |  | 2018-07-26 | BETA | Android V2.3, iOS |  | Trackrecording does not allow to move or zoom while recording | No | Y |  | Open | Open | 26 Jul, CS: This is new requirement. 27 Jul, MM: this is useability issue, while recording you should be able to still look where you are going etc. It is possible if you click on the map and get out of the trackrecording notification screen. Just not intuitive so users think they are no longer to do this. How can we make this clearer?
476 |  | 2018-07-26 | BETA | Android V2.3, iOS |  | Track recording not always show track during recording, only after saving. For instance I looked at the track recording during walk and only showed duration 3 min and no line from where I started recording but later on in the walk it does (coming in to view of the screen), not sure if it had to do with the fact that in the beginning I was using airplane mode and later no longer and that allowed it to show real time. But it should be working in airplane mode as that is the typcial use case. | Yes | N |  | Closed | Closed | 26 Jul, CS: So far we don't encounter this, we can try to replicate 27 Jul, SK: Kindly correct me if my step is wrong, because i still cannot see the problem at my side. 1- Set phone in Flight Mode. 2- Launch the Talkabout APP, and connect to the radio. 3- In Maps View, to start TRACK recording. 4- Moving and check the Track Line. (where i can see the Track moving in flight mode) 27 Jul, MM: as follows (no radios involved in this test) 1- Launch the Talkabout APP, and set phone to airplane mode 2- In Maps View, to start TRACK recording. 3- Moving no track line is displayed. Only after turning phone back to online mode, the track shows up. So it did not limit the phone to record it, just to display it. How is airplane mode related to displaying the track?
477 |  | 2018-07-26 | BETA | Android V2.3, iOS |  | How to you indicate that user is no longer online? right now a user still shows even though off line. | No | N |  | Closed | Closed | 26 Jul, CS: If user is offline, the thumbN/Ail color will be dim. This is currently supported in both iOS and Android 26 Jul, Marjon: No, not for me. If you go offline it still is showing. even after pinging again to give system a chance to know they are offline it is still bright. Does not dim. I know we had discuss dimming so it seem that it was defined but not working. 27 Jul, Marjon: Ok. I now see that the color is slightly less bright but no-one will see this as an off line as you likely don't recall the brightness of the color to begin with (difference is very subtle). I suggest we find a better 'dim' indicator, e.g. initial is gray in stead of white.
478 |  | 2018-07-28 | BETA | Android V2.3, iOS | 4 | location pin can only be shared over radio, not network but no indication in the app so users are confused by it. short term we have to have a pop up warning if they try to share without radio network that it can only be done with radio network. Vise versa when you share map and track we need to tell them network is required. | Yes | Y |  | Open | Open | 31 Jul, XY: costing is required 1 Aug, CS: Only Track and offline maps can be shaerd without radio, since it is sent via cloud. For Location Pin, it would require radio network to be present. So propose to put up Pop Up msg for Location Pin sharing when radio is disconnected. | Needs 1 week after cost lock down.
479 |  | 2018-07-28 | BETA | Android V2.3, iOS |  | Change the time stamp on the member icon to not have seconds, makes harder to understand what user is looking at and seems silly given the lag of transmission. | No | Y |  | Open | Open | Jul 27: can be future update.
480 |  | 2018-07-28 | BETA | Android V2.3, iOS | 3 | Time stamps reflecting updated status even if offline | Yes | N |  | Closed | Closed | What I don't understand is that the time stamp of my location, even though I am off line, is up to date to today? What is the behaviour of the time stamp supposed to be? Should it not reflect the most up to date and latest online status? So user can determine if the location is current and if user is offline when he went offline and where he was. On the other phone it does do that but on one of the phones it shows a recent online status without the radio connected (nor able to send member update to the other radio since that one was not connected either. Please explain. Seems like a bug needing fixing. If so, that bug should be a yes before D2. 31 Jul, XY: fixed in Android V2.4 SK please to confirm if it is fixed in Android 2.4 and for iOS check if this issue is seen. |  | image
481 |  | 2018-07-28 | BETA | Android V2.3, iOS | 3 | redirect the link for NO T800 yet on the home welcome screen to: shop.motorolasolutions.com/T800 | Yes | N |  | Closed | Closed |  | 2018-08-10

## Auctus defect tracking
编号 | 项目 | 优先级 | 严重性 | 分类 | 报告日期 | 最后更新 | 摘要 | 状态 | Validity
1 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-02-24 | 2018-03-12 | 关闭程序后再打开，蓝牙不能重新自动连接 | 已解决 | Yes
2 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-02-24 | 2018-03-08 | 点击“AGREE ALL”之前必须点击“I agree to both the terms and privacy policy” | 已解决 | No
3 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-02-24 | 2018-03-08 | 6个Tip页面中第二页的左滑动提示箭头点击没有反应 | 已解决 | Yes
4 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-02-24 | 2018-03-08 | 点击“LEAVE SETUP”和“YES”后应该退出程序 | 已解决 | Yes
5 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-02-24 | 2018-03-12 | 搜索设备页面，“RETRY”按钮总是可用的，并且旋转30秒后不会停止 | 已解决 | Yes
6 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-02-24 | 2018-03-08 | 在获取验证码页面没有输入验证码也能进入程序主页面 | 已解决 | Yes
7 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-02-24 | 2018-03-08 | 获取验证码页面，缺少返回键 | 已解决 | Yes
8 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-02-24 | 2018-03-08 | “USE WITHOUT ACCOUNT” 页面缺少返回键 | 已解决 | Yes
9 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-02-24 | 2018-03-08 | 6个Tip页面中的第一页没有左箭头，第六页没有右箭头 | 已解决 | Yes
10 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-02-24 | 2018-05-06 | 匹配成功时，对讲机上的通道跟代码会自动都变为0，但是手机上的通道却显示1 | 已关闭 | Yes
11 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-02-24 | 2018-05-06 | 根据“Wireframes”文档，在启动模块中点击“DECLINE”或者“LEAVE SETUP”弹出的内容格式不符 | 已关闭 | Yes
12 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-02-24 | 2018-03-12 | 在启动程序模块中，没有提示打开位置服务 | 已解决 | Yes
13 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-02-24 | 2018-03-08 | Tip页面被kill后，重新进入程序应直接进入到Tip页面 | 已解决 | Yes
14 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-02-24 | 2018-05-23 | Tip页面被kill后，有时候对讲机上的蓝牙连接图标状态显示错误 | 已解决 | Yes
15 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-02-24 | 2018-05-06 | 有时候程序与设备配对成功后，点击“TEST”没有反应 | 已关闭 | Yes
16 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-02-26 | 2018-03-08 | 当用户滑动到过Tip页面的第六页后，即使再往前五页滑动，“START”按钮也应该一直出现 | 已解决 | Yes
17 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-02-26 | 2018-03-12 | 有时候对讲机上显示蓝牙已经连接，但是程序上显示的是正在连接 | 已解决 | Yes
18 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-02-26 | 2018-05-17 | 点击“SEARCH PHONE CONTACTS”进入联系人页面，页面没有搜索框 | 已解决 | Yes
19 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-02-26 | 2018-03-12 | 在提示页面的内容中，或者是应用商店的应用名称中“Talkabout”才是正确的，而不是其他的拼写 | 已解决 | Yes
20 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-02-26 | 2018-05-06 | 在更换头像中，使用相机拍照，照片会翻转，角度也会改变 | 已关闭 | No
21 | Moto_talkabout | 中 | 细节 | moto_iOS | 2018-02-26 | 2018-05-06 | 应用程序上，对讲机电池的显示 | 已关闭 | Yes
22 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-02-26 | 2018-05-06 | 在使用搜索电话联系人添加好友的时候，选择带有国家代码的号码，却没有自动替换掉默认的国家代码 | 已关闭 | Yes
23 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-02-26 | 2018-05-06 | 有时候程序会自动断开与对讲机的连接 | 已关闭 | Yes
24 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-02-26 | 2018-05-06 | 点击“TEST”按钮，对讲机上的蓝牙图标闪两次，与“Wireframes”文档上的描述不符 | 已关闭 | Yes
25 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-02-26 | 2018-03-08 | 客户反映蓝牙页面上对讲机电池一直是百分之百是否真实（状态为对讲机与应用程序连接） | 已解决 | Yes
26 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-02-26 | 2018-03-12 | 程序与对讲机连接，但是有时蓝牙设置页面没有显示对讲机电池状态 | 已解决 | Yes
27 | Moto_talkabout | 中 | 细节 | moto_iOS | 2018-02-27 | 2018-05-27 | 关闭对讲机后，蓝牙设置页面的连接状态显示问题 | 已解决 | Yes
28 | Moto_talkabout | 中 | 小调整 | moto_iOS | 2018-02-27 | 2018-03-08 | VOX和iVOX将被合并为一项功能 | 已解决 | No
29 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-02-27 | 2018-05-06 | 有时候在设置页面上进行设置，对讲机上的显示却不一致，是否蓝牙显示本身就有问题？ | 已关闭 | No
30 | Moto_talkabout | 低 | 小错误 | moto_iOS | 2018-02-27 | 2018-05-06 | 少数时候会出现设置程序上的“Call Tone”的时候，对讲机上也只显示“Call Tone”的号数，而没有图标显示 | 已关闭 | No
31 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-02-27 | 2018-05-06 | 双向模式切换到天气模式还没完成 | 已关闭 | Yes
32 | Moto_talkabout | 低 | 细节 | moto_iOS | 2018-02-27 | 2018-05-06 | 在紧急信息的编写中，是否有什么特殊符号等的限制 | 已关闭 | Yes
33 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-02-27 | 2018-03-12 | 紧急信息编辑页面在iphone 5S中的一些显示问题 | 已解决 | Yes
34 | Moto_talkabout | 低 | 细节 | moto_iOS | 2018-02-27 | 2018-05-06 | 在紧急信息编辑页面，编辑完紧急信息后点击保存没有任何提示保存是否成功 | 已关闭 | Yes
35 | Moto_talkabout | 低 | 小错误 | moto_iOS | 2018-02-27 | 2018-03-12 | 使用手机多任务功能结束应用后。再重新打开应用，应用也无法自动与对讲机连接 | 已解决 | Yes
36 | Moto_talkabout | 低 | 小调整 | moto_iOS | 2018-02-27 | 2018-03-14 | 客户对“EASY PAIRING”页面内容显示的疑问 | 已解决 | No
37 | Moto_talkabout | 低 | 小调整 | moto_iOS | 2018-02-27 | 2018-03-12 | 通道，子代码和调用音调的上下限很难知道，应做改正 | 已解决 | Yes
38 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-02-27 | 2018-03-08 | 设置模块的蓝牙设置页面，页眉应该是“BLUETOOTH CONNECTION”而不是“BLUETOOTH SETTINGS” | 已解决 | No
39 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-02-27 | 2018-03-08 | 点击“My Members”里面的任意成员，显示的标题不正确 | 已解决 | Yes
40 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-02-27 | 2018-05-03 | 设置模块中，点击“Radio Settings”进入的页面，右上角缺少“i”图标 | 已解决 | Yes
41 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-02-27 | 2018-05-06 | 应用程序与对讲机连接的一些问题 | 已关闭 | Yes
42 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-02-27 | 2018-03-12 | 在iphone 5S上，使用联系人添加好友页面的返回图标与“SEARCH”重叠 | 已解决 | No
43 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-02-27 | 2018-05-06 | 在术语和隐私策略页面上，背景颜色不正确，字体类型是不正确，按钮的样式也不正确 | 已关闭 | No
44 | Moto_talkabout | 高 | 小错误 | moto_iOS | 2018-02-27 | 2018-05-06 | 当应用程序在搜索配对的时候，少数情况下会出现对讲机突然震动然后关闭的现象 | 已关闭 | No
45 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-02-27 | 2018-03-12 | On pairing page, the "Skip Pairing" button should be same style as the "Test". Follow the Android version. After "Skip Pairing" | 已解决 | No
46 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-02-27 | 2018-05-06 | The Radio with the stair bar - if this is not showing the radio signal, then it should be removed. If it is to show Radio batter | 已关闭 | No
47 | Moto_talkabout | 中 | 新功能 | moto_iOS | 2018-02-27 | 2018-03-14 | 进行权限设置后是否能快速回到应用中？ | 已解决 | Yes
48 | Moto_talkabout | 低 | 小错误 | moto_iOS | 2018-02-27 | 2018-03-12 | Languages - Below the last list menu, the line should not appears (the line below French should not be there). | 已解决 | No
49 | Moto_talkabout | 低 | 小错误 | moto_iOS | 2018-02-27 | 2018-03-12 | Metric - Below is the last list menu, the line should not appears (the line below Imperial should not appears). | 已解决 | No
50 | Moto_talkabout | 中 | 小调整 | moto_iOS | 2018-02-27 | 2018-05-23 | 在设置页面的删除账号页面，当点击“LOG OUT”之后需加提示文字 | 已解决 | Yes
51 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-02-27 | 2018-03-12 | 在使用手机号码登录程序时，点击输入验证码的时候，弹出的键盘样式不正确 | 已解决 | Yes
52 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-02-27 | 2018-03-08 | 在iPhone 5S中，6个Tip页面中的第一页上面的文字与下面的连接重叠 | 已解决 | Yes
53 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-02-27 | 2018-05-06 | 有时候我蓝牙不可用，但是我重新打开应用的时候没有提示要打开蓝牙 | 已关闭 | Yes
54 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-02-27 | 2018-05-06 | iVOX跟VOX的设置问题 | 已关闭 | Yes
55 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-02-27 | 2018-03-14 | 客户反映问题：There is no option to remove photo in profile | 已解决 | No
56 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-02-27 | 2018-05-06 | 不正常的连接 | 已关闭 | Yes
57 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-02-27 | 2018-05-06 | 程序进入后台后再次前台后遇到的问题 | 已关闭 | Yes
58 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-02-27 | 2018-03-12 | 不同情况下在登录页面出现的问题 | 已解决 | Yes
59 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-02-27 | 2018-05-28 | 启动模块中，匹配时出现问题描述1 | 已解决 | Yes
60 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-02-27 | 2018-05-28 | 启动模块中，匹配时出现问题描述2 | 已解决 | Yes
61 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-02-27 | 2018-05-06 | 关于“Call Tone”的设置 | 已关闭 | Yes
62 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-02-27 | 2018-05-06 | Help and Supports 跟 About还没有完成 | 已关闭 | Yes
63 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-02-27 | 2018-03-12 | 在iPhone 5S上的显示问题 | 已解决 | Yes
64 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-02-27 | 2018-05-06 | 不同情况地图显示位置的描述 | 已关闭 | Yes
65 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-02-27 | 2018-03-12 | My Maps --> Offline Maps --> Search Maps进入搜索离线地图页面，点击输入地名没有反应 | 已解决 | Yes
66 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-02-27 | 2018-03-14 | My Maps --> Offline Maps页面右上角的删除图标，用户可能不知道点击他删除 | 已解决 | Yes
67 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-02-27 | 2018-03-15 | My Maps --> My Tracks 页面的“SHOW ON MAP”一直处于可用状态 | 已解决 | Yes
68 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-02-27 | 2018-05-06 | My Maps --> Geofence点击没有反应，还没有完成 | 已关闭 | Yes
69 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-02-27 | 2018-03-12 | 在“Offline Maps”页面，当没有下载好的离线地图时，删除图标不应该出现 | 已解决 | Yes
70 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-02-27 | 2018-03-12 | My Maps - Offline Maps - Search Maps - when I key in search - Bayan Baru, it is not working. | 已解决 | Yes
71 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-02-27 | 2018-03-12 | When create 1 offline maps - the list menu should not show the line below | 已解决 | Yes
72 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-02-27 | 2018-05-06 | On the right side of the offline maps save - tap the icon, it does not work. | 已关闭 | Yes
73 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-02-27 | 2018-03-08 | 在“My Tracks”页面，当没有轨迹地图时，删除图标不应该出现 | 已解决 | Yes
74 | Moto_talkabout | 中 | 小调整 | moto_iOS | 2018-02-27 | 2018-03-08 | 在“My Location Pin”页面，当一天中有很多位置时，容易混乱 | 已解决 | Yes
75 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-02-27 | 2018-05-03 | My Maps --> Purchase Map Types点击没有反应，还没有完成 | 已解决 | Yes
76 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-02-27 | 2018-03-12 | “App Setting”的Auto Update Location的滑动条有问题 | 已解决 | Yes
77 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-02-27 | 2018-03-09 | Map Styles 跟 View Members的弹出框不应该挡住按钮 | 已解决 | Yes
78 | Moto_talkabout | 中 | 新功能 | moto_iOS | 2018-02-27 | 2018-05-06 | My Tracks - Is it possible to add a time to each track? Can the track color shown on the icons? | 已关闭 | No
79 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-02-27 | 2018-05-06 | Geofence - After I click SHARE, there is no confirmation. Not sure I manage to share. | 已关闭 | No
80 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-02-27 | 2018-05-06 | In the "My Track" and "My pin" Settings name page, more than 32 bytes can also be saved. That's wrong | 已关闭 | No
81 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-02-28 | 2018-05-06 | Some messages take long to receive and won't show message receive notification even though they were received by other radio | 已关闭 | No
82 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-02-28 | 2018-03-14 | 重命名的成员，其名字不能在聊天页面中刷新显示 | 已解决 | Yes
83 | Moto_talkabout | 中 | 小调整 | moto_iOS | 2018-02-28 | 2018-05-06 | 关于客户提出对重发消息的问题 | 已关闭 | Yes
84 | Moto_talkabout | 低 | 小错误 | moto_iOS | 2018-02-28 | 2018-05-06 | The typing window should be rounded front and back. Now it is square with small corner. | 已关闭 | Yes
85 | Moto_talkabout | 低 | 小错误 | moto_iOS | 2018-02-28 | 2018-03-12 | Chat bubble shape is still not perfect round. It is squashed. | 已解决 | Yes
86 | Moto_talkabout | 低 | 小错误 | moto_iOS | 2018-02-28 | 2018-03-08 | Chat bubble time stamp font color should be grey #A8AAAD. Please refer guideline. | 已解决 | Yes
87 | Moto_talkabout | 中 | 小调整 | moto_iOS | 2018-02-28 | 2018-05-06 | Predefined Message - Can user predefined their own message? | 已关闭 | Yes
88 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-02-28 | 2018-03-08 | This "Net Chat" page is missing "Great Group" | 已解决 | Yes
89 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-02-28 | 2018-05-06 | 关于接收者接收离线地图跟位置等的问题 | 已关闭 | Yes
90 | Moto_talkabout | 高 | 小错误 | moto_iOS | 2018-02-28 | 2018-03-12 | Unable to read complete message. Using iphone 5S. | 已解决 | Yes
91 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-02-28 | 2018-05-06 | 有时候发送的信息会丢失 | 已关闭 | Yes
92 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-02-28 | 2018-03-08 | 在“Shout”中，当聊天记录为空时，点击“Delete Chat History”不应该提示是否删除聊天记录 | 已解决 | Yes
93 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-02-28 | 2018-05-06 | Wrong GPS reading | 已关闭 | Yes
94 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-02-28 | 2018-03-12 | 使用iPhone 5S，在“Shout”中查看消息，消息有重叠 | 已解决 | Yes
95 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-02-28 | 2018-03-08 | It does not show the shout message is from who | 已解决 | Yes
96 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-02-28 | 2018-05-06 | In Shout, share Offline Map. Rx side does not get anything. Note: Receive side is Android phone. | 已关闭 | Yes
97 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-02-28 | 2018-03-15 | 在“Shout”中，没有消息发送通知 | 已解决 | Yes
98 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-02-28 | 2018-03-14 | “SELECT TRACKS” page, click the return selection to display the map page, and all will be reset to hide | 已解决 | Yes
99 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-02-28 | 2018-03-13 | 在“View Members”中，还不能显示成员的位置 | 已解决 | Yes
100 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-02-28 | 2018-05-06 | 在组内发消息的时候，有些消息已经发送成功，接收者已经收到了，但是发送者的UI上没有显示发送成功 | 已关闭 | Yes
101 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-02-28 | 2018-05-07 | 组内的成员离开组，到设置模块的“My Member”去查看，仍然能看到那个组的存在，但是点击没有反应 | 已解决 | Yes
102 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-03-01 | 2018-03-09 | 为什么有弹出消息迫使用户登录的时候要访问照片/媒体 | 已解决 | Yes
103 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-03-01 | 2018-03-01 | 当用户滑动到过Tip页面的第六页后，即使再往前五页滑动，“START”按钮也应该一直出现 | 已解决 | Yes
104 | Moto_talkabout | 高 | 小错误 | moto_android | 2018-03-01 | 2018-07-11 | 在Android7.0上面，应用程序无法与对讲机配对 | 已关闭 | Yes
105 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-03-01 | 2018-06-30 | 在术语和隐私策略页面上，背景颜色是错误的，当我轻敲页面的时候，最后一句话会闪 | 已解决 | Yes
106 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-03-01 | 2018-06-30 | 创建账号的时候，默认国家代码为什么是+1，而且选择的国家代码有限 | 已解决 | Yes
107 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-03-01 | 2018-03-09 | 创建账号的时候，点击“LOGIN”之后弹出的窗口，他的样式可以自定义吗？还是遵循手机安卓系统？ | 已解决 | Yes
108 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-03-01 | 2018-03-14 | Tip页面的第一页不应该有左提示按钮，第六页不应该有右提示按钮，且点击按钮应该起作用 | 已解决 | Yes
109 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-03-01 | 2018-03-14 | 客户关于对讲机电池显示状态的建议 | 已解决 | Yes
110 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-03-01 | 2018-03-05 | The Radio Settingss icon is wrong. | 已解决 | Yes
111 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-03-01 | 2018-03-14 | 客户关于关闭WIFI跟数据流量时获取验证码的疑问 | 已解决 | Yes
112 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-03-01 | 2018-03-02 | 获取验证码失败的窗口提示 | 已解决 | Yes
113 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-03-01 | 2018-03-05 | 杀死程序后在进入程序，会从启动页开始进入程序 | 已解决 | Yes
114 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-03-01 | 2018-03-01 | 将按钮从“CONTINUE”更改为“NEXT” | 已解决 | Yes
115 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-03-01 | 2018-03-01 | 关于应用程序对对讲机的联机问题 | 已解决 | Yes
116 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-03-01 | 2018-03-14 | in radio setting from VI vox and ivox same row in app is separate . | 已解决 | Yes
117 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-03-01 | 2018-03-02 | 提示开启蓝牙的是提示窗口没有出现 | 已解决 | Yes
118 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-03-01 | 2018-03-02 | 启动配对失败，会一直出现请求访问媒体/照片的弹窗 | 已解决 | Yes
119 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-03-01 | 2018-03-12 | 选择删除帐户时，对讲机上的蓝牙连接不会立即断开 | 已解决 | Yes
120 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-03-01 | 2018-03-12 | 在设置页面，名称显示有错误，并没有将太长的名称做剪切，覆盖的到了下面的布局 | 已解决 | Yes
121 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-03-01 | 2018-03-02 | 在设置页面的页眉显示信息的地方，“ID”这个词没有写 | 已解决 | Yes
122 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-03-01 | 2018-03-02 | 在设置页面的页眉显示信息的地方，“Disconnected”写错成了“DisConnected” | 已解决 | Yes
123 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-03-01 | 2018-03-01 | 点击“Myself”进入个人信息编辑页面，名字的设置长度没有限制，不符合需求 | 已解决 | Yes
124 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-03-01 | 2018-03-02 | Myself - I have never set any picture. How come there is a picture inside my profile? | 已解决 | Yes
125 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-03-01 | 2018-03-02 | 在“Myself”里面，默认的头像边框颜色应该是下面选项的第一个，并且应该要有标记出来当前选的是哪一个 | 已解决 | Yes
126 | Moto_talkabout | 中 | 细节 | moto_android | 2018-03-01 | 2018-03-14 | 客户反映关于选择并裁剪头像时的细节问题 | 已解决 | Yes
127 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-03-01 | 2018-03-02 | 在“Myself”中设置好自己的资料后，点击返回按钮应该回到设置主页面 | 已解决 | Yes
128 | Moto_talkabout | 低 | 小错误 | moto_android | 2018-03-01 | 2018-03-02 | 我已经在“Myself”里面更改了头像，但每次我再点击进入“Myself”的时候总会先闪过一下默认头像才显示出更改的头像 | 已解决 | Yes
129 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-03-01 | 2018-03-14 | 在“My Member”里面，单击垃圾箱图标后，能够选择的成员列表，最后一行不应该有一条横线 | 已解决 | Yes
130 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-03-01 | 2018-03-01 | My Members --> Add Members --> Search phone contacts，跳转到联系人列表添加成员还没有完成 | 已解决 | Yes
131 | Moto_talkabout | 低 | 小错误 | moto_android | 2018-03-01 | 2018-03-02 | “My Member”里面的已成员都有默认的图片头像，应该跟IOS一样使用一个logo | 已解决 | Yes
132 | Moto_talkabout | 低 | 小错误 | moto_android | 2018-03-01 | 2018-03-01 | 在我的成员联系列表上，点击成员的名字，头像圈的颜色会改变。如果我不设置任何颜色，颜色会一直变化。 | 已解决 | Yes
133 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-03-01 | 2018-03-02 | Hamburger menu --> My Members --> Click on any member name --> the title shows MYSELF. | 已解决 | Yes
134 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-03-01 | 2018-03-02 | The Vibracall, Keypad tone switch should be same design as IOS. | 已解决 | Yes
135 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-03-01 | 2018-03-01 | 在设置页面编辑紧急消息并点击“SAVE”之后，没有什么任何反应向用户表示这已经成功地保存 | 已解决 | Yes
136 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-03-01 | 2018-03-01 | 编辑紧急消息页面的编辑输入框里“Name”写错成了“Nmae” | 已解决 | Yes
137 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-03-01 | 2018-07-02 | “App Settings”里面只完成了“Delete Account”, 请及时完成其他功能 | 已关闭 | Yes
138 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-03-01 | 2018-03-01 | “Radio Settings”里面的”EASY PAIRING”还没有完成，请及时完成 | 已解决 | Yes
139 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-03-01 | 2018-03-14 | 在“Radio Settings”里面的“WEATHER”页面，我没有做任何操作，他会自己发消息 | 已解决 | Yes
140 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-03-01 | 2018-03-01 | 在“Radio Settings”里面的“WEATHER”页面，“i”图标的功能没有完成 | 已解决 | Yes
141 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-03-01 | 2018-03-02 | Hamburger menu --> Bluetooth Connection --> click on the top left arrow back button，应该回到设置主页面 | 已解决 | Yes
142 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-03-01 | 2018-03-01 | 在“Bluetooth Connection”的连接状态显示问题 | 已解决 | Yes
143 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-03-01 | 2018-03-14 | Power off radio, APP side still showing status Connected for few seconds. The connection status sync is slow. | 已解决 | Yes
144 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-03-01 | 2018-03-01 | 应用程序不能自动连接对讲机 | 已解决 | Yes
145 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-03-01 | 2018-03-01 | 在“Bluetooth Connection”中只完成了“Test”功能，请尽快完成其他功能 | 已解决 | Yes
146 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-03-01 | 2018-03-01 | 接到电话后，应用程序与对讲机连接问题 | 已解决 | Yes
147 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-03-01 | 2018-03-12 | radio power off but the app still showing connected | 已解决 | Yes
148 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-03-01 | 2018-06-30 | 在“Help and Support”中，页眉的标题不应该有“&”，列表的最后一行也不应该有一条横线 | 已解决 | Yes
149 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-03-01 | 2018-03-14 | App Info is not working | 已解决 | Yes
150 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-03-01 | 2018-06-30 | FAQ and Troubleshooting, and Send Feedback are not working | 已解决 | Yes
151 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-03-01 | 2018-03-09 | 在“Radio Settings”页面的通道与对讲机上的通道显示问题 | 已解决 | Yes
152 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-03-01 | 2018-03-01 | After Bluetooth disconnect, Radio still showing the bluetooth icon blinking. | 已解决 | Yes
153 | Moto_talkabout | 高 | 小错误 | moto_android | 2018-03-01 | 2018-03-01 | Bluetooth connection sometime will auto disconnect. | 已解决 | Yes
154 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-03-02 | 2018-03-02 | 在“Help and Support”的“Motorola Contact Info”页面中的电子邮件地址应该是一个活跃的电子邮件链接 | 已解决 | Yes
155 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-03-02 | 2018-03-02 | 在“Maps”页面中，当点击各个图标时弹出窗口的弹出方式应该参考IOS的弹出方式 | 已解决 | Yes
156 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-03-02 | 2018-03-02 | After rename offline map name, there is no way to hide the keyboard. | 已解决 | Yes
157 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-03-02 | 2018-03-09 | 请把“My Maps”和地图页面的所有“My Waypoints”改成“My Location Pin” | 已解决 | Yes
158 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-03-02 | 2018-03-06 | 在“My Maps”里的“My Track”页面中，点击“SHOW ON MAP”的时候总是跳转到主页面 | 已解决 | Yes
159 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-03-02 | 2018-03-05 | From VI Mapbox Menu only 3 selection from app got 4 selection. | 已解决 | Yes
160 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-03-02 | 2018-03-02 | In the "My Track" and "My pin" Settings name page, more than 32 bytes can also be saved. | 已解决 | Yes
161 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-03-02 | 2018-03-02 | 有时候点击发送消息的时候，应用程序会崩溃退出 | 已解决 | Yes
162 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-03-02 | 2018-03-02 | 聊天界面的消息显示不符合要求 | 已解决 | Yes
163 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-03-02 | 2018-03-05 | In VI chat option only can select "member info & delete chat history " from app got extra "delete chat " | 已解决 | Yes
164 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-03-02 | 2018-03-02 | 在聊天界面，只要你发送消息，无论是否发送成功，UI上都显示消息已经发送成功 | 已解决 | Yes
165 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-03-02 | 2018-03-02 | In android, when "Location" sent, Click on the received map, which is inconsistent with the actual location | 已解决 | Yes
166 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-03-02 | 2018-03-02 | The sent and delivered notification tick color is too close, grey and white. User might not be able to see the different | 已解决 | Yes
167 | Moto_talkabout | 中 | 小调整 | moto_iOS | 2018-03-05 | 2018-03-09 | member name 过长时显示异常 | 已解决 | Yes
168 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-03-09 | 2018-03-09 | NO：210 ADD NEW MEMBERS 编辑名字的时候键盘把编辑框遮了一半 | 已解决 | Yes
169 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-03-09 | 2018-03-09 | Cannot select the Group Chat added in "MY MEMBER" | 已解决 | Yes
170 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-03-09 | 2018-03-09 | On group chat, I am not able to press on the "Group Icon" to view the particular group's detail i.e. member name/ID | 已解决 | Yes
171 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-03-16 | 2018-05-06 | User name can add over than 32 charactoers, it should less than 32 characters | 已关闭 | Yes
172 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-03-16 | 2018-05-23 | 点击进入“Bluetooth Connection”页面，“Status”和“Battery”不会立刻显示 | 已解决 | Yes
173 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-03-16 | 2018-05-06 | default to imperial instead of metric | 已关闭 | Yes
174 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-03-22 | 2018-05-06 | 每次注册登陆后，对讲机默认的Channel跟Sub Code 是0,0 手机上却默认的是1,0 两者显示不一致 | 已关闭 | Yes
175 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-03-22 | 2018-05-15 | Radio setting Keypad tone is ON by default, but the App Keypad Tone is OFF | 已关闭 | Yes
176 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-03-22 | 2018-05-06 | IOS version 10.3.3 and 11.0.3 we have, MAPS > MY TRACK, MY LOCATION PIN, GEOFENCE > cannot do selection | 已关闭 | Yes
177 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-03-22 | 2018-05-06 | Radio pairing does not always work automatically, sometimes requires killing app and turning on/of radio a few times. | 已关闭 | Yes
178 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-03-22 | 2018-05-06 | There is no unread message or incoming message notification when APP is at the background. Wireframes/VI need to be updated | 已关闭 | Yes
179 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-03-22 | 2018-05-06 | sometimes the sent message not deliver to the receiver, if continuesly send a few messages. | 已关闭 | Yes
180 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-03-22 | 2018-03-22 | sometimes the sent message not deliver to the receiver, if continuesly send a few messages. | 已解决 | Yes
181 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-03-23 | 2018-03-23 | Click on the "setting" button next to "SOS" , it goes to radio setting page instead of emergency msg | 已解决 | Yes
182 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-03-22 | 2018-05-06 | This statement appear in Maroon Bells URD but it not implemeted in APP: 同时在没有外部耳机时，只能设置ivox等级,在有外部耳机时，只能设置Vox等级 | 已关闭 | Yes
183 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-04-15 | 2018-05-07 | TERMS AND PRIVACY POLICY 显示问题 | 已解决 | Yes
184 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-04-15 | 2018-05-08 | 定位权限不会动态打开 | 已解决 | Yes
185 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-04-15 | 2018-06-19 | 名字长度限制 | 已关闭 | Yes
186 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-04-15 | 2018-05-04 | shout 界面右上角需要显示垃圾桶图标而不是3个点 | 已解决 | Yes
187 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-04-15 | 2018-05-28 | GEO fence 设置 | 已解决 | Yes
188 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-04-15 | 2018-05-28 | 需要添加编译开关 | 已解决 | Yes
189 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-04-15 | 2018-05-03 | 现在的版本无法接收到offline map 和track信息 | 已关闭 | Yes
190 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-04-15 | 2018-06-06 | 对讲机的软件model 和version 没有显示 | 已关闭 | Yes
191 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-04-15 | 2018-05-08 | Customized Message 编辑 | 已解决 | Yes
192 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-04-15 | 2018-06-06 | track 文件外部分享功能 | 已关闭 | Yes
193 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-04-15 | 2018-05-07 | Pre Redefined is incorrect, should be Predefined messages | 已解决 | Yes
194 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-04-15 | 2018-05-16 | Blutooth Connection 里面选择pairing radio 进入 pairing 界面后，左边的按键需要改成cancel ,点击后回到 Bluetooth connection 界面 | 已解决 | Yes
195 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-04-15 | 2018-05-08 | 第一次进地图，如果没有打开网络需要提示用户 | 已解决 | Yes
196 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-04-15 | 2018-05-23 | 添加联系人 | 已解决 | Yes
197 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-04-15 | 2018-05-07 | 联系人相同的号码，不能重复添加 | 已解决 | Yes
198 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-04-15 | 2018-05-16 | 在消息的菜单里面重命名群组名无效 | 已解决 | Yes
199 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-04-15 | 2018-05-23 | 接收方在重命名名称后，不更新 | 已解决 | Yes
200 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-04-15 | 2018-05-16 | 关闭蓝牙，然后从Bluetooth connection 选择pairing 不会提示打开蓝牙 | 已解决 | Yes
201 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-04-15 | 2018-06-12 | 默认单位为imperial | 已关闭 | Yes
202 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-04-15 | 2018-05-07 | track 里面 需要把 Elevation 改成 'Total Ascent' | 已解决 | Yes
203 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-04-15 | 2018-05-23 | 每次进入Bluetooth Connection model， version， status ，battery都会先试N/A几秒后才跳到正常值 | 已解决 | Yes
204 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-04-15 | 2018-04-15 | GPS 纠偏--没有测试，如果有写纠偏就忽略 | 已解决 | Yes
205 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-04-15 | 2018-05-27 | easy pairing 功能 | 已解决 | Yes
206 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-04-15 | 2018-05-07 | Radio Setting EMERGENCY | 已解决 | Yes
207 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-04-15 | 2018-05-24 | 切换weather mode | 已解决 | Yes
208 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-04-15 | 2018-05-08 | 关闭联系人权限后，添加联系人提示搜索联系人 | 已解决 | Yes
209 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-04-17 | 2018-06-19 | My self 里面的change your name 需要改成Change Profile Name | 已关闭 | Yes
210 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-04-28 | 2018-06-19 | TERMS AND PRIVACY POLICY 里面加上 I agree to both the terms and privacy policy | 已关闭 | Yes
211 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-05-03 | 2018-06-15 | 所有的地图显示都是在Tab 的地图页面上 | 已解决 | Yes
212 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-05-03 | 2018-06-19 | maps view members view or hide 的问题 | 已关闭 | Yes
213 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-05-03 | 2018-06-12 | GEO fence request 需要有 set 和 deny | 已关闭 | Yes
214 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-05-03 | 2018-05-23 | tracks 需要显示 validate time | 已解决 | Yes
215 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-05-03 | 2018-05-27 | 成员离开需要显示到消息列表中 | 已解决 | Yes
216 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-05-03 | 2018-06-19 | online /offline 图标显示 | 已关闭 | Yes
217 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-05-06 | 2018-06-19 | 群组功能 | 已关闭 | Yes
218 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-05-14 | 2018-06-12 | 新建组时，可成功添加1或2个人 | 已关闭 | Yes
219 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-05-14 | 2018-05-31 | 发送群消息时，立即关闭聊天对话框，直接退出系统 | 已关闭 | Yes
220 | Moto_talkabout | 中 | 细节 | moto_iOS | 2018-05-14 | 2018-07-30 | 新增member、group后，立马点开该成员或组的聊天框，未聊天并关闭该聊天框，该成员或信息栏及时出现在chat首页 | 已关闭 | Yes
221 | Moto_talkabout | 低 | 小错误 | moto_iOS | 2018-05-14 | 2018-06-11 | 新增、修改member、group的名字时，可以输入空格，再次打开这个修改界面，name显示为空 | 已关闭 | Yes
222 | Moto_talkabout | 中 | 细节 | moto_iOS | 2018-05-14 | 2018-06-12 | member、group和Shout聊天时，可以输入空格，并发送成功 | 已关闭 | Yes
223 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-05-15 | 2018-05-31 | 不点击agree按钮的页面跳转问题（2个bug） | 已关闭 | Yes
224 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-05-15 | 2018-06-12 | 查询组或成员时，查询框遮住了对应的聊天对话框 | 已关闭 | Yes
225 | Moto_talkabout | 中 | 文字 | moto_iOS | 2018-05-16 | 2018-06-12 | 录制My Tracks时，Total Ascent数据为空 | 已关闭 | Yes
226 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-05-16 | 2018-05-31 | 当保存的My Track名字为空时，其它相关信息也显示为空 | 已关闭 | Yes
227 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-05-16 | 2018-06-13 | 删除MY LOCATION信息时，只能选中一条记录 | 已关闭 | Yes
228 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-05-17 | 2018-05-30 | 当下载离线地图速度慢，Downloading为100%时，点击SAVE按钮没有反应 | 已关闭 | Yes
229 | Moto_talkabout | 高 | 小错误 | moto_iOS | 2018-05-17 | 2018-05-31 | 有时发送My Track信息失败 | 已关闭 | Yes
230 | Moto_talkabout | 低 | 文字 | moto_iOS | 2018-05-17 | 2018-05-30 | 创建账号时，输入错误的验证码，弹出的提示信息与需求中不同 | 已关闭 | Yes
231 | Moto_talkabout | 低 | 文字 | moto_iOS | 2018-05-17 | 2018-05-30 | 建议新增需求中的点击RESEND VERIFICATION CODE后，弹出”The verification code has been sent via sms”（如果不新增，无意中会发送很多条验证码短信） | 已关闭 | Yes
232 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-05-17 | 2018-06-12 | 在组里Add Members，取消已选中的所有人员后，再点击SELECT按钮，出现闪退现象 | 已关闭 | Yes
233 | Moto_talkabout | 低 | 文字 | moto_iOS | 2018-05-17 | 2018-05-30 | 删除Member或Group聊天记录时的提示信息与需求中不一致 | 已关闭 | Yes
234 | Moto_talkabout | 低 | 文字 | moto_iOS | 2018-05-17 | 2018-05-30 | Shout、Member和Group的文本框名与需求中不一致 | 已关闭 | Yes
235 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-05-17 | 2018-06-15 | 当没有网络时，点击Map styles，没有提示用户打开网络 | 已关闭 | Yes
236 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-05-22 | 2018-05-30 | TERMS AND PRIVACY POLICY中，Privacy Policy页面跳转问题 | 已关闭 | Yes
237 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-05-22 | 2018-05-30 | TERMS AND PRIVACY POLICY中，弹出界面滑到最底处，但是前面界面没有滑到最底处，AGREE ALL按钮可用 | 已关闭 | Yes
238 | Moto_talkabout | 中 | 小调整 | moto_iOS | 2018-05-23 | 2018-06-13 | Shout聊天框中，点击清除键后，需求中的提示内容是：clear all shout messages，且No按钮显示为Cancel按钮 | 已关闭 | Yes
239 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-05-23 | 2018-07-24 | Shout、Member和Group聊天框中，点击文本输入框后，再点击return按钮没有反应 | 已关闭 | Yes
240 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-05-28 | 2018-05-28 | APP与对讲机配对前后，各切换一次蓝牙状态，当蓝牙可用也配对失败 | 已解决 | Yes
241 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-05-28 | 2018-05-28 | 当蓝牙为可用状态，一直在旋转配对，没有及时切换到RETRY状态 | 已关闭 | Yes
242 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-05-28 | 2018-05-31 | CREATE ACCOUNT在User name中输入空格，没有提示信息 | 已关闭 | Yes
243 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-05-28 | 2018-05-31 | CREATE ACCOUNT中，多次点击【Login】按钮，点击几次，闪屏几次 | 已关闭 | Yes
244 | Moto_talkabout | 低 | 文字 | moto_iOS | 2018-05-28 | 2018-06-11 | VERIFICATION重发验证码中没有“THE”，与需求中截图不一致 | 已关闭 | Yes
245 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-05-28 | 2018-06-11 | USE WITHOUT ACCOUNT的User name中输入空格，没有提示"Name is required." | 已关闭 | Yes
246 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-05-28 | 2018-06-11 | USE WITHOUT ACCOUNT中，REGISTER按钮显示为“BACK”按钮 | 已关闭 | Yes
247 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-05-28 | 2018-06-12 | ADD NEW MEMBER时，点击SEARCH PHONE CONTACTS,无法修改选中的含有超长字符、特殊字符的电话号码 | 已关闭 | Yes
248 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-05-28 | 2018-06-12 | 建议侧边栏进入MY MEMBERS界面后，Add Member显示为“Add New Member”（需求中的描述） | 已关闭 | Yes
249 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-05-28 | 2018-05-31 | Shout、Member和Group聊天框中，点击Location图标，再点击弹出提示框的OK，关闭当前聊天框 | 已关闭 | Yes
250 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-05-29 | 2018-06-12 | Shout、Member和Group聊天框中，输入文本信息并确定后，没有及时更新信息 | 已关闭 | Yes
251 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-05-29 | 2018-06-12 | Shout、Member和Group聊天框中，当输入信息为空时，没有提示信息，需求中提示“Content is required." | 已关闭 | Yes
252 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-05-29 | 2018-06-11 | 正在录制My Tracks信息时，member、group中对应的Track信息为空，且发送失败 | 已关闭 | Yes
253 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-05-29 | 2018-06-12 | 没有看到My Location Pin的显示、隐藏功能 | 已关闭 | Yes
254 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-05-29 | 2018-06-12 | MY LOCATION PIN的删除问题（3个） | 已关闭 | Yes
255 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-05-29 | 2018-06-12 | OFFLINE MAPS 分享功能不正确 | 已关闭 | Yes
256 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-05-30 | 2018-07-13 | 发送文本、Location Pin信息成功，但是发送的记录和状态有问题 | 已关闭 | Yes
257 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-05-30 | 2018-06-12 | 发送的My Track、Location Pin信息，发送方处有时显示为Geofence Request | 已关闭 | Yes
258 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-05-30 | 2018-07-11 | 有时相互发Location Pin失败 | 已关闭 | Yes
259 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-05-30 | 2018-06-15 | 接收方没有及时收到My Track、Offline Map消息 | 已关闭 | Yes
260 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-05-30 | 2018-07-30 | APP2发送track给APP1，同时APP1在下载离线地图，突然APP1出现闪退现象 | 已关闭 | Yes
261 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-05-31 | 2018-06-12 | 发送的Offline Map信息，发送方处显示为Geofence Request | 已关闭 | Yes
262 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-05-31 | 2018-06-12 | 设置EMERGENCY消息输入超长和特殊字符，再点击手机键盘的删除按钮没有及时响应 | 已关闭 | Yes
263 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-06-01 | 2018-06-15 | 有时分享、发送My Tracks信息不成功 | 已关闭 | Yes
264 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-06-04 | 2018-06-19 | RADIO SETTINGS中设置iVox/Vox信息，在radio上没有看到显示效果 | 已关闭 | Yes
265 | Moto_talkabout | 低 | 文字 | moto_iOS | 2018-06-04 | 2018-06-12 | Location Pin的显示问题 | 已关闭 | Yes
266 | Moto_talkabout | 低 | 小调整 | moto_iOS | 2018-06-05 | 2018-06-12 | 建议修改APP SETTINGS中Units的默认值为Imperial | 已关闭 | Yes
267 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-06-05 | 2018-06-12 | ADD NEW MEMBER时，点击SEARCH PHONE CONTACTS后，无法新增带有“—”的member | 已关闭 | Yes
268 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-06-05 | 2018-06-12 | ADD NEW MEMBER时，通过Using phone number和Using ID可以重复添加同一name的member | 已关闭 | Yes
269 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-06-05 | 2018-06-12 | 修改个人name时，手机键盘挡住了输入框一大半高度 | 已关闭 | Yes
270 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-06-05 | 2018-06-12 | Shout中删除聊天记录的图标显示问题，与需求和设计中不一样 | 已关闭 | Yes
271 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-06-05 | 2018-06-12 | Shout中，点击删除聊天记录图标后，弹出的提示信息刚好遮住“Shout”字迹 | 已关闭 | Yes
272 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-06-05 | 2018-06-12 | 接收方set Geofence成功后，对方处于待机状态，且在APP上没有任何显示 | 已关闭 | Yes
273 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-06-05 | 2018-06-19 | 设置RADIO SETTINGS的iVox/Vox值时，没有任何反应 | 已关闭 | Yes
274 | Moto_talkabout | 低 | 文字 | moto_android | 2018-06-06 | 2018-06-08 | TERMS AND PRIVACY POLICY中有部分字体风格不一致 | 已关闭 | Yes
275 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-06-06 | 2018-06-12 | 点击TERMS AND PRIVACY POLICY的DECLINE按钮，出现闪退现象 | 已关闭 | Yes
276 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-06 | 2018-06-25 | 当PAIRING失败时，图标一直在转 | 已关闭 | Yes
277 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-06 | 2018-06-08 | 当位置信息和蓝牙没有打开，点击PHONE SETUP的NEXT按钮时，没有提示打开位置信息 | 已关闭 | Yes
278 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-06 | 2018-06-08 | 在CREATE ACCOUNT页面输入非法字符，可以进入VERIFICATION界面 | 已关闭 | Yes
279 | Moto_talkabout | 中 | 文字 | moto_android | 2018-06-07 | 2018-06-08 | TERMS AND PRIVACY POLICY的文档内容与规定文档中不一致 | 已关闭 | Yes
280 | Moto_talkabout | 低 | 文字 | moto_iOS | 2018-06-07 | 2018-06-12 | TERMS AND PRIVACY POLICY的第6、7条没有序号 | 已关闭 | Yes
281 | Moto_talkabout | 低 | 细节 | moto_android | 2018-06-07 | 2018-06-08 | TALKABOUT RADIO SETUP中，图片挡住了文字 | 已关闭 | Yes
282 | Moto_talkabout | 低 | 文字 | moto_android | 2018-06-07 | 2018-06-08 | USE WITHOUT ACCOUNT的REGISTER按钮显示为BACK按钮 | 已关闭 | Yes
283 | Moto_talkabout | 中 | 文字 | moto_android | 2018-06-07 | 2018-06-08 | 用户注册后的最后一条TIPS内容不正确 | 已关闭 | Yes
284 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-07 | 2018-06-08 | USE WITHOUT ACCOUNT的User name输入空格，直接进入TIPS界面 | 已关闭 | Yes
285 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-07 | 2018-06-08 | ADD NEW MEMBERS时，点击SEARCH PHONE CONTACTS，出现闪退现象 | 已关闭 | Yes
286 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-07 | 2018-06-11 | 在ADD NEW MEMBERS、CREATE GROUP中输入空格，成功新增成员或组 | 已关闭 | Yes
287 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-07 | 2018-06-11 | 在ADD NEW MEMBERS，新增的成员，应立即显示成员信息框 | 已关闭 | Yes
288 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-07 | 2018-06-29 | 新增的MEMBERS在SELECT MEMBERS和MY MEMBERS界面都显示为在线状态 | 已关闭 | Yes
289 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-07 | 2018-06-29 | SELECT MEMBERS和MY MEMBERS界面自动新增附近的radios成员 | 已关闭 | Yes
290 | Moto_talkabout | 低 | 细节 | moto_iOS | 2018-06-07 | 2018-06-12 | TIPS的第一个界面上有向左的箭头 | 已关闭 | Yes
291 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-08 | 2018-06-26 | 点击RESEND VERIFICATION CODE，弹出的提示框不符合需求定义 | 已关闭 | Yes
292 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-08 | 2018-06-08 | 通过手机通讯录ADD NEW MEMBERS时，如果号码中有特殊字符，新增出现闪退现象 | 已关闭 | Yes
293 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-08 | 2018-06-08 | 在SEARCH PHONE CONTACTS查询框里，建议新增自动检索功能 | 已关闭 | Yes
294 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-08 | 2018-06-11 | GROUP INFO的Group members问题 | 已关闭 | Yes
295 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-08 | 2018-06-11 | 点击member和group聊天框右上角任意选项，没有反应 | 已关闭 | Yes
296 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-08 | 2018-06-19 | Map Styles和View Members的地图和定位问题 | 已关闭 | Yes
297 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-08 | 2018-06-11 | 保存My Track、Location Pin时，删除之前的名字，及时显示My Track 20171111 | 已关闭 | Yes
298 | Moto_talkabout | 中 | 新功能 | moto_iOS | 2018-06-08 | 2018-06-08 | 录制My Tracks时，如果目标一直不动，希望新增提示信息 | 已解决 | Yes
299 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-08 | 2018-06-11 | 通过Using phone number和Using ID无法ADD NEW MEMBERS | 已关闭 | Yes
300 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-11 | 2018-06-19 | 未屏蔽Shout中的My Tracks、Offline Maps发送功能 | 已关闭 | Yes
301 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-11 | 2018-06-19 | 通过ID加的成员发送消息时，还可以看到My Tracks、Offline Maps信息 | 已关闭 | Yes
302 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-11 | 2018-07-02 | 默认情况下member、group和Shout聊天框中，文本输入框的标题和内容与需求不一致 | 已关闭 | Yes
303 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-11 | 2018-06-19 | 有时发送任意member、group消息失败 | 已关闭 | Yes
304 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-11 | 2018-06-19 | member、group发送栏中的前面空白部分太多 | 已关闭 | Yes
305 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-11 | 2018-06-29 | Offline Maps的下载功能问题 | 已关闭 | Yes
306 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-11 | 2018-06-19 | 显示View Members信息，出现闪退现象 | 已关闭 | Yes
307 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-11 | 2018-06-19 | 分享Geofence信息，一直显示为RETRY状态 | 已关闭 | Yes
308 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-11 | 2018-06-26 | 在MYSELF中输入空格、超长字符或特殊字符的Name，保存成功 | 已关闭 | Yes
309 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-06-11 | 2018-06-19 | 重新安装系统后，第一次新增、修改member或group的picture时，弹出的提示信息不一致 | 已关闭 | Yes
310 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-11 | 2018-06-25 | MY MEMBERS的查询功能问题 | 已关闭 | Yes
311 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-11 | 2018-06-29 | 无法打开发送方的Locations信息 | 已关闭 | Yes
312 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-11 | 2018-06-29 | 发送前的Locations信息显示不正确，没有正确显示地图 | 已关闭 | Yes
313 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-11 | 2018-07-02 | 发送超长文本消息，一直显示为RETRY | 已关闭 | Yes
314 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-06-12 | 2018-06-13 | 接收方点击已收到的My Track信息，出现闪退现象 | 已关闭 | Yes
315 | Moto_talkabout | 低 | 细节 | moto_iOS | 2018-06-12 | 2018-06-13 | 当界面上只有一个按钮时，这个按钮的显示风格，还有部分未统一 | 已关闭 | Yes
316 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-06-12 | 2018-06-13 | 点击MY MEMBERS的Search空白部分，弹出CREATE GROUP对话框 | 已关闭 | Yes
317 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-12 | 2018-07-02 | 建议在PAIRING SUCESSFUL中，新增点击UNPAIR后，弹出是否取消配对提示框 | 已关闭 | Yes
318 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-12 | 2018-06-29 | 修改MEMBER INFO、GROUP INFO时，可以输入超长的name | 已关闭 | Yes
319 | Moto_talkabout | 低 | 文字 | moto_android | 2018-06-12 | 2018-07-02 | LOCTION PIN的显示问题 | 已关闭 | Yes
320 | Moto_talkabout | 低 | 文字 | moto_android | 2018-06-12 | 2018-07-02 | 点击Maps图标，保存location时，Location pin 默认名字注意pin的大小写、pin后面加一个空格，且按24小时制显示 | 已关闭 | Yes
321 | Moto_talkabout | 低 | 文字 | moto_iOS | 2018-06-12 | 2018-06-13 | RADIO SETTINGS中Vox/iVox、Dual Watch显示不正确 | 已关闭 | Yes
322 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-13 | 2018-06-24 | RADIO SETTINGS中Channel的取值显示为1-22，实际取值范围为0-23，且设置时数值会随意跳转 | 已关闭 | Yes
323 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-13 | 2018-06-24 | RADIO SETTINGS中Sub Code的取值显示为0-121，实际取值范围为-1-122，且设置时数值会随意跳转 | 已关闭 | Yes
324 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-13 | 2018-06-24 | RADIO SETTINGS中Call Tone的取值显示为0-20，实际取值范围为-1-21，且设置时数值会随意跳转 | 已关闭 | Yes
325 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-13 | 2018-06-24 | RADIO SETTINGS中Vox/iVox的取值显示为0开头，应该显示为off开头 | 已关闭 | Yes
326 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-13 | 2018-06-24 | RADIO SETTINGS中Dual Watch的取值显示Channel（0-22），Subcode（0-121）；需求中只有Channel（1-22），Code（0-121），且实际取值范围也不正确 | 已关闭 | Yes
327 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-13 | 2018-07-02 | RADIO SETTINGS中WEATHER的Weather Channel取值不正确 | 已关闭 | Yes
328 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-13 | 2018-06-29 | 可以在RADIO SETTINGS中EMERGENCY的文本框中输入超长字符 | 已关闭 | Yes
329 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-13 | 2018-06-29 | RADIO SETTINGS中，EMERGENCY的说明文字与ios不一致 | 已关闭 | Yes
330 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-13 | 2018-06-19 | 点击RADIO SETTINGS中EASY PAIRING的任意按钮，没有反应 | 已关闭 | Yes
331 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-06-13 | 2018-06-15 | My Track在地图上的显示，Total Ascent值为空 | 已关闭 | Yes
332 | Moto_talkabout | 低 | 文字 | moto_iOS | 2018-06-13 | 2018-06-15 | 建议修改VERIFICATION下面的验证码第一个单词"Validation"为“Verification” | 已关闭 | Yes
333 | Moto_talkabout | 低 | 文字 | moto_android | 2018-06-13 | 2018-06-19 | SEARCH MAP中卫星街道的第一个单词少了一个“l” | 已关闭 | Yes
334 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-06-13 | 2018-07-30 | 接收方和发送方第一次相互发送信息后，接收方的头像颜色显示为离线状态 | 已关闭 | Yes
335 | Moto_talkabout | 中 | 文字 | moto_iOS | 2018-06-14 | 2018-06-15 | 修改BLUETOOTH CONNECTION说明中最后一句话 | 已关闭 | Yes
336 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-06-14 | 2018-06-15 | 打开已下载的多种OFFLINE MAPS地图模式，只显示同一地图模式 | 已关闭 | Yes
337 | Moto_talkabout | 低 | 文字 | moto_iOS | 2018-06-14 | 2018-06-19 | 建议修改FAQ的第2项第1句括号部分为图标显示 | 已关闭 | Yes
338 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-19 | 2018-07-02 | SEARCH PHONE CONTACTS的查询功能，不支持模糊查询 | 已关闭 | Yes
339 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-19 | 2018-07-02 | 第一次通过通讯录ADD NEW MEMBERS时，如果选择拒绝，再点击SEARCH PHONE CONTACTS，没有反应 | 已关闭 | Yes
340 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-19 | 2018-07-03 | 点击View Members的MORE后，group图标与member图标一样 | 已关闭 | Yes
341 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-19 | 2018-07-03 | View Members中的SELECT MEMBERS不支持模糊查询 | 已关闭 | Yes
342 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-19 | 2018-07-02 | 当MY TRACKS记录为空时，点击SHOW ON MAP直接显示地图 | 已关闭 | Yes
343 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-19 | 2018-07-02 | 建议点击Access Permissions后，新增返回功能 | 已关闭 | Yes
344 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-19 | 2018-06-25 | 点击GEOFENCE的SET按钮，出现闪退现象 | 已关闭 | Yes
345 | Moto_talkabout | 低 | 文字 | moto_android | 2018-06-20 | 2018-06-24 | 当蓝牙未连接，弹出提示框的Permission显示为permissions | 已关闭 | Yes
346 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-20 | 2018-07-02 | SELECT MEMBERS自动加载周边已连接radio的用户为好友 | 已关闭 | Yes
347 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-20 | 2018-07-03 | ADD NEW MEMBERS时，点击SEARCH PHONE CONTACTS新增member，手机通讯录的名字没有自动更新 | 已关闭 | Yes
348 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-20 | 2018-06-26 | 点击USE WITHOUT ACCOUNT左上角的返回按钮，没有反应 | 已关闭 | Yes
349 | Moto_talkabout | 低 | 文字 | moto_android | 2018-06-20 | 2018-06-24 | 为了统一风格，建议修改Shout提示框的Shout为shout、OK为YES | 已关闭 | Yes
350 | Moto_talkabout | 中 | 小调整 | moto_android | 2018-06-20 | 2018-07-02 | Country Code下拉框信息挡住了对应的文本框 | 已关闭 | Yes
351 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-20 | 2018-06-29 | 接收方可以收到Shout消息，但是不显示在聊天框中 | 已关闭 | Yes
352 | Moto_talkabout | 低 | 文字 | moto_android | 2018-06-22 | 2018-06-24 | About中PRIVACY POLICY蓝色部分的显示不一致 | 已关闭 | Yes
353 | Moto_talkabout | 低 | 文字 | moto_android | 2018-06-22 | 2018-06-24 | 建议修改APP INFO的信息显示格式，与ios保持一致 | 已关闭 | Yes
354 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-06-22 | 2018-06-22 | 建议修改FAQ AND TROUBLESHOOTING中Radio链接后，再点击返回按钮的返回页面 | 已关闭 | Yes
355 | Moto_talkabout | 低 | 文字 | moto_android | 2018-06-22 | 2018-06-24 | 为了统一风格，建议修改HELP AND SUPPORT的标题名 | 已关闭 | Yes
356 | Moto_talkabout | 低 | 文字 | moto_android | 2018-06-22 | 2018-06-24 | 为了统一风格，建议修改FAQ AND TROUBLESHOOTING的标题名 | 已关闭 | Yes
357 | Moto_talkabout | 低 | 文字 | moto_android | 2018-06-22 | 2018-06-24 | 为了统一风格，建议修改MOTOROLA CONTACT INFO的蓝色链接部分 | 已关闭 | Yes
358 | Moto_talkabout | 低 | 文字 | moto_android | 2018-06-22 | 2018-06-24 | 为了统一风格，建议修改Map and Location中How do i share a map？的图标颜色 | 已关闭 | Yes
359 | Moto_talkabout | 低 | 文字 | moto_android | 2018-06-22 | 2018-06-24 | FAQ的Messaging中How do i use the emergency message feature of the radio and the App？括号部分不正确 | 已关闭 | Yes
360 | Moto_talkabout | 中 | 文字 | moto_android | 2018-06-22 | 2018-06-24 | BLUETOOTH CONNECTION中Check connection下面的内容不正确 | 已关闭 | Yes
361 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-22 | 2018-07-02 | 默认情况下，MY MAPS的GEOFENCE是关闭状态 | 已关闭 | Yes
362 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-25 | 2018-06-29 | RADIO SETTINGS中Dual Watch的Code显示为Subcode | 已关闭 | Yes
363 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-25 | 2018-06-29 | RADIO SETTINGS中Channel、Code的取值没有括号备注 | 已关闭 | Yes
364 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-26 | 2018-07-04 | PAIRING失败，直接黑屏并退出系统（安卓4.3） | 已关闭 | Yes
365 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-26 | 2018-07-02 | 在WELCOME界面，点击手机的返回按钮，弹出WARNING界面 | 已关闭 | Yes
366 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-26 | 2018-07-02 | 当关掉已连接上的对讲机，状态连接显示为Connecting，且Chat界面的状态显示为已连接 | 已关闭 | Yes
367 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-26 | 2018-07-02 | 点击MYSELF头像框的Album或Camera后，再点击弹出提示框的TURN ON按钮，没有反应 | 已关闭 | Yes
368 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-26 | 2018-07-02 | 默认情况下，MYSELF头像的显示与IOS不一样 | 已关闭 | Yes
369 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-26 | 2018-07-02 | 点击MYSELF头像框的Album或Camera，再点击弹出提示框的TURN ON后，引导用户去打开对应功能 | 已关闭 | Yes
370 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-27 | 2018-07-02 | 点击BLUETOOTH CONNECTION的TEST按钮，没有反应 | 已关闭 | Yes
371 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-27 | 2018-07-02 | BLUETOOTH CONNECTION的TEST按钮的显示风格需与Unpair radio保持一致 | 已关闭 | Yes
372 | Moto_talkabout | 低 | 细节 | moto_android | 2018-06-27 | 2018-07-04 | member、group、shout和myself的信息显示问题 | 已关闭 | Yes
373 | Moto_talkabout | 低 | 细节 | moto_android | 2018-06-27 | 2018-07-04 | member、group菜单栏遮住了member、group名字 | 已关闭 | Yes
374 | Moto_talkabout | 低 | 细节 | moto_android | 2018-06-27 | 2018-07-04 | GROUP INFO的DONE按钮显示不够美观，建议下移该按钮 | 已关闭 | Yes
375 | Moto_talkabout | 低 | 细节 | moto_android | 2018-06-27 | 2018-07-04 | 修改member info、MYSELF的Profile Name时，手机键盘挡住了name横线（魅蓝，note2） | 已关闭 | Yes
376 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-06-27 | 2018-07-30 | 修改MYSELF、member的name后，新名字没有及时更新 | 已关闭 | Yes
377 | Moto_talkabout | 低 | 文字 | moto_android | 2018-06-27 | 2018-07-02 | 建议修改侧边栏radio连接状态为大写字母 | 已关闭 | Yes
378 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-28 | 2018-07-02 | CREATE GROUP选择Group members时，默认选中已新增的所有members | 已关闭 | Yes
379 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-28 | 2018-07-02 | 为了统一风格，建议在头像下，新增members的统计功能 | 已关闭 | Yes
380 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-28 | 2018-07-02 | group Name的输入长度，没有进行数据校验 | 已关闭 | Yes
381 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-28 | 2018-07-02 | 当group的总数为8个或更多数量时，提示信息不正确，请保持与IOS系统一致 | 已关闭 | Yes
382 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-28 | 2018-07-04 | 新增、修改GROUP头像的功能不可用 | 已关闭 | Yes
383 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-28 | 2018-07-04 | 查询过程中的SELECT按钮，建议下移或隐藏 | 已关闭 | Yes
384 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-28 | 2018-07-04 | 新增、修改GROUP时，SELECT MEMBERS的查询功能不可用 | 已关闭 | Yes
385 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-28 | 2018-07-11 | Offline Maps的下载功能和显示问题 | 已关闭 | Yes
386 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-28 | 2018-07-11 | 结束进程，再重新打开Offline Maps，显示的地图区域与已下载地图不一样 | 已关闭 | Yes
387 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-28 | 2018-07-11 | 下载离线地图时，选择地图样式的说明文字style应为复数styles | 已关闭 | Yes
388 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-28 | 2018-07-11 | 下载离线地图时，中途中断下载，弹出的提示信息不正确 | 已关闭 | Yes
389 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-28 | 2018-07-11 | Offline Maps的名字每个单词中间要有一个空格，且应按24小时制显示 | 已关闭 | Yes
390 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-28 | 2018-07-11 | 删除完所有OFFLINE MAPS记录后，建议此时隐藏DELETE按钮 | 已关闭 | Yes
391 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-28 | 2018-07-11 | 魅族note6，安卓7.0，无法下载第3样式地图 | 已关闭 | Yes
392 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-28 | 2018-07-11 | 魅蓝安卓5.1，在SEARCH MAPS中，把地图缩至最小，显示为白屏；之后无法再放大地图 | 已关闭 | Yes
393 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-28 | 2018-07-11 | 下载地图过程中，删除离线地图名字后，手机键盘挡住save按钮 | 已关闭 | Yes
394 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-28 | 2018-07-11 | map名字没有进行数据校验 | 已关闭 | Yes
395 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-28 | 2018-07-11 | 下载完地图后，将下载进度替换成文件大小单位为：MB | 已关闭 | Yes
396 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-28 | 2018-07-02 | 当MY TRACKS记录为空时，My Maps中MY TRACKS的SHOW ON MAP功能不正确 | 已关闭 | Yes
397 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-28 | 2018-07-02 | 建议当MY TRACKS记录为空时，隐藏SHOW ON MAP按钮 | 已关闭 | Yes
398 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-28 | 2018-07-02 | 录制My Track时，Distance数据始终为0.1，Average Speed数据不正确，Elevetion数据始终为空 | 已关闭 | Yes
399 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-28 | 2018-07-02 | 没有看到Maps中GEOFENCE的越界功能 | 已关闭 | Yes
400 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-28 | 2018-07-02 | Maps中GEOFENCE显示为Geofence，建议根据VI改为大写字母 | 已关闭 | Yes
401 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-28 | 2018-07-02 | 默认情况下GEOFENCE的Enable notification、Sound应为打开状态 | 已关闭 | Yes
402 | Moto_talkabout | 低 | 文字 | moto_android | 2018-06-28 | 2018-07-02 | 已收到的My Tracks信息只显示为My.. | 已关闭 | Yes
403 | Moto_talkabout | 低 | 文字 | moto_iOS | 2018-06-29 | 2018-07-11 | 设置、发送Locations，位置信息关闭时，弹出的提示信息第一个单词不正确 | 已关闭 | Yes
404 | Moto_talkabout | 中 | 小调整 | moto_android | 2018-06-29 | 2018-07-02 | 当位置信息关闭，点击聊天框Locations的√，弹出的提示信息内容不够友好 | 已关闭 | Yes
405 | Moto_talkabout | 低 | 文字 | moto_android | 2018-06-29 | 2018-07-02 | group聊天框的右上角菜单项内容少了Delete Chat选项 | 已关闭 | Yes
406 | Moto_talkabout | 低 | 文字 | moto_android | 2018-06-29 | 2018-07-02 | group聊天框的菜单栏挡住了group名字 | 已关闭 | Yes
407 | Moto_talkabout | 低 | 文字 | moto_android | 2018-06-29 | 2018-07-02 | group名字分2行显示（魅蓝5.1，魅族note6安卓7.0） | 已关闭 | Yes
408 | Moto_talkabout | 低 | 文字 | moto_android | 2018-06-29 | 2018-07-02 | 点击member聊天框右上角选项的Delete Chat弹出的提示框中，Chat应改为小写chat | 已关闭 | Yes
409 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-29 | 2018-07-24 | 关闭位置信息，点击每一个Maps图标，没有提示信息 | 已关闭 | Yes
410 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-29 | 2018-07-24 | 关闭位置信息，点击member、group和shout聊天框的Locations图标，没有提示信息 | 已关闭 | Yes
411 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-29 | 2018-07-24 | 关闭网络，点击Maps的第一个图标，没有提示信息 | 已关闭 | Yes
412 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-29 | 2018-07-24 | 关闭网络，点击OFFLINE MAPS的Search Maps图标，没有提示信息 | 已关闭 | Yes
413 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-29 | 2018-07-24 | 点击member、group聊天框的My tracks、Offline Maps图标，没有提示信息 | 已关闭 | Yes
414 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-29 | 2018-07-02 | 在文本发送框中，member、group和shout的Locaitions和文本信息可以叠加显示 | 已关闭 | Yes
415 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-29 | 2018-07-02 | member、group的My Tracks和Offline Maps可以与文本信息叠加显示 | 已关闭 | Yes
416 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-06-29 | 2018-07-02 | 成功发送组消息后，发送方无法打开My Track和Offline Map | 已关闭 | Yes
417 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-07-02 | 2018-07-04 | 下载Offline Maps时，显示Downloaded，再点击SAVE按钮，出现闪退现象 | 已关闭 | Yes
418 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-07-02 | 2018-07-04 | View Members中选择Hide所有group和member后，地图上仍然有一个浅灰色的圆影（安卓4.4） | 已关闭 | Yes
419 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-07-02 | 2018-07-04 | 切换Map Styles时，只显示第一种Street地图模式（安卓4.4） | 已关闭 | Yes
420 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-07-04 | 2018-07-24 | 修改group时的拍照功能问题（安卓4.4） | 已关闭 | Yes
421 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-07-04 | 2018-07-24 | 新增group时，点击头像的拍照功能，关闭新增框（安卓4.4） | 已关闭 | Yes
422 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-07-04 | 2018-07-24 | 修改member时的拍照功能问题（安卓4.4） | 已关闭 | Yes
423 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-07-04 | 2018-07-11 | 点击Predefined Messages中自定义的超长字符行信息，出现闪退现象（安卓7.0） | 已关闭 | Yes
424 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-07-05 | 2018-07-11 | View Members选择Show member和group时，出现蓝屏现象 | 已关闭 | Yes
425 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-07-05 | 2018-07-11 | Locations中新增的Loaction Pin显示为固定图片 | 已关闭 | Yes
426 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-07-05 | 2018-07-30 | 手机与radio配对失败时，RETRY按钮颜色一直显示为灰色不可用状态（iOS） | 已关闭 | Yes
427 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-07-05 | 2018-07-30 | 接收方的My Track数据显示不正确 | 已关闭 | Yes
428 | Moto_talkabout | 中 | 小调整 | moto_android | 2018-07-05 | 2018-07-11 | 输入文本消息，再点击其它图标时，文本信息应立即被清空 | 已关闭 | Yes
429 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-07-05 | 2018-07-11 | 新增的Offline Maps、My Tracks和Location Pin显示在界面的最后一条记录 | 已关闭 | Yes
430 | Moto_talkabout | 中 | 细节 | moto_iOS | 2018-07-05 | 2018-07-24 | create account和新增member界面的国家代码后面出现3个点 | 已关闭 | Yes
431 | Moto_talkabout | 中 | 细节 | moto_iOS | 2018-07-05 | 2018-07-24 | 成功接收group消息后，对方ID号被遮住了一大半 | 已关闭 | Yes
432 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-07-05 | 2018-07-11 | 隐藏的MY TRACKS记录，在被滑动屏幕的同时，前面2条和最后2条记录又被自动显示 | 已关闭 | Yes
433 | Moto_talkabout | 低 | 文字 | moto_android | 2018-07-05 | 2018-07-11 | 建议修改group右上角菜单栏的Add Member为Add Members | 已关闭 | Yes
434 | Moto_talkabout | 低 | 文字 | moto_iOS | 2018-07-05 | 2018-07-12 | 接收方聊天框中My Track的时间Valid until 03-09-18显示为Valid util2018/9/3 | 已关闭 | Yes
435 | Moto_talkabout | 低 | 文字 | moto_iOS | 2018-07-05 | 2018-07-12 | 接收方新收到的群组消息框藏到输入框后面（ios10） | 已关闭 | Yes
436 | Moto_talkabout | 低 | 文字 | moto_iOS | 2018-07-05 | 2018-07-12 | 发送方发送3行文字，但接收方只显示其中2行（ios10） | 已关闭 | Yes
437 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-07-06 | 2018-07-24 | 点击Create New Group图标，直接退出系统（IOS9） | 已关闭 | Yes
438 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-07-06 | 2018-07-11 | 无法打开TERMS AND PRIVACY POLICY中privacy1@motorolasolutions.com蓝色链接（安卓8.1） | 已关闭 | Yes
439 | Moto_talkabout | 低 | 细节 | moto_android | 2018-07-06 | 2018-07-11 | 输入最大长度的member、group名字，第二排名字只显示一小部分（安卓8、安卓6） | 已关闭 | Yes
440 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-07-06 | 2018-07-11 | Shout、member和group聊天框中Locations地图上没有地图认证图标 | 已关闭 | Yes
441 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-07-06 | 2018-07-30 | 同时下载多个offline maps出现卡住现象，再次下载offline map，弹出系统提示框（4.3） | 已关闭 | Yes
442 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-07-06 | 2018-07-30 | 同时下载多个offline maps出现卡住现象，尤其是下载多个卫星地图的时候（安卓4.3/4.4） | 已关闭 | Yes
443 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-07-06 | 2018-07-30 | 下载offline maps一旦出现卡住，再查看下载地图进度，下载进度骤减 | 已关闭 | Yes
444 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-07-06 | 2018-07-27 | Maps中View Members的Show功能问题 | 已关闭 | Yes
445 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-07-09 | 2018-07-09 | 接收方查看Location Pin时，pin被show member挡住了 | 已关闭 | Yes
446 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-07-09 | 2018-07-09 | 接收方的show member图标，会跟着实时的Location Pin发生位置变化 | 已关闭 | Yes
447 | Moto_talkabout | 低 | 文字 | moto_android | 2018-07-09 | 2018-07-11 | RADIO SETTINGS中EASY PAIRING第2段文字中your radio显示为you radio | 已关闭 | Yes
448 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-07-09 | 2018-07-24 | 接收方收到的track记录数与发送方不一致 | 已关闭 | Yes
449 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-07-09 | 2018-07-24 | 点击接收方的track，日期限制时间突然消失 | 已关闭 | Yes
450 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-07-10 | 2018-07-11 | View Members中，在show member上滑动屏幕的时候会自动显示和隐藏成员记录 | 已关闭 | Yes
451 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-07-10 | 2018-07-30 | 断网时在地图上分享的一条track，联网后一直显示加载状态 | 已关闭 | Yes
452 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-07-11 | 2018-07-30 | 发送下载完的offline map，发送方一直显示发送中状态 | 已关闭 | Yes
453 | Moto_talkabout | 低 | 文字 | moto_iOS | 2018-07-12 | 2018-07-24 | 点击Maps的Location Pin图标，弹出框中说明文字的want显示为what | 已关闭 | Yes
454 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-07-12 | 2018-07-27 | 保存offline map、my track和location pin时，可以输入大于32个字节的名字 | 已关闭 | Yes
455 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-07-12 | 2018-07-24 | 输入最大长度的track、location pin名字，再点击delete按钮，出现半个黑屏现象 | 已关闭 | Yes
456 | Moto_talkabout | 低 | 文字 | moto_android | 2018-07-13 | 2018-07-24 | 为了统一风格，建议修改MYSELF的Change Profile Name为Change profile name | 已关闭 | Yes
457 | Moto_talkabout | 低 | 文字 | moto_android | 2018-07-13 | 2018-07-24 | 为了统一风格，建议修改Member Info的Profile Name为name | 已关闭 | Yes
458 | Moto_talkabout | 低 | 文字 | moto_android | 2018-07-13 | 2018-07-24 | 为了统一风格，去掉Member Info中color前面的your | 已关闭 | Yes
459 | Moto_talkabout | 中 | 小调整 | moto_android | 2018-07-13 | 2018-07-24 | 不选中LOCATION PIN记录，直接点击delete按钮后，按钮直接消失 | 已关闭 | Yes
460 | Moto_talkabout | 低 | 文字 | moto_iOS | 2018-07-13 | 2018-07-13 | 建议修改点击Bluetooth Connection的Unpair radio后，弹出提示框的OK为YES | 已关闭 | Yes
461 | Moto_talkabout | 低 | 文字 | moto_android | 2018-07-13 | 2018-07-24 | 建议修改GEOFENCE中Enable notification下面的说明文字GeoFence为Geo Fence | 已关闭 | Yes
462 | Moto_talkabout | 低 | 文字 | moto_iOS | 2018-07-16 | 2018-07-16 | USE WITHOUT ACCOUNT中第二段说明文字，and后面的文字显示不全（ios9） | 已关闭 | Yes
463 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-07-16 | 2018-07-16 | CREATE ACCOUNT中可以输入超长名字字符（IOS9） | 已关闭 | Yes
464 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-07-16 | 2018-07-16 | USE WITHOUT ACCOUNT可以输入超长名字字符（IOS9） | 已关闭 | Yes
465 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-07-16 | 2018-07-16 | ADD NEW MEMBER、CREATE GROUP中可以输入超长名字字符（IOS9） | 已关闭 | Yes
466 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-07-16 | 2018-07-16 | 当通讯录权限未开启，点击SEARCH PHONE CONTACTS，弹出提示框的your contacts显示为yout Contacts（IOS9） | 已关闭 | Yes
467 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-07-16 | 2018-07-16 | member info、group info可以输入超长名字字符（IOS9） | 已关闭 | Yes
468 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-07-16 | 2018-07-16 | EMERGENCY、text message输入框中可以输入超长信息（IOS9） | 已关闭 | Yes
469 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-07-16 | 2018-07-16 | 可以输入超长My Track、Location Pin名字（IOS9） | 已关闭 | Yes
470 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-07-17 | 2018-07-17 | MY TRACKS的导出功能问题（ios9） | 已解决 | Yes
471 | Moto_talkabout | 低 | 文字 | moto_android | 2018-07-18 | 2018-07-24 | 建议修改Add New Members为Add New Member | 已关闭 | Yes
472 | Moto_talkabout | 中 | 小调整 | moto_iOS | 2018-07-18 | 2018-07-18 | 新增、修改member name为中文名字后，在列表上的显示问题 | 已分配 | Yes
473 | Moto_talkabout | 低 | 文字 | moto_android | 2018-07-19 | 2018-07-24 | APP SETTINGS中Permissions显示为Persissions | 已关闭 | Yes
474 | Moto_talkabout | 低 | 文字 | moto_android | 2018-07-19 | 2018-07-24 | RADIO SETTINGS中EMERGENCY说明文字的code和frequency中间没有空格隔开 | 已关闭 | Yes
475 | Moto_talkabout | 低 | 文字 | moto_android | 2018-07-23 | 2018-07-30 | TALKABOUT RADIO SETUP说明文字的最后一句话the显示为a new | 已关闭 | Yes
476 | Moto_talkabout | 低 | 文字 | moto_android | 2018-07-23 | 2018-07-30 | 第3条TIPS的电池battery显示为batery | 已关闭 | Yes
477 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-07-23 | 2018-07-25 | 新增或修改group、my self头像时，出现黑屏现象（安卓5.1） | 已解决 | Yes
478 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-07-24 | 2018-07-27 | 点击TERMS AND PRIVACY POLICY的邮箱蓝色链接，弹出的界面显示问题 | 已关闭 | Yes
479 | Moto_talkabout | 低 | 小错误 | moto_android | 2018-07-24 | 2018-07-30 | 通过手机通讯录ADD NEW MEMBER时，返回按钮遮住了SEARCH的第一个单词 | 已关闭 | Yes
480 | Moto_talkabout | 低 | 细节 | moto_android | 2018-07-24 | 2018-08-01 | 发送、接收的shout、member和group消息，时间与短信内容相重叠 | 已关闭 | Yes
481 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-07-25 | 2018-07-30 | 下载成功后的Satellite Street地图，显示为Street地图 | 已关闭 | Yes
482 | Moto_talkabout | 低 | 文字 | moto_android | 2018-07-26 | 2018-07-30 | RADIO INFORMATION标题栏显示为BLUETOOTH CONNECTION | 已关闭 | Yes
483 | Moto_talkabout | 低 | 文字 | moto_android | 2018-07-26 | 2018-07-30 | set as leader、Set as Member弹出的成功框里，最后一句话的to do显示为todo | 已关闭 | Yes
484 | Moto_talkabout | 低 | 文字 | moto_iOS | 2018-07-27 | 2018-07-27 | 点击ADD NEW MEMBER的SEARCH PHONE CONTACTS,弹出提示信息的your显示为yout | 已分配 | Yes
485 | Moto_talkabout | 低 | 文字 | moto_iOS | 2018-07-27 | 2018-07-27 | 点击ADD NEW MEMBER的SEARCH PHONE CONTACTS，建议修改提示信息的Contacts为小写的contacts | 已关闭 | Yes
486 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-07-27 | 2018-07-30 | offline maps的下载进度一直显示为78%或3%（安卓6） | 已关闭 | Yes
487 | Moto_talkabout | 中 | 小错误 | moto_iOS | 2018-07-30 | 2018-07-30 | 在地图上快速查看My Track信息时，track信息的颜色更改部分被遮住 | 已分配 | Yes
488 | Moto_talkabout | 中 | 新功能 | moto_android | 2018-08-01 | 2018-08-01 | 修改WELCOME界面的蓝色链接为shop.motorolasolutions.com/T800 | 已分配 | Yes
489 | Moto_talkabout | 中 | 新功能 | moto_android | 2018-08-01 | 2018-08-01 | 录制track时，目标超过10分钟不动，要提示用户是否暂停录制 | 已分配 | Yes
490 | Moto_talkabout | 中 | 新功能 | moto_android | 2018-08-01 | 2018-08-01 | 手机号码注册的人不能给id注册的成员或都是id注册的组发track和offline map，发送方显示为retry，否则发送成功 | 已分配 | Yes
491 | Moto_talkabout | 中 | 新功能 | moto_android | 2018-08-01 | 2018-08-01 | radio设置，出现设置channel、sub code、call tone、vox和dual watch数值不受控制，随意滑动现象 | 已分配 | Yes
492 | Moto_talkabout | 中 | 新功能 | moto_iOS | 2018-08-01 | 2018-08-02 | 手机蓝牙显示为开启状态，APP却还是提示打开蓝牙（iphone6、iphone8） | 已解决 | Yes
493 | Moto_talkabout | 中 | 新功能 | moto_android | 2018-08-02 | 2018-08-02 | geofence被激活，一旦出界就自动退出程序（Huawei (Andriod 4.4.2)） | 已分配 | Yes
494 | Moto_talkabout | 中 | 新功能 | moto_android | 2018-08-02 | 2018-08-02 | 安装APP成功后，第一次打开APP，弹出提示框的速度太快了 | 已分配 | Yes
495 | Moto_talkabout | 中 | 新功能 | moto_android | 2018-08-02 | 2018-08-02 | Chat界面中未读短信数字，未显示在对应member记录的正中间（Pixel 1, Android 8手机） | 已分配 | No
496 | Moto_talkabout | 中 | 新功能 | moto_android | 2018-08-02 | 2018-08-02 | 新增、修改组员时，修改校验短信3 members为2 members | 已分配 | Yes
497 | Moto_talkabout | 中 | 新功能 | moto_android | 2018-08-02 | 2018-08-02 | 断网时，在CREATE ACCOUNT界面输入用户名和手机号码，再点击LOGIN按钮后，弹出的提示框与IOS不一致 | 已分配 | Yes
498 | Moto_talkabout | 中 | 新功能 | moto_android | 2018-08-02 | 2018-08-02 | 显示View Members，离线用户在地图上也显示为在线状态 | 已分配 | Yes
499 | Moto_talkabout | 中 | 新功能 | moto_android | 2018-08-02 | 2018-08-02 | Help and Support字体要改成Roboto Font | 已分配 | Yes
500 | Moto_talkabout | 中 | 新功能 | moto_android | 2018-08-02 | 2018-08-02 | 结束APP进程后，安卓手机又自动连接上radio（Huawei Y6,Samsung A8） | 已分配 | Yes
501 | Moto_talkabout | 中 | 小错误 | moto_android | 2018-08-03 | 2018-08-03 | 发送方未连接radio的情况下发送track，接收方出现空白聊天记录（安卓6） | 已分配 | Yes

## Summary
iOS |  |  |  | Android
Severity | number of issues | Unresolved | Resolved | Severity | number of issues | Unresolved | Resolved
1 | 67 | 0 | 67 | 1 | 46 | 0 | 45
2 | 150 | 0 | 150 | 2 | 119 | 0 | 118
3 | 110 | 6 | 102 | 3 | 66 | 7 | 69
4 | 32 | 4 | 30 | 4 | 26 | 4 | 32
TOTAL | 359 | 10 | 349 | TOTAL | 257 | 11 | 264
BETA
iOS |  |  |  | Android
Severity | number of issues | Unresolved | Resolved | Severity | number of issues | Unresolved | Resolved
1 | 8 | 0 | 8 | 1 | 1 | 0 | 1
2 | 4 | 0 | 4 | 2 | 0 | 0 | 0
3 | 9 | 0 | 9 | 3 | 9 | 0 | 9
4 | 15 | 0 | 15 | 4 | 16 | 0 | 32
TOTAL | 36 | 0 | 36 | TOTAL | 26 | 0 | 42
Opened Items | Status | Target Closure
Pop up during transmission failure | Completed
FAQ layout refactoring | Android Completed iOS target complete by 28-Sep-18 | 2018-10-10
French Translation | Target ready 12-Oct-18 | 2018-10-10